## Cover
Contract Management Template
<Release Date>

## 1. Contract Inventory
CONTRACT INVENTORY
Contract Inventory | [12 empty] | NaaS Operator
Today's Date | 2020-07-24
Key Contract Data
[5 empty] | Date Contract |  | Contract Term |  | Renewal Notice |  |  |  | Country |  | Est Annual Value |  | Key Contacts
Supplier Name | Contract Name | Contract Type | Services Category | Services Provided | Starts | Ends | Duration | D/W/M/Y | Date | Days Away | Status | Key? | Where Signed | Law Applies | Currency | Amount | Buyer | Supplier
eg. ABC Corp | IT Security Testing 15 May 2017 | MSA | IT Security | IT security testing | 2017-01-01 | 2018-12-31 | 2 | Y | 2018-11-30 | -602 | Active | Y | Australia | Texas USA | USD | 200000 | F Bloggs | P Smith
Note on M11: Rod Linsley: Y if this is a key contract else blank
What's it for?
Record basic details of all contracts of the NaaS Operators

## 2. Confidential Info Register
CONTRACT CONFIDENTIAL INFO
NaaS Operator
Confidential Information Register |  |  |  |  | Confidential Information Disclosed
|  |  | Contract Dates |  | To Supplier |  |  |  | To Buyer
# | Supplier Name | Contract Name | Start | End | Nature of Info | How Disclosed | At End of Term | Done? | Nature of Info | How Disclosed | At End of Term | Done?
1 | eg. ABC Corp | IT Security Testing 15 May 2017 | 2017-07-01 | 2018-06-30 | Custom server build process | Softcopy | Return
Note on G8: Gatekkeeper Guidance: Hardcopy, softcopy, software, hardware device
Note on I8: Gatekeeper Guidance Confirm that end of contract action completed
What's it for?
Identify all Confidential Information disclosed by each party to a contract, to allow compliance with end-of-contract return or destruction obligations

## 3. Contract Change Log
CONTRACT CHANGE LOG
NaaS Operator
Contract Change Log
| Contract |  |  | Change
Supplier Name | Name | From | Change # | Req # | Outline | Date
eg. ABC Corp | IT Security Testing 15 May 2017 | Buyer | 6 | 82 | Update pricing schedules for next year | 2017-12-15
What's it for?
Record summary details of every change made to every contract, to allow Contract Management workload analysis and contract volatility tracking

## 4. Disputes Log
CONTRACT DISPUTES LOG
NaaS Operator
Contract Disputes Log
|  |  | Dispute |  |  |  |  | Resolution |  |  | Managed By
# | Supplier Name | Contract Name | Date | Details | Notifier | Severity | Status | Date | For | Details | For Buyer | For Supplier
1 | eg. ABC Corp | IT Security Testing 15 May 2017 | 2018-01-01 | Supplier alleged to have deliberately charged for services not delivered Q4 2017 | Buyer | High | Resolved | 2018-01-10 | Buyer | Supplier investigations revealed fraudulent activitiy in its Finance team. Staff sacked, corrected invoices reissued | F Bloggs | P Smith
What's it for?
Record details of all formally notified disputes, their progress and any resolution details, to allow relationship volatility tracking

## 5. Events Calendar
CONTRACT EVENTS CALENDAR
NaaS Operator
Contract Events Calendar
Event
Supplier Name | Contract Name | Due On | Details
eg. ABC Corp | IT Security Testing 15 May 2017 | 2018-04-01 | Advise supplier if contract will be renewed or terminated
What's it for?
Record details of all date-driven contract events and associated supporting events, to allow Contract Management workload planning and monitoring

## 6. Issues Log
CONTRACT ISSUES LOG
NaaS Operator
Contract Issues Log
|  |  | Issue |  |  |  |  | Resolution |  |  | Managed By
# | Supplier Name | Contract Name | Date | Details | Notifier | Severity | Status | Date | For | Details | For Buyer | For Supplier
1 | eg. ABC Corp | IT Security Testing 15 May 2017 | 2017-06-01 | Friction between onsite supplier staff | Buyer | Low | Resolved | 2017-06-15 | Buyer | At-fault supplier staff replaced | F Bloggs | P Smith
What's it for?
Record details of all contract-related issues, their progress and any resolution details, to allow contract and relationship volatility tracking

## 7. Lessons Learned Register
LESSONS LEARNED REGISTER
NaaS Operator
Lessons Learned Register
# | Date | Subject Matter Category | Situation Details | Root Cause | Lessons Learned | Keywords (for easy search)
1 | 2017-06-30 | eg. User satisfaction surveys | Supplier strongly disputed that service delivery performance was problematic | Staff members shared their completed survey form with the supplier | 1. Never assume that staff understand what is and isn't confidential 2. Clearly mark all such surveys as 'not to be shared with supplier' and reiterate the message on all emails to survey participants | User satisfaction survey Confidential
What's it for?
Record details of every lesson learned from various situations during the course of business, to provide guidance for the future

## 8. Loaned Items Register
LOANED ITEMS REGISTER
NaaS Operator
Loaned Items Register
Supplier Name
Contract Name
Date Signed
Loaned Items |  |  |  |  | Not Returned
Loaned By | Description | Date Loaned | Loan Period | Date Returned | Reason | Consequence
eg. Buyer | 1 x Dell Latitude E7470 notebook, S/N 123456 1 x building access card, no. 7524 | 2017-09-18 | 12 months
What's it for?
Identify all items loaned by one party to the other during the term of a contract, to ensure the return of those items when due, or payment of any compensation otherwise

## 9. Contract Management Plan
CONTRACT MANAGEMENT PLAN
NaaS Operator
Contract Management Plan
Supplier Name | Contract Name
Lifecycle Stage | Activity | Frequency
Start-up | eg. Onsite kick-off meeting | One-off
Note on A12: Rod Linsley: initiation, negotiation, execution, start-up, operation, renewal, close-out
What's it for?
Record the key high-level activities planned for managing a contract, to allow Contract Management workload planning

## 10. Obligations Compliance Log
CONTRACT OBLIGATIONS COMPLIANCE LOG
NaaS Operator
Obligations Compliance Checking Log
Supplier Name
Contract Name
Obligation |  |  | Checked |  |  | Non-Compliance
Subject Matter | Description | Applies To | Date | By | Outcome | Issues Found | Actions Taken
eg. Payment | No tax invoices to be issued by supplier later than 180 days after provision of the applicable goods and / or services | Supplier | 2018-01-15 | F Bloggs | Non-Compliant | 26 instances of such invalid tax invoices discovered by AP during the measurement period | Invoices not paid. Supplier officially warned about unacceptable behaviour
Note on F12: Rod Linsley: eg compliant part compliant non-compliant
What's it for?
Identify each party's individual and joint contract obligations and rights, to allow Contract Management workload planning and monitoring

## 11. Outstanding Matters Summary
CONTRACT OUTSTANDING MATTERS SUMMARY
NaaS Operator
Oustanding Contract Matters Summary
Supplier Name
Contract Name
Date Signed
Outstanding Matter |  |  |  | Date |  | Applicable Contract
Category | Applicable Clause # | Description | Reason | To Be Addressed | Addressed | Change Request #
eg. SLA implementation | Section E, cl 26-32 | SLA ramp-up timing needs to be finalised | Network inventory analysis needs to be finalised so roll-out plan can be completed | 2018-03-30
Note on G13: Rod Linsley: Identify the contract change used to formally record the conclusion of the outstanding matter
What's it for?
Identify all contract matters to be addressed post-execution, to allow Contract Management workload planning and contract finalisation