## Slide 1: High Level Schedule
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Jan
Dec
Build Project Plan
3 weeks
Headquarters Set-up
6 weeks
Hiring & Staffing
15 weeks
Commercial Agreements
12 weeks
Spectrum Acquisition
16 weeks
Other Resource Acquisition
10 weeks
Network Architecture Definition
14 weeks
Vendor Selection & Onboarding
8 weeks
Network HLD
4 weeks
Network LLD
12 weeks
Site Acquisition & Permits
16 weeks
Hardware Delivery
9 weeks
Site & Fiber Construction
8 weeks
Training & Preparation
8 weeks
Site Deployment
11 weeks
1
2
3, 4
5
6
7
8, 9
11
12,13,14
10
15
16
19
20
17
18
NaaS Initiative Launch
Project Plan Ready
HQ Set-up
TX Provider Agreements
Infra Sharing Agreements
1st Customer Agreement
Minimal Team Onboarding
Spectrum Acquired
Network Architecture Defined
Full Team Onboarded
HLD Ready
Construction Company Onboarded
Deployment Contractors Onboarded
Equipment Vendors Onboarded
Equipment PO Issued
Sites Acquired
Deployment Kickoff
Sites Built
1st Site On-Air
Deployment Complete
Milestones