## Cover
Staffing Plan
<Release Date>

## Instructions
Instructions
This template allows users to develop a Staffing Plan for their initiative. The elements are:
- Revision Control sheet allows to maintain a record of changes made on the document.
- Resource Checklist tab provides a way to register human resources required along with the activities, reporting relationships and onboarding timeframes. Guidance to use the columns of the template is provided below:
Position | Name of the position. Initial Positions are provided for customization
Reports To | Person/organization to whom the position reports. Initial reporting relationships are provided for customization
Management Level | Indication of the level of authority/hierarchy within the organization
Key Activities | Enumeration of the main functions and activities performed by this position. Typical activities are provided as guidance
Count | Number of resources required
On-boarding Date | Deadline to onboard this resource
On-boarding Timeframe | Time to onboard resources with regard to the Project status. (Provided as a guide to establish on-boarding date)
After the template is customized this sheet can be deleted

## Revision Control
Revision Control
Version N° | Issue Date | Status | Reasons for Change

## Staffing Plan
Staffing Plan
Position | Reports To | Management Level | Key Activities | Count | On-boarding Date | On-boarding Timeframe
Managing Director | Board / Investors | Director | .Overall Management .Strategy Definition & Implementation | 1 |  | NaaS Initiative Kickoff
Technical Director | Managing Director | Director | .Lead network and systems decisions .Oversee Engineering, Deployment and Operations | 1 |  | After Strategy & High Level Project Plan definition
Financial/ Commercial Director | Managing Director | Director | .Manage legal, commercial and financial activities | 1 |  | After Strategy & High Level Project Plan definition
Engineering |  |  |  | 0
Engineering Manager | Technical Director | Manager | .Oversee and engage in network planning, design and optimization activities |  |  | Before or during Network Architecture specification
RAN Engineer | Engineering Manager | Individual | .RAN site planning, design and optimization |  |  | Before High Level Design (desired) or Low Level Design starts
Transport Engineer | Engineering Manager | Individual | .Transport network planning, design and optimization |  |  | Before High Level Design (desired) or Low Level Design starts
Core Engineer | Engineering Manager | Individual | .Mobile core planning, design and optimization |  |  | Before High Level Design (desired) or Low Level Design starts
Deployment |  |  |  | 0
Deployment Manager | Technical Director | Manager | .Planning, control and monitoring of network deployment activities |  |  | After Network Architecture specification
Deployment Engineer | Deployment Manager | Supervisor | .Inventory, warehousing and kitting .Site acquisition and construction overseeing .Coordination of I&C tasks |  |  | During High Level Design or immediately afterwards
Integration Engineer | Deployment Manager | Individual | .Support field activties .Remote site integration activities |  |  | During procurement process
Deployment Technician | Deployment Engineer | Individual | .On-site Installation & Commissioning |  |  | During procurement process
Operations & Maintenance |  |  |  | 0
O&M Manager | Technical Director | Manager | .Lead network operations, preventive and corrective maintenance .Manage implementation of network and IT Systems |  |  | After Network Architecture specification
Systems/IT Engineer | O&M Manager | Individual | .Implement, operate and maintain network and IT Systems |  |  | After Network Architecture specification
NOC Operator | O&M Manager | Supervisor | .Monitor network status and performance .Fault Management and Troubleshooting .Coordination of field activities |  |  | During procurement process
Site Technician | NOC Operator | Individual | .Preventive and corrective field maintenance |  |  | During procurement process
Commercial / Business Development |  |  |  | 0
Sales Manager | Financial/ Commercial Director | Manager | .Manage engagement with customers |  |  | After Strategy & High Level Project Plan definition
Sales Executive/ Representative | Sales Manager | Individual | .Point of contact for customers .Billing |  |  | TBD
Procurement Manager/Analyst | Financial/ Commercial Director | Individual | .Supply chain management
Financial & Legal |  |  |  | 0
Financial Specialist | Financial/ Commercial Director | Individual | .Accounting and payments
Legal Associate | Financial/ Commercial Director | Individual | .Manage agreements, permits and other legal issues .Oversee regulatory aspects
Other |  |  |  | 0
Administrative Support | (May vary) | Individual | .Human Resources .Report preparation .Paperwork
TOTAL |  |  |  | 3