## Cover
Deployment Management Worksheet templates
Key for document IDs: | P = Planning; E = Executing; MC = Monitor & Control
TAB | Executive Summary
RACI Chart | Sample RAM (Responsibility Assignment Matrix) for Generic Project
Cost Break Structure | Template to record Work , Services and NetworkMaterials Cost
Resource Plan | Template to elaborate Resource Schedule
Comms Mgmt Plan | Template to record Communications Management plans
Risk Register | Template to records Risks throughout the project lifecycle
Issue Log | Template to record Issues throughout the project lifecycle

## RACI Chart
Project ROLES & RESPONSIBILITIES
Project: NaaS 2020 Transport Project / Date prepared: March 4th, 2020 | [7 empty] | PM: DV
Organization | Operator | [6 empty] | SMEs |  | CONSULTANTS
Group | Engineering |  |  | Commercial |  | DPLY | PMO | PM | Eng. | Engineering |  |  | PM
Name | JMP | LM | MG | AU | SR | RS | JI | JA | FS | MAG | WA | CJ | DV
1) Tech Specs & Site Selection | R | R | A |  |  | C |  | I | I | C | C |  | I
2) Carriers & Regional Projects |  |  |  | R | R | C |  | I | I |  |  |  | I
3) Design Criteria | R | R | A |  |  | C |  | I | C | C | C |  | I
4) Analysis & Design | A | A | A |  |  |  |  | I | A | R | C |  | I
5) Budget Model | A | A | A |  |  | C |  | C | I | R | C |  | I
6) Budget Commercial Inputs (Prices) | R | R | A | A | A | C |  |  |  | I | I |  | I
7) Project Facilitation & Reporting | I | I | I | I | I | I | i | I | I | I | I | I | R
8) Unification of Base of Information | R | R | I |  |  | R |  | A | C | R | R | R | I
9) Data Change Management [Long Term] | R/A | R/A | I |  |  | I |  | I | C |  |  |  | I
Key: | R=Responsible, A=Accountable, C=Consult, I=Inform
Responsible = The person performing the work
Consult = The person who has information necessary to complete the work
Accountable = The person who is answerable to the project manager that the work is done on time, meets requirements, and is acceptable
Inform = This person should be notified when the work is complete

## Resource Plan
Resource Planning Template
Project Title: NaaS Network Deployment ABC |  | Date Prepared: April, 2020
Deployment Phase | Resource | Name | Type | START DATE | END DATE | DURATION in days | COMMENTS
Management | Deployment Manager | Staff | Internal | 2022-01-16 | 2022-02-21 | 36
Network Design | Network Designer RAN | Staff 0 | Internal | 2022-01-18 | 2022-01-21 | 3
Network Design | Network Designer CORE | Staff 1 | Internal | 2022-01-22 | 2022-01-23 | 1
Network Design | Network Designer TX | Staff 2 | Internal | 2022-01-22 | 2022-01-23 | 1
Construction | Tower Construction | Company1 | External | 2022-01-22 | 2022-01-28 | 6
Construction | Fiber Construction | Company2 | External | 2022-01-27 | 2022-01-29 | 2
Installation & Comissionning | Installation | Staff 5 | Internal | 2022-01-28 | 2022-02-04 | 7
Installation & Comissionning | Integrator | Staff 6 | External | 2022-02-05 | 2022-02-09 | 4
Resource 7 | Resource 7 | Staff 7 |  | 2022-01-28 | 2022-02-05 | 8
Resource 8 | Resource 8 | Staff 8 |  | 2022-02-04 | 2022-02-06 | 2
Resource 9 | Resource 9 | Staff 9 |  | 2022-02-07 | 2022-02-10 | 3
Resource 10 | Resource 10 | Staff 10 |  | 2022-02-09 | 2022-02-12 | 3
Resource 11 | Resource 11 | Staff 11 |  | 2022-02-11 | 2022-02-14 | 3
Resource 12 | Resource 12 | Staff 12 |  | 2022-02-15 | 2022-02-17 | 2
Resource 13 | Resource 13 | Staff 13 |  | 2022-02-15 | 2022-02-17 | 2
Resource 14 | Resource 14 | Staff 14 |  | 2022-02-15 | 2022-02-17 | 2
Resource 15 | Resource 15 | Staff 15 |  | 2022-02-15 | 2022-02-17 | 2
Resource 16 | Resource 16 | Staff 16 |  | 2022-02-15 | 2022-02-17 | 2
Resource 17 | Resource 17 | Staff 17 |  | 2022-02-15 | 2022-02-17 | 2

## Cost Breakdown Structure
Cost Breakdown Structure
Project Title: NaaS Network Deployment ABC
Date Prepared: April 20t, 2020
Category | Subcategory | Phase | ID | Concept | Model | Vendor | Unit | Quantity | Cost x Unit | Total | Comments
Network Equipment | RAN | Installation & Commissioning | RRU01 | RAN RRUs | RRUXYZ01 | VendorN | Piece
Network Equipment | Transport | Installation & Commissioning | VSD01 | VSAT Dish | VSATXYZ | VendorY | Piece
Power Equipment | Grid | Installation & Commissioning | PSU01 | PSU | PSUXYZ | VendorN | Piece
Power Equipment | Solar | Installation & Commissioning | SP01 | Panels | PANELXYZBATTERYXZ | VendorZ | Piece
Power Equipment | Solar | Installation & Commissioning | BAT1 | Batteries | BATTERYXYZ | VendorU | Piece
Supporting Infra | Cabinets | Installation & Commissioning | OCN001 | Outdoor Cabinet for Vendor X | CABINETXYZ | VendorV | Piece
Supporting Infra | Ancillaries | Construction | ODF01 | ODF | ODFXYZ | VendorW | Piece
Services | Macro Cell Site Construction | Construction | SER1 | Tower Construction | NA | Tower Company X | Site
Services | Fiber Deployment | Construction | SER2 | Pole Installation & Cabling | NA | Installation Compmany X | Pole
Services | Small Cell I&C | Installation & Commissioning | SER3 | Installation & Commissioning Vendor y | NA | Consultant Company X | Site
Labor | Engineering Resources | Network Design | D1 | Designer | NA | Naas Internal | Hours
Labor | Deployment Resources | Installation & Commissioning | F1 | Field Technician | NA | Naas Internal | Hours
Labor | Management Resources | Management | DM1 | Deployment Manager | NA | Naas Internal | Hours
Labor | Travel Expenses | Installation & Commissioning | TEJ | Travel Expenses Field Technician X | NA | Naas Internal | Month
Labor | Supplies | Installation & Commissioning | SUP1 | Supplies Field Technician X | NA | Naas Internal | Month

## Comms Mgmt Plan
COMMUNICATIONS MANAGEMENT PLAN
Project Title: NaaS Network Deployment ABC
Date Prepared: March 16th, 2020
Stakeholder | Information | Method | Timing or Frequency | Sender
Assumptions |  | Constraints
Glossary of Terms or Acronyms
Attach relevant communication diagrams or flowcharts.

## Risk Register
RISK REGISTER
Project Title: NaaS Network Deployment ABC
Date Prepared: March 16th, 2020
ID | Cause | Event | Risk Owner | Date | Effect | Probability | Impact | Priority | EVM | Strategy and Response Plan

## Issue Log
ISSUE LOG
Project Title: NaaS Network Deployment ABC
Date Prepared: March 16th, 2020
ID | Description | Type | Date Raised | Raised By | Report Author | Priority | Severity | Status | Closure Date
0 | Vendor RFP Responses are all delayed | Problem/Concern | 2020-03-16 | Supply Chain Mgmt. | S.C. Manager | High | Level 2 | Closed | 2020-03-20
1 | Fibers do not match specifications | Off-Specification | 2020-07-16 | Supply Chain Mgmt. | Field Technician | High | Level 0 | Open
2 | Design of Site X must be reworked | Request for Change | 2020-07-20 | Executive Operations | Designer | High | Level 1 | Open