## Table of Contents
Cover
Table of Contents
User Guide
1. Duration Estimating
2. Design Tracking
3. Design Tracking Summary
4. Site Tracking Sheet
5. Summary Tracking Sheet
A. Schedule Visuals
B. Cost & Variance Visuals
C. Deployment KPI's
D. Dashboards
E.Sites Milestones List
Deployment Management Tracking Workseet
Table of Contents

## User Guide
Instructions
All sheets have relations and references between them, as a Deployment Project, is expected to firstly forecast the Duration and Cost using Duration Estimating and Cost Estimating Sheets.
This Worksheet is categorized in Input & Output Sheets:
Input Sheets:
Output Sheets:
Input Sheets
1. Duration Estimating - Use three different Techniques to Forecast duration of a Task.
1.1 Parametric Estimating: Uses an algorithm to calculate cost or duration based on historical data and project parameters (e.g. weight, distance, volume). It uses a statistical relationship between historical data and other variables (e.g. number of sites, kilometers of fiber) to calculate and estimate for activity parameters.
1.2 Analogous Estimating: Estimate duration or cost using historical data from a similar activity or project. It is a gross value estimating approach, sometimes adjusted for known differences in project complexity.
1.3 Three-Point Estimating. A step deeper than Parametric Estimating. Increases the accuracy of single-point estimates by considering estimation uncertainty and risk.
| Record the required input in Cells Mared with following Format: | [6 empty] | Input |  | Input Description is Showed in Column Header :
| Outcome will be showed in Cells with Following Format: | [6 empty] | Output
2. Cost Estimating - Use same Techniques as Duration Estimating but now used to forecast Task Cost with Three Point Estimates, or Calculate Precisely Task Cost with Parametric Estimate.
| Record the required input in Cells Mared with following Format: |  |  |  | Input | Input Description is Showed in the Column Header :
| Outcome will be showed in Cells with Following Format: |  |  |  | Output
3. Design Tracking - Use it to Record Sites Designs Progress, Iterations and Changes.
Input Description is Showed in the Column Header :
| Record the required input in Cells Mared with following Format: |  |  |  | Input
| Outcome will be showed in Cells with Following Format: |  |  |  | Output
4. Design Tracking Summary - Use it to Review Sites Designs Progress. Shows the Required Iterations to finish the design, completion date of last Iteration, Total Days Required to finish all teh Iterations
| Record the required input in Cells Mared with following Format: |  |  |  | Input |  | <
| Outcome will be showed in Cells with Following Format: |  |  |  | Output
5. Site Tracking Sheet - Used to Analyze the Deployment Progress and Performance based on Milestones, It shows planned dates of each Site Milestone , record actual completion dates and review the progress of all Sites.Also shows the Cost Baseline of all Sites and allows to record the Actual Cost
| The Cells in this Sheet shows information based on following Format: |  |  |  |  | Record the required input in Cells Mared with following Format: |  |  | Input
| BaseLine Milestones Date | Actual Milstone Date | KPI | Baseline Cost | Actual Cost
| Calculated with Three Point Estimate | Record Dates Below ↓ |  | Calculated with Three Point Estimate | Record Costs Below ↓ | Outcome will be showed in Cells with Following Format: |  |  | Output
Milestones:
1. Site Design Started: This is a site’s initial milestone, when the particular site’s characteristics and site selection have been confirmed (technical and logistical feasibility), and the network LLD and infrastructure/facility designs have been started.
2. Site Design Ready: A given site reaches this milestone once its LLD is finished, including its Radio Network Design (RND), and Infrastructure/Facility Design has been completed, validated and approved. Next stage is to obtain all necessary permits and prepare all necessary materials, resources and tools.
3. Site Ready for CW (Civil Works). Once all permits, resources, teams, and tools are ready, the site enters this milestone. Now it can be visited by the construction teams or contractors to begin work.
4. Site Ready for Power On. After the site construction or adaptations have been completed, validated and certified according to quality standards established by the project team, it is ready for power connection, or adequation of current power supply.
5. TX Ready. This milestone is reached when the transport provider provisions the transport service whether it starts at the RAN Site or at a transport node, and its connectivity has been tested and certified.
6. Site Ready for Installation. Once all activities related to power on, the contract with the main power company is executed, and all Network equipment is available at the final warehouse. The installation activities can start.
7. Site Ready for Integration. Once the site is powered on, the TX connectivity is ready, and the equipment has been installed and configured on-site, the Network Integration can start; afterwards, the Acceptance Test Protocols are executed as agreed with the NaaS Operator. If there are any faults detected during this stage, they must be corrected before qualifying to the next milestone.
8. Site on Air. Once the site has been integrated to the network, and starts driving traffic, it enters this stage.
6. Summary Tracking Sheet - Used to Review and Track Each Milestone Week By Week
| Milestone_BL | It shows planned number of sites that must Reach each Milestone by week
| Milestone_BL(SUM) | It shows the Accumulated planned number of sites of previous weeks
| Milestone_AC | It shows Actual number of sites that Reach respective Milestone
| Milestone_AC(SUM) | It shows the Accumulated Actual number of sites of previous weeks
| Milestone EV | It shows the Earned Value (EV) of specific week
| MilestoneEV(SUM) | It shows the Accumulated Earned Value (EV) of previous weeks
| MilestoneCostBL | It shows the baseline cost of respective milestone in specific week
| MilestoneCostBL(SUM) | It shows the Accumulated baseline cost of previous weeks
| MilestoneCostAC | It shows the Actual Cost of each Site in respective Milestone for specific week
| MilestonetAC(SUM) | It showsthe Accumulated Actual Cost of each Site in respective Milestone for previous weeks
Output Sheets
Schedule Visuals :Shows track performance through visual interpretation with S-Curve charts, in order to quantitatively forecast future project performance.
Considerations:
. Each “S-curve” represents the planned (baseline) or observed (actual) progress for each milestone. Once sites pass each milestone, they move to the next one, thus starting to contribute to the “S-Curve” of that next Milestone.
. The distance between the starting point of each “S-Curve” and another, is the Activity Duration of the task involved in shifting the site from one Milestone to the next one. The farther apart one S-Curve is to another, the longer is the associated task.
Cost & Variance Visuals : Shows Visual project progress, and compare it against the Cost Baseline based on following Concepts:
Earned Value (EV). Defined as the monetary value of the work achieved so far by the project.
Planned Value (PV). Defined as the monetary value of the work planned to have been delivered by the project in a moment in time.
Actual Cost (AC). Defined as the accumulated costs incurred to deliver the work carried out by the project so far.
Schedule Variance (SV). Defined as the difference between the Earned Value (EV) minus the Planned Value (PV)
Cost Variance (CV). Defined as the difference between the Earned Value (EV) minus the Actual Costs (AC)
Deployment KPIs: Key Performace Indicators Organized by Deployment Phases, Analyze the Dates and Cost Obtained from the Site Tracking Sheet , Remarks shows additional Information of each KPI:
Dashboard: Graphic Representations of KPI's Process Useful Information based on Deployment KPIs and Shows Critical Sites that have the highest Delay in their respective current Milestone.
Deployment Tracking & KPIs
User Guide

## 1. Duration Estimating
DURATION ESTIMATING WORKSHEET
Project Title: NaaS Network Deployment ABC
Date Prepared: March 16th, 2020
Parametric Estimates
ID | Effort Hours | Resource Quantity | % Available | Performance Factor | Duration Estimate
D1 | 2 | 1 | 60% | 85% | 3.9216
Analogous Estimates
ID | Previous Task | Previous Duration | Current Task | Multiplier | Duration Estimate
R1 | 2018 Project Risk Assessment | 4 | 2020 Project Risk Assessment | 1.5 | 6
0
0
0
0
0
0
Three-Point Estimates
ID | Optimistic Duration | Most Likely Duration | Pessimistic Duration | Weighting Equation | Expected Duration Estimate
t0_SiteDesignDelayBL | 1 | 2 | 3 | TTP= (TO+4*TML+TP)/6 | 2
t1_SiteSurveyBL | 1 | 2 | 3 | TTP= (TO+4*TML+TP)/6 | 2
t2a_SiteCWReadinessBL | 1 | 2 | 3 | TTP= (TO+4*TML+TP)/6 | 2
t2_SiteAcquisitionBL | 7 | 10 | 14 | TTP= (TO+4*TML+TP)/6 | 11
t3_CivilWorksBL | 7 | 7 | 10 | TTP= (TO+4*TML+TP)/6 | 8
t4_PowerInstallBL | 3 | 5 | 7 | TTP= (TO+4*TML+TP)/6 | 5
t5_TxintegrationBL | 4 | 6 | 9 | TTP= (TO+4*TML+TP)/6 | 7
t6_InstallationBL | 2 | 3 | 10 | TTP= (TO+4*TML+TP)/6 | 4
t7_IntegrationBL | 2 | 3 | 7 | TTP= (TO+4*TML+TP)/6 | 4
t8_AcceptanceBL | 2 | 3 | 7 | TTP= (TO+4*TML+TP)/6 | 4
t9_HandoverBL | 6 | 8 | 10 | TTP= (TO+4*TML+TP)/6 | 8
Note on B8: Task Unique Identifier
Note on C8: Effort to do the Task for a Single Resource
Note on D8: Quantity of Resources assigned to the Task
Note on E8: Time Availability of the Resources to Assigned to the Task
Note on F8: Planned Productivity over actual Productivity
Note on G8: Result
Note on B18: Activity Unique Identifier
Note on C18: Reference Activity
Note on D18: Reference Duration
Note on E18: Current Activity to be Estimated
Note on F18: Complexity Multiplier using : -Comparative complexity and design; -Differences in the way portions of the work will be performed; -Additions to or omissions from the work of the previous projects; -Geographical and economic data.
Note on G18: Result
Note on B28: Task Unique Identifier
Note on C28: Best forecast in days
Note on D28: Most Likely Duration in Days
Note on E28: Worst scenario to be considered
Note on F28: Three-Point Estimates Formula

## 2. Cost Estimating
COST ESTIMATING WORKSHEET
Project Title: NaaS Network Deployment ABC
Date Prepared: March 16th, 2020
Parametric Estimates
ID | Cost Variable | Cost per Unit | Number of Units | Cost Estimate
ID0 | RRU | 5000 | 150 | 750000
0
0
0
0%
0%
0%
0
0
0
Analogous Estimates
ID | Previous Activity | Previous Cost | Current Activity | Multiplier | Cost Estimate
R1 | 2018 Project Risk Assessment | 500 | 2020 Project Risk Assessment | 1.5 | 750
0
0
0
0
0
0
Three-Point Estimates
ID | Optimistic_Cost | Most_Likely_Cost | Pessimistic_Cost | Weighting_Equation | Expected_Cost_Estimate
c0_SiteDesignCostBL | 300 | 500 | 700 | CTP= (CO+4*CML+CP)/6 | 500
c1_SiteSurveyCostBL | 250 | 500 | 750 | CTP= (CO+4*CML+CP)/6 | 500
c2_SiteAcquisitionCostBL | 350 | 600 | 850 | CTP= (CO+4*CML+CP)/6 | 600
c2a_SiteCWReadinessCost_BL | 100 | 150 | 200 | CTP= (CO+4*CML+CP)/7 | 150
c3_CivilWorksCostBL | 500 | 1500 | 2500 | CTP= (CO+4*CML+CP)/6 | 1500
c4_PowerInstallCostBL | 200 | 500 | 800 | CTP= (CO+4*CML+CP)/6 | 500
c5_TxintegrationCostBL | 300 | 500 | 700 | CTP= (CO+4*CML+CP)/6 | 500
c6_InstallationCostBL | 2250 | 2500 | 2750 | CTP= (CO+4*CML+CP)/6 | 2500
c7_IntegrationCostBL | 250 | 500 | 750 | CTP= (CO+4*CML+CP)/6 | 500
c8_AcceptanceCostBL | 200 | 250 | 300 | CTP= (CO+4*CML+CP)/6 | 250
c9_HandoverCostBL | 100 | 200 | 300 | CTP= (CO+4*CML+CP)/6 | 200
Note on B8: Unique Item Identifier

## 3. Design Tracking
LLD - Design Process Tracking per site
104 | Total LLD Iterations |  |  | Add one row per each Design iteration per site, record the LLDIterationNumber
SiteID | Region | District | SiteConfig | LLDIterationNum | LLD_ID | LLDIterationEndDate | Change | Remark
AA00219 | North | MTY | MACRO | 1 | AA00219_1 | 2020-05-25 | Initial Release | Initial Release
AA00219 | North | MTY | MACRO | 2 | AA00219_2 | 2020-05-25 | Switched from MW to Fiber TX | Requested by Engineering
AA00219 | North | MTY | MACRO | 3 | AA00219_3 | 2020-05-26 | Added another carrier | Requested by Engineering
AA00951 | North | ZAC | MINI | 1 | AA00951_1 | 2020-06-02 | Initial Release | Initial Release
ED00640 | Center | GTO | SMALL | 1 | ED00640_1 | 2020-06-04 | Initial Release | Initial Release
FE00941 | Center | QRO | MACRO | 1 | FE00941_1 | 2020-06-04 | Initial Release | Initial Release
FE00941 | Center | QRO | MACRO | 2 | FE00941_2 | 2020-06-07 | Switched from SAT to MW | Requested by Commercial
VC00029 | South | VER | MINI | 1 | VC00029_1 | 2020-06-02 | Initial Release | Initial Release
CH00128 | South | CHI | SMALL | 1 | CH00128_1 | 2020-06-03 | Initial Release | Initial Release
CA00135 | North | MTY | MACRO | 1 | CA00135_1 | 2020-06-04 | Initial Release | Initial Release
CA00135 | North | MTY | MACRO | 2 | CA00135_2 | 2020-06-06 | Switched from Tower A to B | Requested by Commercial
CA00216 | North | ZAC | MINI | 1 | CA00216_1 | 2020-06-11 | Initial Release | Initial Release
CA00162 | Center | GTO | SMALL | 1 | CA00162_1 | 2020-06-12 | Initial Release | Initial Release
CA00257 | Center | QRO | MACRO | 1 | CA00257_1 | 2020-06-10 | Initial Release | Initial Release
CA00391 | South | VER | MINI | 1 | CA00391_1 | 2020-06-13 | Initial Release | Initial Release
CA00130 | South | CHI | SMALL | 1 | CA00130_1 | 2020-06-11 | Initial Release | Initial Release
CA00149 | North | MTY | MACRO | 1 | CA00149_1 | 2020-06-09 | Initial Release | Initial Release
CA00199 | North | ZAC | MINI | 1 | CA00199_1 | 2020-06-09 | Initial Release | Initial Release
CA00260 | Center | GTO | SMALL | 1 | CA00260_1 | 2020-06-12 | Initial Release | Initial Release
CA00261 | Center | QRO | MACRO | 1 | CA00261_1 | 2020-06-11 | Initial Release | Initial Release
CA00262 | South | VER | MINI | 1 | CA00262_1 | 2020-06-16 | Initial Release | Initial Release
CA00263 | South | CHI | SMALL | 1 | CA00263_1 | 2020-06-16 | Initial Release | Initial Release
AM00053 | North | MTY | MACRO | 1 | AM00053_1 | 2020-06-18 | Initial Release | Initial Release
CA00264 | North | ZAC | MINI | 1 | CA00264_1 | 2020-06-16 | Initial Release | Initial Release
CA00265 | Center | GTO | SMALL | 1 | CA00265_1 | 2020-06-15 | Initial Release | Initial Release
CA00372 | Center | QRO | MACRO | 1 | CA00372_1 | 2020-06-19 | Initial Release | Initial Release
CA00565 | South | VER | MINI | 1 | CA00565_1 | 2020-06-19 | Initial Release | Initial Release
CA00269 | South | CHI | SMALL | 1 | CA00269_1 | 2020-06-17 | Initial Release | Initial Release
CA00496 | North | MTY | MACRO | 1 | CA00496_1 | 2020-06-16 | Initial Release | Initial Release
CA00241 | North | ZAC | MINI | 1 | CA00241_1 | 2020-06-18 | Initial Release | Initial Release
CA00353 | Center | GTO | SMALL | 1 | CA00353_1 | 2020-06-24 | Initial Release | Initial Release
HU00017 | Center | QRO | MACRO | 1 | HU00017_1 | 2020-06-24 | Initial Release | Initial Release
HU00060 | South | VER | MINI | 1 | HU00060_1 | 2020-06-23 | Initial Release | Initial Release
HU00180 | South | CHI | SMALL | 1 | HU00180_1 | 2020-06-21 | Initial Release | Initial Release
AM00040 | North | MTY | MINI | 1 | AM00040_1 | 2020-06-24 | Initial Release | Initial Release
AM00041 | North | ZAC | SMALL | 1 | AM00041_1 | 2020-06-22 | Initial Release | Initial Release
AM00067 | Center | GTO | MACRO | 1 | AM00067_1 | 2020-06-24 | Initial Release | Initial Release
AM00100 | Center | QRO | MINI | 1 | AM00100_1 | 2020-06-24 | Initial Release | Initial Release
AM00118 | South | VER | SMALL | 1 | AM00118_1 | 2020-06-23 | Initial Release | Initial Release
AM00147 | South | CHI | MACRO | 1 | AM00147_1 | 2020-06-26 | Initial Release | Initial Release
AM00230 | North | MTY | MINI | 1 | AM00230_1 | 2020-06-25 | Initial Release | Initial Release
AY00031 | North | ZAC | SMALL | 1 | AY00031_1 | 2020-06-23 | Initial Release | Initial Release
AY00210 | Center | GTO | MACRO | 1 | AY00210_1 | 2020-07-02 | Initial Release | Initial Release
HU00200 | Center | QRO | MINI | 1 | HU00200_1 | 2020-07-02 | Initial Release | Initial Release
AN00035 | South | VER | SMALL | 1 | AN00035_1 | 2020-07-02 | Initial Release | Initial Release
AN00228 | South | CHI | MACRO | 1 | AN00228_1 | 2020-07-02 | Initial Release | Initial Release
AM00059 | North | MTY | MINI | 1 | AM00059_1 | 2020-06-30 | Initial Release | Initial Release
AM00227 | North | ZAC | SMALL | 1 | AM00227_1 | 2020-06-29 | Initial Release | Initial Release
PI00226 | Center | GTO | SMALL | 1 | PI00226_1 | 2020-07-03 | Initial Release | Initial Release
PI00227 | Center | QRO | MACRO | 1 | PI00227_1 | 2020-06-29 | Initial Release | Initial Release
PI00229 | South | VER | MINI | 1 | PI00229_1 | 2020-06-28 | Initial Release | Initial Release
PI00170 | South | CHI | SMALL | 1 | PI00170_1 | 2020-07-01 | Initial Release | Initial Release
PI00179 | North | ZAC | MACRO | 1 | PI00179_1 | 2020-06-30 | Initial Release | Initial Release
PI00244 | North | GTO | MINI | 1 | PI00244_1 | 2020-06-28 | Initial Release | Initial Release
PI00265 | Center | QRO | SMALL | 1 | PI00265_1 | 2020-07-01 | Initial Release | Initial Release
PI00309 | Center | VER | MACRO | 1 | PI00309_1 | 2020-07-03 | Initial Release | Initial Release
PI00188 | South | CHI | MINI | 1 | PI00188_1 | 2020-07-01 | Initial Release | Initial Release
PI00269 | South | MTY | SMALL | 1 | PI00269_1 | 2020-07-02 | Initial Release | Initial Release
PI00213 | North | ZAC | MACRO | 1 | PI00213_1 | 2020-07-05 | Initial Release | Initial Release
PI00225 | North | GTO | MINI | 1 | PI00225_1 | 2020-07-02 | Initial Release | Initial Release
PI00240 | Center | QRO | SMALL | 1 | PI00240_1 | 2020-07-02 | Initial Release | Initial Release
PI00241 | Center | MTY | MACRO | 1 | PI00241_1 | 2020-07-03 | Initial Release | Initial Release
AN00231 | South | ZAC | MINI | 1 | AN00231_1 | 2020-07-02 | Initial Release | Initial Release
AN00262 | South | GTO | SMALL | 1 | AN00262_1 | 2020-07-03 | Initial Release | Initial Release
PI00256 | North | QRO | MACRO | 1 | PI00256_1 | 2020-07-01 | Initial Release | Initial Release
PI00257 | North | VER | MINI | 1 | PI00257_1 | 2020-07-03 | Initial Release | Initial Release
PI00277 | Center | CHI | SMALL | 1 | PI00277_1 | 2020-07-05 | Initial Release | Initial Release
PI00308 | Center | MTY | MACRO | 1 | PI00308_1 | 2020-07-06 | Initial Release | Initial Release
PI00313 | South | ZAC | MINI | 1 | PI00313_1 | 2020-07-02 | Initial Release | Initial Release
AP00049 | South | GTO | SMALL | 1 | AP00049_1 | 2020-07-03 | Initial Release | Initial Release
PI00135 | North | QRO | MACRO | 1 | PI00135_1 | 2020-07-05 | Initial Release | Initial Release
PI00184 | North | VER | MINI | 1 | PI00184_1 | 2020-07-09 | Initial Release | Initial Release
AP00092 | Center | CHI | SMALL | 1 | AP00092_1 | 2020-07-09 | Initial Release | Initial Release
AP00146 | Center | MTY | MACRO | 1 | AP00146_1 | 2020-07-11 | Initial Release | Initial Release
AP00231 | South | ZAC | MINI | 1 | AP00231_1 | 2020-07-09 | Initial Release | Initial Release
AP00235 | South | GTO | SMALL | 1 | AP00235_1 | 2020-07-10 | Initial Release | Initial Release
AP00239 | North | QRO | MACRO | 1 | AP00239_1 | 2020-07-12 | Initial Release | Initial Release
PI00189 | North | VER | MINI | 1 | PI00189_1 | 2020-07-11 | Initial Release | Initial Release
PI00282 | Center | CHI | SMALL | 1 | PI00282_1 | 2020-07-09 | Initial Release | Initial Release
PI00284 | Center | MTY | MACRO | 1 | PI00284_1 | 2020-07-10 | Initial Release | Initial Release
LO00158 | South | ZAC | MINI | 1 | LO00158_1 | 2020-07-10 | Initial Release | Initial Release
LO00159 | South | GTO | SMALL | 1 | LO00159_1 | 2020-07-10 | Initial Release | Initial Release
CA00351 | North | QRO | MACRO | 1 | CA00351_1 | 2020-07-12 | Initial Release | Initial Release
CA00514 | North | VER | MINI | 1 | CA00514_1 | 2020-07-13 | Initial Release | Initial Release
JU00157 | Center | CHI | SMALL | 1 | JU00157_1 | 2020-07-09 | Initial Release | Initial Release
JU00247 | Center | MTY | MACRO | 1 | JU00247_1 | 2020-07-08 | Initial Release | Initial Release
JU00229 | South | ZAC | MINI | 1 | JU00229_1 | 2020-07-09 | Initial Release | Initial Release
JU00415 | South | GTO | SMALL | 1 | JU00415_1 | 2020-07-11 | Initial Release | Initial Release
LA00134 | North | QRO | MACRO | 1 | LA00134_1 | 2020-07-11 | Initial Release | Initial Release
LA00613 | North | VER | MINI | 1 | LA00613_1 | 2020-07-09 | Initial Release | Initial Release
LI01455 | Center | CHI | SMALL | 1 | LI01455_1 | 2020-07-15 | Initial Release | Initial Release
LI01461 | Center | MTY | MINI | 1 | LI01461_1 | 2020-07-20 | Initial Release | Initial Release
LI01476 | South | ZAC | SMALL | 1 | LI01476_1 | 2020-07-18 | Initial Release | Initial Release
LI01542 | South | GTO | MACRO | 1 | LI01542_1 | 2020-07-15 | Initial Release | Initial Release
LI02051 | North | QRO | MINI | 1 | LI02051_1 | - | Initial Release | Not finished
LI02052 | North | VER | SMALL | 1 | LI02052_1 | - | Initial Release | Not finished
LI01472 | Center | CHI | MACRO | 1 | LI01472_1 | - | Initial Release | Not finished
LI01483 | Center | MTY | MINI | 1 | LI01483_1 | - | Initial Release | Not finished
LI01550 | South | ZAC | SMALL | 1 | LI01550_1 | - | Initial Release | Not finished
PI00220 | South | GTO | MACRO | 1 | PI00220_1 | - | Initial Release | Not finished
PI00246 | North | QRO | MINI | 1 | PI00246_1 | - | Initial Release | Not finished
AM00004 | North | VER | SMALL | 1 | AM00004_1 | - | Initial Release | Not finished
AM00226 | Center | CHI | MACRO | 1 | AM00226_1 | - | Initial Release | Not finished
AP00017 | Center | MTY | MINI | 1 | AP00017_1 | - | Initial Release | Not finished
Note on A3: Unique Site Identifier
Note on B3: Site Region
Note on C3: District or State where the Site is Located
Note on E3: Low Level Design Iteration Sequency Number
Note on F3: LLD Iteration unique identifier
Note on G3: Date when LLD is ready
Note on H3: Justification for Design Change
Note on I3: Notes and Remarks of Area Responsible of the Request the change

## 4. Design Tracking Summary
Summary of LLD - Design Process Tracking per site
100 | [7 empty] | 2.7111 | Average Days per LLD
SiteID | Region | District | SiteConfig | SiteDesignStarted_AC | SumLLDIterations | LatestLLD_ID | LatestLLDIterationEndDate | LLD_TotalDays
AA00219 | North | MTY | MACRO | 2020-05-25 | 3 | AA00219_3 | 2020-05-26 | 1
AA00951 | North | ZAC | MINI | 2020-05-31 | 1 | AA00951_1 | 2020-06-02 | 2
ED00640 | Center | GTO | SMALL | 2020-06-01 | 1 | ED00640_1 | 2020-06-04 | 3
FE00941 | Center | QRO | MACRO | 2020-06-01 | 2 | FE00941_2 | 2020-06-07 | 6
VC00029 | South | VER | MINI | 2020-06-01 | 1 | VC00029_1 | 2020-06-02 | 1
CH00128 | South | CHI | SMALL | 2020-06-01 | 1 | CH00128_1 | 2020-06-03 | 2
CA00135 | North | MTY | MACRO | 2020-06-01 | 2 | CA00135_2 | 2020-06-06 | 5
CA00216 | North | ZAC | MINI | 2020-06-08 | 1 | CA00216_1 | 2020-06-11 | 3
CA00162 | Center | GTO | SMALL | 2020-06-07 | 1 | CA00162_1 | 2020-06-12 | 5
CA00257 | Center | QRO | MACRO | 2020-06-08 | 1 | CA00257_1 | 2020-06-10 | 2
CA00391 | South | VER | MINI | 2020-06-07 | 1 | CA00391_1 | 2020-06-13 | 6
CA00130 | South | CHI | SMALL | 2020-06-08 | 1 | CA00130_1 | 2020-06-11 | 3
CA00149 | North | MTY | MACRO | 2020-06-08 | 1 | CA00149_1 | 2020-06-09 | 1
CA00199 | North | ZAC | MINI | 2020-06-08 | 1 | CA00199_1 | 2020-06-09 | 1
CA00260 | Center | GTO | SMALL | 2020-06-08 | 1 | CA00260_1 | 2020-06-12 | 4
CA00261 | Center | QRO | MACRO | 2020-06-07 | 1 | CA00261_1 | 2020-06-11 | 4
CA00262 | South | VER | MINI | 2020-06-15 | 1 | CA00262_1 | 2020-06-16 | 1
CA00263 | South | CHI | SMALL | 2020-06-14 | 1 | CA00263_1 | 2020-06-16 | 2
AM00053 | North | MTY | MACRO | 2020-06-14 | 1 | AM00053_1 | 2020-06-18 | 4
CA00264 | North | ZAC | MINI | 2020-06-15 | 1 | CA00264_1 | 2020-06-16 | 1
CA00265 | Center | GTO | SMALL | 2020-06-15 | 1 | CA00265_1 | 2020-06-15 | 0
CA00372 | Center | QRO | MACRO | 2020-06-15 | 1 | CA00372_1 | 2020-06-19 | 4
CA00565 | South | VER | MINI | 2020-06-15 | 1 | CA00565_1 | 2020-06-19 | 4
CA00269 | South | CHI | SMALL | 2020-06-15 | 1 | CA00269_1 | 2020-06-17 | 2
CA00496 | North | MTY | MACRO | 2020-06-14 | 1 | CA00496_1 | 2020-06-16 | 2
CA00241 | North | ZAC | MINI | 2020-06-14 | 1 | CA00241_1 | 2020-06-18 | 4
CA00353 | Center | GTO | SMALL | 2020-06-20 | 1 | CA00353_1 | 2020-06-24 | 4
HU00017 | Center | QRO | MACRO | 2020-06-20 | 1 | HU00017_1 | 2020-06-24 | 4
HU00060 | South | VER | MINI | 2020-06-21 | 1 | HU00060_1 | 2020-06-23 | 2
HU00180 | South | CHI | SMALL | 2020-06-21 | 1 | HU00180_1 | 2020-06-21 | 0
AM00040 | North | MTY | MINI | 2020-06-21 | 1 | AM00040_1 | 2020-06-24 | 3
AM00041 | North | ZAC | SMALL | 2020-06-20 | 1 | AM00041_1 | 2020-06-22 | 2
AM00067 | Center | GTO | MACRO | 2020-06-20 | 1 | AM00067_1 | 2020-06-24 | 4
AM00100 | Center | QRO | MINI | 2020-06-21 | 1 | AM00100_1 | 2020-06-24 | 3
AM00118 | South | VER | SMALL | 2020-06-20 | 1 | AM00118_1 | 2020-06-23 | 3
AM00147 | South | CHI | MACRO | 2020-06-20 | 1 | AM00147_1 | 2020-06-26 | 6
AM00230 | North | MTY | MINI | 2020-06-21 | 1 | AM00230_1 | 2020-06-25 | 4
AY00031 | North | ZAC | SMALL | 2020-06-21 | 1 | AY00031_1 | 2020-06-23 | 2
AY00210 | Center | GTO | MACRO | 2020-06-27 | 1 | AY00210_1 | 2020-07-02 | 5
HU00200 | Center | QRO | MINI | 2020-06-28 | 1 | HU00200_1 | 2020-07-02 | 4
AN00035 | South | VER | SMALL | 2020-06-28 | 1 | AN00035_1 | 2020-07-02 | 4
AN00228 | South | CHI | MACRO | 2020-06-27 | 1 | AN00228_1 | 2020-07-02 | 5
AM00059 | North | MTY | MINI | 2020-06-28 | 1 | AM00059_1 | 2020-06-30 | 2
AM00227 | North | ZAC | SMALL | 2020-06-28 | 1 | AM00227_1 | 2020-06-29 | 1
PI00226 | Center | GTO | SMALL | 2020-06-27 | 1 | PI00226_1 | 2020-07-03 | 6
PI00227 | Center | QRO | MACRO | 2020-06-27 | 1 | PI00227_1 | 2020-06-29 | 2
PI00229 | South | VER | MINI | 2020-06-28 | 1 | PI00229_1 | 2020-06-28 | 0
PI00170 | South | CHI | SMALL | 2020-06-28 | 1 | PI00170_1 | 2020-07-01 | 3
PI00179 | North | ZAC | MACRO | 2020-06-27 | 1 | PI00179_1 | 2020-06-30 | 3
PI00244 | North | GTO | MINI | 2020-06-28 | 1 | PI00244_1 | 2020-06-28 | 0
PI00265 | Center | QRO | SMALL | 2020-06-27 | 1 | PI00265_1 | 2020-07-01 | 4
PI00309 | Center | VER | MACRO | 2020-06-30 | 1 | PI00309_1 | 2020-07-03 | 3
PI00188 | South | CHI | MINI | 2020-07-01 | 1 | PI00188_1 | 2020-07-01 | 0
PI00269 | South | MTY | SMALL | 2020-07-01 | 1 | PI00269_1 | 2020-07-02 | 1
PI00213 | North | ZAC | MACRO | 2020-07-01 | 1 | PI00213_1 | 2020-07-05 | 4
PI00225 | North | GTO | MINI | 2020-06-30 | 1 | PI00225_1 | 2020-07-02 | 2
PI00240 | Center | QRO | SMALL | 2020-06-30 | 1 | PI00240_1 | 2020-07-02 | 2
PI00241 | Center | MTY | MACRO | 2020-06-30 | 1 | PI00241_1 | 2020-07-03 | 3
AN00231 | South | ZAC | MINI | 2020-06-30 | 1 | AN00231_1 | 2020-07-02 | 2
AN00262 | South | GTO | SMALL | 2020-06-30 | 1 | AN00262_1 | 2020-07-03 | 3
PI00256 | North | QRO | MACRO | 2020-06-30 | 1 | PI00256_1 | 2020-07-01 | 1
PI00257 | North | VER | MINI | 2020-07-01 | 1 | PI00257_1 | 2020-07-03 | 2
PI00277 | Center | CHI | SMALL | 2020-07-01 | 1 | PI00277_1 | 2020-07-05 | 4
PI00308 | Center | MTY | MACRO | 2020-06-30 | 1 | PI00308_1 | 2020-07-06 | 6
PI00313 | South | ZAC | MINI | 2020-06-30 | 1 | PI00313_1 | 2020-07-02 | 2
AP00049 | South | GTO | SMALL | 2020-06-30 | 1 | AP00049_1 | 2020-07-03 | 3
PI00135 | North | QRO | MACRO | 2020-07-01 | 1 | PI00135_1 | 2020-07-05 | 4
PI00184 | North | VER | MINI | 2020-07-07 | 1 | PI00184_1 | 2020-07-09 | 2
AP00092 | Center | CHI | SMALL | 2020-07-08 | 1 | AP00092_1 | 2020-07-09 | 1
AP00146 | Center | MTY | MACRO | 2020-07-08 | 1 | AP00146_1 | 2020-07-11 | 3
AP00231 | South | ZAC | MINI | 2020-07-08 | 1 | AP00231_1 | 2020-07-09 | 1
AP00235 | South | GTO | SMALL | 2020-07-08 | 1 | AP00235_1 | 2020-07-10 | 2
AP00239 | North | QRO | MACRO | 2020-07-08 | 1 | AP00239_1 | 2020-07-12 | 4
PI00189 | North | VER | MINI | 2020-07-07 | 1 | PI00189_1 | 2020-07-11 | 4
PI00282 | Center | CHI | SMALL | 2020-07-07 | 1 | PI00282_1 | 2020-07-09 | 2
PI00284 | Center | MTY | MACRO | 2020-07-08 | 1 | PI00284_1 | 2020-07-10 | 2
LO00158 | South | ZAC | MINI | 2020-07-08 | 1 | LO00158_1 | 2020-07-10 | 2
LO00159 | South | GTO | SMALL | 2020-07-07 | 1 | LO00159_1 | 2020-07-10 | 3
CA00351 | North | QRO | MACRO | 2020-07-07 | 1 | CA00351_1 | 2020-07-12 | 5
CA00514 | North | VER | MINI | 2020-07-07 | 1 | CA00514_1 | 2020-07-13 | 6
JU00157 | Center | CHI | SMALL | 2020-07-08 | 1 | JU00157_1 | 2020-07-09 | 1
JU00247 | Center | MTY | MACRO | 2020-07-07 | 1 | JU00247_1 | 2020-07-08 | 1
JU00229 | South | ZAC | MINI | 2020-07-08 | 1 | JU00229_1 | 2020-07-09 | 1
JU00415 | South | GTO | SMALL | 2020-07-08 | 1 | JU00415_1 | 2020-07-11 | 3
LA00134 | North | QRO | MACRO | 2020-07-08 | 1 | LA00134_1 | 2020-07-11 | 3
LA00613 | North | VER | MINI | 2020-07-07 | 1 | LA00613_1 | 2020-07-09 | 2
LI01455 | Center | CHI | SMALL | 2020-07-20 | 1 | LI01455_1 | 2020-07-15 | -5
LI01461 | Center | MTY | MINI | 2020-07-15 | 1 | LI01461_1 | 2020-07-20 | 5
LI01476 | South | ZAC | SMALL | 2020-07-15 | 1 | LI01476_1 | 2020-07-18 | 3
LI01542 | South | GTO | MACRO | 2020-07-13 | 1 | LI01542_1 | 2020-07-15 | 2
LI02051 | North | QRO | MINI | 2020-07-14 | 1 | LI02051_1 | - | -
LI02052 | North | VER | SMALL | 2020-07-14 | 1 | LI02052_1 | - | -
LI01472 | Center | CHI | MACRO | 2020-07-14 | 1 | LI01472_1 | - | -
LI01483 | Center | MTY | MINI | 2020-07-14 | 1 | LI01483_1 | - | -
LI01550 | South | ZAC | SMALL | 2020-07-14 | 1 | LI01550_1 | - | -
PI00220 | South | GTO | MACRO | 2020-07-13 | 1 | PI00220_1 | - | -
PI00246 | North | QRO | MINI | 0 | 1 | PI00246_1 | - | -
AM00004 | North | VER | SMALL | 0 | 1 | AM00004_1 | - | -
AM00226 | Center | CHI | MACRO | 0 | 1 | AM00226_1 | - | -
AP00017 | Center | MTY | MINI | 0 | 1 | AP00017_1 | - | -
Formulas:
SiteDesignStarted_AC = INDEX(Table_SiteMilestoneTracking[SiteDesignStarted_AC],MATCH(Table_LLDTrackingSummary[[#This Row],[SiteID]],Table_SiteMilestoneTracking[SiteID],0))
LatestLLDIterationEndDate = INDEX(Table_LLDTrackingSheet[LLDIterationEndDate],MATCH(Table_LLDTrackingSummary[[#This Row],[LatestLLD_ID]],Table_LLDTrackingSheet[LLD_ID],0))
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is this
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is this?
Note on A4: Unique Site Identifier
Note on B4: Region where site is located
Note on C4: District or State where site is located
Note on D4: Site Configuration Type
Note on E4: First Iteration End Day
Note on F4: Number of of Iterations Required
Note on G4: Last Iteration ID
Note on H4: Last Iteration date
Note on I4: Difference between first and last iteration in days

## 5. Site Tracking Sheet
Deployment Tracking per site | [6 empty] | Cost Accumulates per site |  | Network Design | [7 empty] | Site Survey |  |  |  |  | Site Acquisition | [5 empty] | Site Construction | [7 empty] | Power Construction | [5 empty] | Tx | [5 empty] | Installation & Commissioning | [5 empty] | Integration | [9 empty] | Site Acceptance | [6 empty] | Handover to Operations
[9 empty] | Record Dates Below ↓ | Record Dates Below ↓ | For KPI Calculation | 500 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI Calculation | 500 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI Calculation | 600 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI Calculation | For KPI Calculation | 150 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation | For KPI calculation | 1500 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation | For KPI calculation | 500 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation | For KPI calculation | 500 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation | For KPI calculation | 2500 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation | For KPI calculation | 500 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation | For KPI calculation | 250 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation | For KPI calculation | 200 | Record Costs Below ↓ |  | Record Dates Below ↓ | For KPI calculation |  | (For KPI Calculation) | (For KPI Calculation) | (For KPI Calculation)
SiteID | Region | District | SiteConfig | TowerCo | TowerID | CurrentSiteMilestone | SiteCostBL | SiteCostAC | SiteDesignStarted_BL | SiteDesignStarted_AC | Delta_SiteDesignStarted_BL_SiteDesignStarted_AC | c0_SiteDesignCostBL | c0_SiteDesignCostAC | SiteDesignReady_BL | SiteDesignReady_AC | Delta_SiteDesignReady_AC_SiteDesignReady_BL | c1_SiteSurveyCostBL | c1_SiteSurveyCostAC | SiteSurveyCompleted_BL | SiteSurveyCompleted_AC | Delta_SiteSurveyCompleted_AC_SiteDesignReady_AC | c2_SiteAcquisitionCostBL | c2_SiteAcquisitionCostAC | SiteAcquired_BL | SiteAcquired_AC | Delta_SiteAcquired_AC_SiteAcquired_BL | Delta_SiteAcquired_AC_SiteSurveyCompleted_AC | c2a_SiteCWReadinessCost_BL | c2a_SiteCWReadinessCost_AC | SiteReadyForCW_BL | SiteReadyForCW_AC | Delta_SiRdyCW_BL_SiRdyCW_AC | Delta_ReadyFor_CW_SiteDesign_Ready | c3_CivilWorksCostBL | c3_CivilWorksCostAC | SiteReadyForPower_BL | SiteReadyForPower_AC | Delta_SiRdyPwr_AC_SiRdyPwr_BL | Delta_SiteReadyForPower_AC_SiteReadyForCW_AC | c4_PowerInstallCostBL | c4_PowerInstallCostAC | TXReady_BL | TXReady_AC | Delta_TXRdy_AC_TXRdy_BL | Delta_TXRdy_AC_SiteReadyForPower_AC | c5_TxintegrationCostBL | c5_TxintegrationCostAC | SiteReadyForInstallation_BL | SiteReadyForInstallation_AC | Delta_SiteReadyForInstallation_AC_SiteRdyFrInstall_BL | Delta_SiteReadyForInstallation_AC_TXReady_AC | c6_InstallationCostBL | c6_InstallationCostAC | SiteReadyForIntegration_BL | SiteReadyForIntegration_AC | Delta_SiteReadyForIntegration_AC_SiRdyInteg_BL | Delta_SiteReadyForIntegration_AC_SiteReadyForInstallation_AC | c7_IntegrationCostBL | c7_IntegrationCostAC | SiteOnAir_BL | SiteOnAir_AC | Delta_SiteOnAir_AC_SiteOnAir_BL | Delta_SiteOnAir_AC_SiteReadyForIntegration_AC | c8_AcceptanceCostBL | c8_AcceptanceCostAC | SiteAccepted_BL | SiteAccepted_AC | Delta_SiteAccepted_AC_SiAccept_BL | Delta_SiteAccepted_AC_SiteOnAir_AC | c9_HandoverCostBL | c9_HandoverCostAC | SiteInOperations_BL | SiteInOperations_AC | Delta_SiteInOperations_AC_SiteInOperations_BL | E2E_Site_BL | E2E_Site_AC | E2E_Site_deltaT | DeltaDays_SiteAccepted_SiteInOperations | Remark
AA00219 | North | MTY | MACRO | SuperTowers | ST0014 | SiteInOperations | 7550 | 7905 | 2020-05-25 | 2020-05-25 | 0 | 500 | 500 | 2020-05-27 | 2020-05-27 | 0 | 500 | 425 | 2020-05-29 | 2020-05-30 | 3 | 600 | 420 | 2020-06-09 | 2020-06-10 | 1 | 11 | 150 | 150 | 2020-06-11 | 2020-06-12 | 1 | 16 | 1500 | 2250 | 2020-06-19 | 2020-06-20 | 1 | 8 | 500 | 650 | 2020-06-24 | 2020-06-25 | 1 | 5 | 500 | 650 | 2020-07-01 | 2020-07-01 | 0 | 6 | 2500 | 2100 | 2020-07-05 | 2020-07-06 | 1 | 5 | 500 | 460 | 2020-07-09 | 2020-07-09 | 0 | 3 | 250 | 250 | 2020-07-13 | 2020-07-13 | 0 | 4 | 200 | 200 | 2020-07-21 | 2020-07-21 | 0 | 55 | 55 | 0 | 8
AA00951 | North | ZAC | MINI | PremiumTowers | PT001211 | SiteInOperations | 7550 | 7620 | 2020-05-30 | 2020-05-31 | 1 | 500 | 460 | 2020-06-01 | 2020-06-02 | 1 | 500 | 375 | 2020-06-03 | 2020-06-05 | 3 | 600 | 540 | 2020-06-14 | 2020-06-17 | 3 | 12 | 150 | 165 | 2020-06-16 | 2020-06-19 | 3 | 17 | 1500 | 1950 | 2020-06-24 | 2020-06-28 | 4 | 9 | 500 | 600 | 2020-06-29 | 2020-07-03 | 4 | 5 | 500 | 550 | 2020-07-06 | 2020-07-11 | 5 | 8 | 2500 | 2200 | 2020-07-10 | 2020-07-16 | 6 | 5 | 500 | 495 | 2020-07-14 | 2020-07-17 | 3 | 1 | 250 | 250 | 2020-07-18 | 2020-07-18 | 0 | 1 | 200 | 200 | 2020-07-26 | 2020-08-04 | 9 | 55 | 63 | 8 | 17
ED00640 | Center | GTO | SMALL | NaaS Owned | T00001 | SiteInOperations | 7550 | 7755 | 2020-05-30 | 2020-06-01 | 2 | 500 | 540 | 2020-06-01 | 2020-06-04 | 3 | 500 | 575 | 2020-06-03 | 2020-06-06 | 2 | 600 | 480 | 2020-06-14 | 2020-06-18 | 4 | 12 | 150 | 150 | 2020-06-16 | 2020-06-21 | 5 | 17 | 1500 | 2250 | 2020-06-24 | 2020-06-30 | 6 | 9 | 500 | 250 | 2020-06-29 | 2020-07-06 | 7 | 6 | 500 | 600 | 2020-07-06 | 2020-07-14 | 8 | 8 | 2500 | 2150 | 2020-07-10 | 2020-07-16 | 6 | 2 | 500 | 460 | 2020-07-14 | 2020-07-16 | 2 | 0 | 250 | 250 | 2020-07-18 | 2020-07-28 | 10 | 12 | 200 | 200 | 2020-07-26 | 2020-08-06 | 11 | 55 | 63 | 8 | 9
FE00941 | Center | QRO | MACRO | NaaS Owned | T00013 | SiteInOperations | 7550 | 7705 | 2020-05-30 | 2020-06-01 | 2 | 500 | 520 | 2020-06-01 | 2020-06-07 | 6 | 500 | 375 | 2020-06-03 | 2020-06-09 | 2 | 600 | 600 | 2020-06-14 | 2020-06-21 | 7 | 12 | 150 | 150 | 2020-06-16 | 2020-06-24 | 8 | 17 | 1500 | 2100 | 2020-06-24 | 2020-06-27 | 3 | 3 | 500 | 700 | 2020-06-29 | 2020-07-08 | 9 | 11 | 500 | 300 | 2020-07-06 | 2020-07-08 | 2 | 0 | 2500 | 2200 | 2020-07-10 | 2020-07-12 | 2 | 4 | 500 | 460 | 2020-07-14 | 2020-07-15 | 1 | 3 | 250 | 250 | 2020-07-18 | 2020-07-22 | 4 | 7 | 200 | 200 | 2020-07-26 | 2020-08-08 | 13 | 55 | 62 | 7 | 17
VC00029 | South | VER | MINI | NeatTowers | NT0041 | SiteInOperations | 7550 | 7185 | 2020-05-30 | 2020-06-01 | 2 | 500 | 460 | 2020-06-01 | 2020-06-02 | 1 | 500 | 375 | 2020-06-03 | 2020-06-05 | 3 | 600 | 780 | 2020-06-14 | 2020-06-16 | 2 | 11 | 150 | 150 | 2020-06-16 | 2020-06-18 | 2 | 16 | 1500 | 1500 | 2020-06-24 | 2020-06-27 | 3 | 9 | 500 | 250 | 2020-06-29 | 2020-07-02 | 3 | 5 | 500 | 600 | 2020-07-06 | 2020-07-10 | 4 | 8 | 2500 | 2300 | 2020-07-10 | 2020-07-14 | 4 | 4 | 500 | 470 | 2020-07-14 | 2020-07-19 | 5 | 5 | 250 | 250 | 2020-07-18 | 2020-07-24 | 6 | 5 | 200 | 200 | 2020-07-26 | 2020-08-01 | 6 | 55 | 60 | 5 | 8
CH00128 | South | CHI | SMALL | NeatTowers | NT0111 | SiteInOperations | 7550 | 7975 | 2020-05-30 | 2020-06-01 | 2 | 500 | 420 | 2020-06-01 | 2020-06-03 | 2 | 500 | 375 | 2020-06-03 | 2020-06-05 | 2 | 600 | 720 | 2020-06-14 | 2020-06-16 | 2 | 11 | 150 | 150 | 2020-06-16 | 2020-06-18 | 2 | 15 | 1500 | 2250 | 2020-06-24 | 2020-06-26 | 2 | 8 | 500 | 600 | 2020-06-29 | 2020-07-02 | 3 | 6 | 500 | 700 | 2020-07-06 | 2020-07-10 | 4 | 8 | 2500 | 2000 | 2020-07-10 | 2020-07-14 | 4 | 4 | 500 | 460 | 2020-07-14 | 2020-07-18 | 4 | 4 | 250 | 250 | 2020-07-18 | 2020-07-22 | 4 | 4 | 200 | 200 | 2020-07-26 | 2020-08-01 | 6 | 55 | 59 | 4 | 10
CA00135 | North | MTY | MACRO | SuperTowers | ST0524 | SiteInOperations | 7550 | 8025 | 2020-05-30 | 2020-06-01 | 2 | 500 | 500 | 2020-06-01 | 2020-06-06 | 5 | 500 | 575 | 2020-06-03 | 2020-06-08 | 2 | 600 | 660 | 2020-06-14 | 2020-06-20 | 6 | 12 | 150 | 180 | 2020-06-16 | 2020-06-23 | 7 | 17 | 1500 | 1950 | 2020-06-24 | 2020-06-26 | 2 | 3 | 500 | 450 | 2020-06-29 | 2020-07-07 | 8 | 11 | 500 | 500 | 2020-07-06 | 2020-07-14 | 8 | 7 | 2500 | 2450 | 2020-07-10 | 2020-07-19 | 9 | 5 | 500 | 490 | 2020-07-14 | 2020-07-23 | 9 | 4 | 250 | 250 | 2020-07-18 | 2020-07-28 | 10 | 5 | 200 | 200 | 2020-07-26 | 2020-08-07 | 12 | 55 | 62 | 7 | 10
CA00216 | North | ZAC | MINI | PremiumTowers | PT044331 | SiteInOperations | 7550 | 7985 | 2020-06-06 | 2020-06-08 | 2 | 500 | 520 | 2020-06-08 | 2020-06-11 | 3 | 500 | 825 | 2020-06-10 | 2020-06-14 | 3 | 600 | 420 | 2020-06-21 | 2020-06-26 | 5 | 12 | 150 | 150 | 2020-06-23 | 2020-06-28 | 5 | 17 | 1500 | 1950 | 2020-07-01 | 2020-07-07 | 6 | 9 | 500 | 650 | 2020-07-06 | 2020-07-12 | 6 | 5 | 500 | 250 | 2020-07-13 | 2020-07-20 | 7 | 8 | 2500 | 2450 | 2020-07-17 | 2020-07-25 | 8 | 5 | 500 | 470 | 2020-07-21 | 2020-07-30 | 9 | 5 | 250 | 250 | 2020-07-25 | 2020-08-04 | 10 | 5 | 200 | 200 | 2020-08-02 | 2020-08-14 | 12 | 55 | 64 | 9 | 10
CA00162 | Center | GTO | SMALL | NaaS Owned | T01110 | SiteInOperations | 7550 | 6845 | 2020-06-06 | 2020-06-07 | 1 | 500 | 540 | 2020-06-08 | 2020-06-12 | 4 | 500 | 475 | 2020-06-10 | 2020-06-15 | 3 | 600 | 360 | 2020-06-21 | 2020-06-26 | 5 | 11 | 150 | 150 | 2020-06-23 | 2020-06-28 | 5 | 16 | 1500 | 1650 | 2020-07-01 | 2020-07-07 | 6 | 9 | 500 | 350 | 2020-07-06 | 2020-07-12 | 6 | 5 | 500 | 300 | 2020-07-13 | 2020-07-19 | 6 | 7 | 2500 | 2250 | 2020-07-17 | 2020-07-23 | 6 | 4 | 500 | 470 | 2020-07-21 | 2020-07-28 | 7 | 5 | 250 | 250 | 2020-07-25 | 2020-08-01 | 7 | 4 | 200 | 200 | 2020-08-02 | 2020-08-11 | 9 | 55 | 60 | 5 | 10
CA00257 | Center | QRO | MACRO | NaaS Owned | T00054 | SiteInOperations | 7550 | 6795 | 2020-06-06 | 2020-06-08 | 2 | 500 | 540 | 2020-06-08 | 2020-06-10 | 2 | 500 | 375 | 2020-06-10 | 2020-06-13 | 3 | 600 | 660 | 2020-06-21 | 2020-06-25 | 4 | 12 | 150 | 180 | 2020-06-23 | 2020-06-28 | 5 | 18 | 1500 | 1350 | 2020-07-01 | 2020-07-07 | 6 | 9 | 500 | 250 | 2020-07-06 | 2020-07-12 | 6 | 5 | 500 | 500 | 2020-07-13 | 2020-07-20 | 7 | 8 | 2500 | 2200 | 2020-07-17 | 2020-07-24 | 7 | 4 | 500 | 470 | 2020-07-21 | 2020-07-29 | 8 | 5 | 250 | 250 | 2020-07-25 | 2020-08-02 | 8 | 4 | 200 | 200 | 2020-08-02 | 2020-08-20 | 18 | 55 | 71 | 16 | 18
CA00391 | South | VER | MINI | SuperTowers | ST0756 | SiteAccepted | 7550 | 7780 | 2020-06-06 | 2020-06-07 | 1 | 500 | 440 | 2020-06-08 | 2020-06-13 | 5 | 500 | 625 | 2020-06-10 | 2020-06-15 | 2 | 600 | 840 | 2020-06-21 | 2020-06-26 | 5 | 11 | 150 | 150 | 2020-06-23 | 2020-06-29 | 6 | 16 | 1500 | 1650 | 2020-07-01 | 2020-07-08 | 7 | 9 | 500 | 700 | 2020-07-06 | 2020-07-13 | 7 | 5 | 500 | 400 | 2020-07-13 | 2020-07-20 | 7 | 7 | 2500 | 2400 | 2020-07-17 | 2020-07-24 | 7 | 4 | 500 | 475 | 2020-07-21 | 2020-07-28 | 7 | 4 | 250 | 250 | 2020-07-25 | 2020-08-01 | 7 | 4 | 200 |  | 2020-08-02 |  | - | 55
CA00130 | South | CHI | SMALL | PremiumTowers | PT00984 | SiteAccepted | 7550 | 7690 | 2020-06-06 | 2020-06-08 | 2 | 500 | 560 | 2020-06-08 | 2020-06-11 | 3 | 500 | 675 | 2020-06-10 | 2020-06-13 | 2 | 600 | 420 | 2020-06-21 | 2020-06-25 | 4 | 12 | 150 | 165 | 2020-06-23 | 2020-06-28 | 5 | 17 | 1500 | 1950 | 2020-07-01 | 2020-07-06 | 5 | 8 | 500 | 450 | 2020-07-06 | 2020-07-12 | 6 | 6 | 500 | 700 | 2020-07-13 | 2020-07-19 | 6 | 7 | 2500 | 2200 | 2020-07-17 | 2020-07-24 | 7 | 5 | 500 | 485 | 2020-07-21 | 2020-07-29 | 8 | 5 | 250 | 250 | 2020-07-25 | 2020-08-03 | 9 | 5 | 200 |  | 2020-08-02 |  | - | 55
CA00149 | North | MTY | MACRO | NaaS Owned | T00612 | SiteAccepted | 7550 | 7275 | 2020-06-06 | 2020-06-08 | 2 | 500 | 400 | 2020-06-08 | 2020-06-09 | 1 | 500 | 775 | 2020-06-10 | 2020-06-11 | 2 | 600 | 540 | 2020-06-21 | 2020-06-23 | 2 | 12 | 150 | 165 | 2020-06-23 | 2020-06-26 | 3 | 17 | 1500 | 2100 | 2020-07-01 | 2020-07-05 | 4 | 9 | 500 | 250 | 2020-07-06 | 2020-07-10 | 4 | 5 | 500 | 450 | 2020-07-13 | 2020-07-18 | 5 | 8 | 2500 | 2050 | 2020-07-17 | 2020-07-22 | 5 | 4 | 500 | 460 | 2020-07-21 | 2020-07-26 | 5 | 4 | 250 | 250 | 2020-07-25 | 2020-07-30 | 5 | 4 | 200 |  | 2020-08-02 |  | - | 55
CA00199 | North | ZAC | MINI | NaaS Owned | T00803 | SiteAccepted | 7550 | 7370 | 2020-06-06 | 2020-06-08 | 2 | 500 | 460 | 2020-06-08 | 2020-06-09 | 1 | 500 | 575 | 2020-06-10 | 2020-06-11 | 2 | 600 | 660 | 2020-06-21 | 2020-06-23 | 2 | 12 | 150 | 135 | 2020-06-23 | 2020-06-26 | 3 | 17 | 1500 | 2100 | 2020-07-01 | 2020-07-04 | 3 | 8 | 500 | 500 | 2020-07-06 | 2020-07-09 | 3 | 5 | 500 | 350 | 2020-07-13 | 2020-07-16 | 3 | 7 | 2500 | 2000 | 2020-07-17 | 2020-07-20 | 3 | 4 | 500 | 475 | 2020-07-21 | 2020-07-25 | 4 | 5 | 250 | 250 | 2020-07-25 | 2020-07-30 | 5 | 5 | 200 |  | 2020-08-02 |  | - | 55
CA00260 | Center | GTO | SMALL | NeatTowers | NT00454 | SiteAccepted | 7550 | 6585 | 2020-06-06 | 2020-06-08 | 2 | 500 | 480 | 2020-06-08 | 2020-06-12 | 4 | 500 | 775 | 2020-06-10 | 2020-06-14 | 2 | 600 | 600 | 2020-06-21 | 2020-06-25 | 4 | 11 | 150 | 120 | 2020-06-23 | 2020-06-27 | 4 | 15 | 1500 | 1050 | 2020-07-01 | 2020-07-06 | 5 | 9 | 500 | 650 | 2020-07-06 | 2020-07-12 | 6 | 6 | 500 | 300 | 2020-07-13 | 2020-07-20 | 7 | 8 | 2500 | 2000 | 2020-07-17 | 2020-07-25 | 8 | 5 | 500 | 480 | 2020-07-21 | 2020-07-29 | 8 | 4 | 250 | 250 | 2020-07-25 | 2020-08-02 | 8 | 4 | 200 |  | 2020-08-02 |  | - | 55
CA00261 | Center | QRO | MACRO | SuperTowers | ST3123 | SiteAccepted | 7550 | 7475 | 2020-06-06 | 2020-06-07 | 1 | 500 | 500 | 2020-06-08 | 2020-06-11 | 3 | 500 | 375 | 2020-06-10 | 2020-06-14 | 3 | 600 | 900 | 2020-06-21 | 2020-06-25 | 4 | 11 | 150 | 120 | 2020-06-23 | 2020-06-27 | 4 | 16 | 1500 | 1350 | 2020-07-01 | 2020-07-05 | 4 | 8 | 500 | 650 | 2020-07-06 | 2020-07-10 | 4 | 5 | 500 | 600 | 2020-07-13 | 2020-07-18 | 5 | 8 | 2500 | 2400 | 2020-07-17 | 2020-07-22 | 5 | 4 | 500 | 450 | 2020-07-21 | 2020-07-26 | 5 | 4 | 250 | 250 | 2020-07-25 | 2020-07-30 | 5 | 4 | 200 |  | 2020-08-02 |  | - | 55
CA00262 | South | VER | MINI | PremiumTowers | PT99231 | SiteAccepted | 7550 | 6865 | 2020-06-13 | 2020-06-15 | 2 | 500 | 520 | 2020-06-15 | 2020-06-16 | 1 | 500 | 825 | 2020-06-17 | 2020-06-19 | 3 | 600 | 720 | 2020-06-28 | 2020-07-01 | 3 | 12 | 150 | 150 | 2020-06-30 | 2020-07-03 | 3 | 17 | 1500 | 1200 | 2020-07-08 | 2020-07-11 | 3 | 8 | 500 | 350 | 2020-07-13 | 2020-07-16 | 3 | 5 | 500 | 500 | 2020-07-20 | 2020-07-23 | 3 | 7 | 2500 | 2050 | 2020-07-24 | 2020-07-27 | 3 | 4 | 500 | 450 | 2020-07-28 | 2020-08-01 | 4 | 5 | 250 | 250 | 2020-08-01 | 2020-08-06 | 5 | 5 | 200 |  | 2020-08-09 |  | - | 55
CA00263 | South | CHI | SMALL | NaaS Owned |  | SiteAccepted | 7550 | 7155 | 2020-06-13 | 2020-06-14 | 1 | 500 | 420 | 2020-06-15 | 2020-06-16 | 1 | 500 | 525 | 2020-06-17 | 2020-06-19 | 3 | 600 | 780 | 2020-06-28 | 2020-06-30 | 2 | 11 | 150 | 135 | 2020-06-30 | 2020-07-03 | 3 | 17 | 1500 | 1200 | 2020-07-08 | 2020-07-11 | 3 | 8 | 500 | 600 | 2020-07-13 | 2020-07-16 | 3 | 5 | 500 | 700 | 2020-07-20 | 2020-07-23 | 3 | 7 | 2500 | 2200 | 2020-07-24 | 2020-07-27 | 3 | 4 | 500 | 480 | 2020-07-28 | 2020-07-31 | 3 | 4 | 250 | 250 | 2020-08-01 | 2020-08-01 | 0 | 1 | 200 |  | 2020-08-09 |  | - | 55
AM00053 | North | MTY | MACRO | NaaS Owned |  | SiteAccepted | 7550 | 7170 | 2020-06-13 | 2020-06-14 | 1 | 500 | 460 | 2020-06-15 | 2020-06-18 | 3 | 500 | 775 | 2020-06-17 | 2020-06-21 | 3 | 600 | 540 | 2020-06-28 | 2020-07-03 | 5 | 12 | 150 | 180 | 2020-06-30 | 2020-07-06 | 6 | 18 | 1500 | 1500 | 2020-07-08 | 2020-07-14 | 6 | 8 | 500 | 350 | 2020-07-13 | 2020-07-19 | 6 | 5 | 500 | 350 | 2020-07-20 | 2020-07-27 | 7 | 8 | 2500 | 2450 | 2020-07-24 | 2020-08-01 | 8 | 5 | 500 | 495 | 2020-07-28 | 2020-08-05 | 8 | 4 | 250 | 250 | 2020-08-01 | 2020-08-10 | 9 | 5 | 200 |  | 2020-08-09 |  | - | 55
CA00264 | North | ZAC | MINI | PremiumTowers |  | SiteAccepted | 7550 | 6300 | 2020-06-13 | 2020-06-15 | 2 | 500 | 440 | 2020-06-15 | 2020-06-16 | 1 | 500 | 775 | 2020-06-17 | 2020-06-18 | 2 | 600 | 420 | 2020-06-28 | 2020-06-30 | 2 | 12 | 150 | 135 | 2020-06-30 | 2020-07-02 | 2 | 16 | 1500 | 1050 | 2020-07-08 | 2020-07-11 | 3 | 9 | 500 | 300 | 2020-07-13 | 2020-07-16 | 3 | 5 | 500 | 600 | 2020-07-20 | 2020-07-24 | 4 | 8 | 2500 | 2000 | 2020-07-24 | 2020-07-28 | 4 | 4 | 500 | 465 | 2020-07-28 | 2020-08-02 | 5 | 5 | 250 | 250 | 2020-08-01 | 2020-08-07 | 6 | 5 | 200 |  | 2020-08-09 |  | - | 55
CA00265 | Center | GTO | SMALL | NaaS Owned |  | SiteOnAir | 7550 | 6100 | 2020-06-13 | 2020-06-15 | 2 | 500 | 520 | 2020-06-15 | 2020-06-15 | 0 | 500 | 825 | 2020-06-17 | 2020-06-17 | 2 | 600 | 540 | 2020-06-28 | 2020-06-29 | 1 | 12 | 150 | 150 | 2020-06-30 | 2020-07-02 | 2 | 17 | 1500 | 900 | 2020-07-08 | 2020-07-11 | 3 | 9 | 500 | 250 | 2020-07-13 | 2020-07-17 | 4 | 6 | 500 | 400 | 2020-07-20 | 2020-07-24 | 4 | 7 | 2500 | 2200 | 2020-07-24 | 2020-07-28 | 4 | 4 | 500 | 465 | 2020-07-28 | 2020-08-02 | 5 | 5 | 250 |  | 2020-08-01 |  | - | - | 200 |  | 2020-08-09 |  | - | 55
CA00372 | Center | QRO | MACRO | NaaS Owned |  | SiteOnAir | 7550 | 7035 | 2020-06-13 | 2020-06-15 | 2 | 500 | 400 | 2020-06-15 | 2020-06-19 | 4 | 500 | 525 | 2020-06-17 | 2020-06-21 | 2 | 600 | 780 | 2020-06-28 | 2020-07-03 | 5 | 12 | 150 | 165 | 2020-06-30 | 2020-07-05 | 5 | 16 | 1500 | 1800 | 2020-07-08 | 2020-07-14 | 6 | 9 | 500 | 600 | 2020-07-13 | 2020-07-20 | 7 | 6 | 500 | 300 | 2020-07-20 | 2020-07-27 | 7 | 7 | 2500 | 2150 | 2020-07-24 | 2020-08-01 | 8 | 5 | 500 | 480 | 2020-07-28 | 2020-08-06 | 9 | 5 | 250 |  | 2020-08-01 |  | - | - | 200 |  | 2020-08-09 |  | - | 55
CA00565 | South | VER | MINI | SuperTowers |  | SiteOnAir | 7550 | 7255 | 2020-06-13 | 2020-06-15 | 2 | 500 | 440 | 2020-06-15 | 2020-06-19 | 4 | 500 | 625 | 2020-06-17 | 2020-06-21 | 2 | 600 | 900 | 2020-06-28 | 2020-07-02 | 4 | 11 | 150 | 135 | 2020-06-30 | 2020-07-04 | 4 | 15 | 1500 | 1800 | 2020-07-08 | 2020-07-13 | 5 | 9 | 500 | 300 | 2020-07-13 | 2020-07-19 | 6 | 6 | 500 | 550 | 2020-07-20 | 2020-07-26 | 6 | 7 | 2500 | 2150 | 2020-07-24 | 2020-07-30 | 6 | 4 | 500 | 490 | 2020-07-28 | 2020-08-04 | 7 | 5 | 250 |  | 2020-08-01 |  | - | - | 200 |  | 2020-08-09 |  | - | 55
CA00269 | South | CHI | SMALL | PremiumTowers |  | SiteOnAir | 7550 | 7025 | 2020-06-13 | 2020-06-15 | 2 | 500 | 480 | 2020-06-15 | 2020-06-17 | 2 | 500 | 675 | 2020-06-17 | 2020-06-19 | 2 | 600 | 540 | 2020-06-28 | 2020-06-30 | 2 | 11 | 150 | 180 | 2020-06-30 | 2020-07-03 | 3 | 16 | 1500 | 1650 | 2020-07-08 | 2020-07-11 | 3 | 8 | 500 | 550 | 2020-07-13 | 2020-07-17 | 4 | 6 | 500 | 600 | 2020-07-20 | 2020-07-25 | 5 | 8 | 2500 | 2050 | 2020-07-24 | 2020-07-30 | 6 | 5 | 500 | 480 | 2020-07-28 | 2020-08-04 | 7 | 5 | 250 |  | 2020-08-01 |  | - | - | 200 |  | 2020-08-09 |  | - | 55
CA00496 | North | MTY | MACRO | NaaS Owned |  | SiteOnAir | 7550 | 7175 | 2020-06-13 | 2020-06-14 | 1 | 500 | 440 | 2020-06-15 | 2020-06-16 | 1 | 500 | 775 | 2020-06-17 | 2020-06-18 | 2 | 600 | 720 | 2020-06-28 | 2020-06-29 | 1 | 11 | 150 | 150 | 2020-06-30 | 2020-07-02 | 2 | 16 | 1500 | 1650 | 2020-07-08 | 2020-07-10 | 2 | 8 | 500 | 400 | 2020-07-13 | 2020-07-15 | 2 | 5 | 500 | 450 | 2020-07-20 | 2020-07-22 | 2 | 7 | 2500 | 2250 | 2020-07-24 | 2020-07-27 | 3 | 5 | 500 | 490 | 2020-07-28 | 2020-07-28 | 0 | 1 | 250 |  | 2020-08-01 |  | - | - | 200 |  | 2020-08-09 |  | - | 55
CA00241 | North | ZAC | MINI | NaaS Owned |  | SiteOnAir | 7550 | 7890 | 2020-06-13 | 2020-06-14 | 1 | 500 | 580 | 2020-06-15 | 2020-06-18 | 3 | 500 | 525 | 2020-06-17 | 2020-06-21 | 3 | 600 | 660 | 2020-06-28 | 2020-07-03 | 5 | 12 | 150 | 120 | 2020-06-30 | 2020-07-05 | 5 | 17 | 1500 | 1950 | 2020-07-08 | 2020-07-13 | 5 | 8 | 500 | 600 | 2020-07-13 | 2020-07-18 | 5 | 5 | 500 | 650 | 2020-07-20 | 2020-07-26 | 6 | 8 | 2500 | 2450 | 2020-07-24 | 2020-07-31 | 7 | 5 | 500 | 475 | 2020-07-28 | 2020-08-05 | 8 | 5 | 250 |  | 2020-08-01 |  | - | - | 200 |  | 2020-08-09 |  | - | 55
CA00353 | Center | GTO | SMALL | NeatTowers |  | SiteOnAir | 7550 | 7020 | 2020-06-19 | 2020-06-20 | 1 | 500 | 560 | 2020-06-21 | 2020-06-24 | 3 | 500 | 575 | 2020-06-23 | 2020-06-27 | 3 | 600 | 720 | 2020-07-04 | 2020-07-08 | 4 | 11 | 150 | 120 | 2020-07-06 | 2020-07-11 | 5 | 17 | 1500 | 1350 | 2020-07-14 | 2020-07-20 | 6 | 9 | 500 | 700 | 2020-07-19 | 2020-07-26 | 7 | 6 | 500 | 500 | 2020-07-26 | 2020-08-02 | 7 | 7 | 2500 | 2150 | 2020-07-30 | 2020-08-07 | 8 | 5 | 500 | 465 | 2020-08-03 | 2020-08-12 | 9 | 5 | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
HU00017 | Center | QRO | MACRO | SuperTowers |  | SiteOnAir | 7550 | 7415 | 2020-06-19 | 2020-06-20 | 1 | 500 | 420 | 2020-06-21 | 2020-06-24 | 3 | 500 | 625 | 2020-06-23 | 2020-06-26 | 2 | 600 | 900 | 2020-07-04 | 2020-07-07 | 3 | 11 | 150 | 120 | 2020-07-06 | 2020-07-09 | 3 | 15 | 1500 | 1650 | 2020-07-14 | 2020-07-17 | 3 | 8 | 500 | 400 | 2020-07-19 | 2020-07-22 | 3 | 5 | 500 | 700 | 2020-07-26 | 2020-07-29 | 3 | 7 | 2500 | 2250 | 2020-07-30 | 2020-08-02 | 3 | 4 | 500 | 470 | 2020-08-03 | 2020-08-06 | 3 | 4 | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
HU00060 | South | VER | MINI | PremiumTowers |  | SiteOnAir | 7550 | 5940 | 2020-06-19 | 2020-06-21 | 2 | 500 | 560 | 2020-06-21 | 2020-06-23 | 2 | 500 | 425 | 2020-06-23 | 2020-06-25 | 2 | 600 | 540 | 2020-07-04 | 2020-07-06 | 2 | 11 | 150 | 165 | 2020-07-06 | 2020-07-09 | 3 | 16 | 1500 | 1050 | 2020-07-14 | 2020-07-18 | 4 | 9 | 500 | 550 | 2020-07-19 | 2020-07-24 | 5 | 6 | 500 | 350 | 2020-07-26 | 2020-08-01 | 6 | 8 | 2500 | 2000 | 2020-07-30 | 2020-08-06 | 7 | 5 | 500 | 465 | 2020-08-03 | 2020-08-11 | 8 | 5 | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
HU00180 | South | CHI | SMALL | SuperTowers |  | SiteOnAir | 7550 | 7905 | 2020-06-19 | 2020-06-21 | 2 | 500 | 580 | 2020-06-21 | 2020-06-21 | 0 | 500 | 825 | 2020-06-23 | 2020-06-24 | 3 | 600 | 900 | 2020-07-04 | 2020-07-05 | 1 | 11 | 150 | 165 | 2020-07-06 | 2020-07-07 | 1 | 16 | 1500 | 1950 | 2020-07-14 | 2020-07-16 | 2 | 9 | 500 | 650 | 2020-07-19 | 2020-07-21 | 2 | 5 | 500 | 500 | 2020-07-26 | 2020-07-29 | 3 | 8 | 2500 | 2050 | 2020-07-30 | 2020-08-03 | 4 | 5 | 500 | 450 | 2020-08-03 | 2020-08-07 | 4 | 4 | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AM00040 | North | MTY | MINI | PremiumTowers |  | SiteReadyForIntegration | 7550 | 6495 | 2020-06-19 | 2020-06-21 | 2 | 500 | 400 | 2020-06-21 | 2020-06-24 | 3 | 500 | 775 | 2020-06-23 | 2020-06-26 | 2 | 600 | 720 | 2020-07-04 | 2020-07-08 | 4 | 12 | 150 | 120 | 2020-07-06 | 2020-07-10 | 4 | 16 | 1500 | 1950 | 2020-07-14 | 2020-07-18 | 4 | 8 | 500 | 350 | 2020-07-19 | 2020-07-24 | 5 | 6 | 500 | 300 | 2020-07-26 | 2020-07-31 | 5 | 7 | 2500 | 2000 | 2020-07-30 | 2020-08-05 | 6 | 5 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AM00041 | North | ZAC | SMALL | NaaS Owned |  | SiteReadyForIntegration | 7550 | 6375 | 2020-06-19 | 2020-06-20 | 1 | 500 | 520 | 2020-06-21 | 2020-06-22 | 1 | 500 | 525 | 2020-06-23 | 2020-06-25 | 3 | 600 | 480 | 2020-07-04 | 2020-07-06 | 2 | 11 | 150 | 135 | 2020-07-06 | 2020-07-08 | 2 | 16 | 1500 | 1950 | 2020-07-14 | 2020-07-16 | 2 | 8 | 500 | 300 | 2020-07-19 | 2020-07-22 | 3 | 6 | 500 | 300 | 2020-07-26 | 2020-07-30 | 4 | 8 | 2500 | 2300 | 2020-07-30 | 2020-07-30 | 0 | 0 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AM00067 | Center | GTO | MACRO | NaaS Owned |  | SiteReadyForIntegration | 7550 | 6465 | 2020-06-19 | 2020-06-20 | 1 | 500 | 440 | 2020-06-21 | 2020-06-24 | 3 | 500 | 525 | 2020-06-23 | 2020-06-27 | 3 | 600 | 900 | 2020-07-04 | 2020-07-08 | 4 | 11 | 150 | 135 | 2020-07-06 | 2020-07-10 | 4 | 16 | 1500 | 1650 | 2020-07-14 | 2020-07-19 | 5 | 9 | 500 | 250 | 2020-07-19 | 2020-07-25 | 6 | 6 | 500 | 550 | 2020-07-26 | 2020-08-01 | 6 | 7 | 2500 | 2150 | 2020-07-30 | 2020-08-05 | 6 | 4 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AM00100 | Center | QRO | MINI | NeatTowers |  | SiteReadyForIntegration | 7550 | 5995 | 2020-06-19 | 2020-06-21 | 2 | 500 | 460 | 2020-06-21 | 2020-06-24 | 3 | 500 | 425 | 2020-06-23 | 2020-06-26 | 2 | 600 | 360 | 2020-07-04 | 2020-07-07 | 3 | 11 | 150 | 150 | 2020-07-06 | 2020-07-10 | 4 | 16 | 1500 | 1650 | 2020-07-14 | 2020-07-19 | 5 | 9 | 500 | 550 | 2020-07-19 | 2020-07-24 | 5 | 5 | 500 | 450 | 2020-07-26 | 2020-07-31 | 5 | 7 | 2500 | 2100 | 2020-07-30 | 2020-08-04 | 5 | 4 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AM00118 | South | VER | SMALL | NeatTowers |  | SiteReadyForIntegration | 7550 | 6095 | 2020-06-19 | 2020-06-20 | 1 | 500 | 400 | 2020-06-21 | 2020-06-23 | 2 | 500 | 675 | 2020-06-23 | 2020-06-26 | 3 | 600 | 420 | 2020-07-04 | 2020-07-08 | 4 | 12 | 150 | 150 | 2020-07-06 | 2020-07-11 | 5 | 18 | 1500 | 1500 | 2020-07-14 | 2020-07-20 | 6 | 9 | 500 | 600 | 2020-07-19 | 2020-07-26 | 7 | 6 | 500 | 300 | 2020-07-26 | 2020-08-02 | 7 | 7 | 2500 | 2200 | 2020-07-30 | 2020-08-07 | 8 | 5 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AM00147 | South | CHI | MACRO | SuperTowers |  | SiteReadyForIntegration | 7550 | 6415 | 2020-06-19 | 2020-06-20 | 1 | 500 | 420 | 2020-06-21 | 2020-06-26 | 5 | 500 | 725 | 2020-06-23 | 2020-06-29 | 3 | 600 | 420 | 2020-07-04 | 2020-07-10 | 6 | 11 | 150 | 180 | 2020-07-06 | 2020-07-12 | 6 | 16 | 1500 | 1650 | 2020-07-14 | 2020-07-20 | 6 | 8 | 500 | 300 | 2020-07-19 | 2020-07-26 | 7 | 6 | 500 | 700 | 2020-07-26 | 2020-08-03 | 8 | 8 | 2500 | 2200 | 2020-07-30 | 2020-08-07 | 8 | 4 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AM00230 | North | MTY | MINI | PremiumTowers |  | SiteReadyForIntegration | 7550 | 6795 | 2020-06-19 | 2020-06-21 | 2 | 500 | 500 | 2020-06-21 | 2020-06-25 | 4 | 500 | 475 | 2020-06-23 | 2020-06-27 | 2 | 600 | 720 | 2020-07-04 | 2020-07-08 | 4 | 11 | 150 | 165 | 2020-07-06 | 2020-07-11 | 5 | 16 | 1500 | 1800 | 2020-07-14 | 2020-07-19 | 5 | 8 | 500 | 400 | 2020-07-19 | 2020-07-25 | 6 | 6 | 500 | 450 | 2020-07-26 | 2020-08-01 | 6 | 7 | 2500 | 2450 | 2020-07-30 | 2020-08-05 | 6 | 4 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AY00031 | North | ZAC | SMALL | NaaS Owned |  | SiteReadyForIntegration | 7550 | 5845 | 2020-06-19 | 2020-06-21 | 2 | 500 | 500 | 2020-06-21 | 2020-06-23 | 2 | 500 | 525 | 2020-06-23 | 2020-06-26 | 3 | 600 | 420 | 2020-07-04 | 2020-07-08 | 4 | 12 | 150 | 135 | 2020-07-06 | 2020-07-10 | 4 | 17 | 1500 | 1050 | 2020-07-14 | 2020-07-19 | 5 | 9 | 500 | 700 | 2020-07-19 | 2020-07-25 | 6 | 6 | 500 | 600 | 2020-07-26 | 2020-08-02 | 7 | 8 | 2500 | 2050 | 2020-07-30 | 2020-08-07 | 8 | 5 | 500 |  | 2020-08-03 |  | - | - | 250 |  | 2020-08-07 |  | - | - | 200 |  | 2020-08-15 |  | - | 55
AY00210 | Center | GTO | MACRO | NaaS Owned |  | SiteReadyForIntegration | 7550 | 6295 | 2020-06-26 | 2020-06-27 | 1 | 500 | 580 | 2020-06-28 | 2020-07-02 | 4 | 500 | 375 | 2020-06-30 | 2020-07-04 | 2 | 600 | 840 | 2020-07-11 | 2020-07-16 | 5 | 12 | 150 | 135 | 2020-07-13 | 2020-07-19 | 6 | 17 | 1500 | 1650 | 2020-07-21 | 2020-07-27 | 6 | 8 | 500 | 350 | 2020-07-26 | 2020-08-01 | 6 | 5 | 500 | 300 | 2020-08-02 | 2020-08-09 | 7 | 8 | 2500 | 2200 | 2020-08-06 | 2020-08-14 | 8 | 5 | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
HU00200 | Center | QRO | MINI | SuperTowers |  | SiteReadyForIntegration | 7550 | 6005 | 2020-06-26 | 2020-06-28 | 2 | 500 | 460 | 2020-06-28 | 2020-07-02 | 4 | 500 | 475 | 2020-06-30 | 2020-07-05 | 3 | 600 | 420 | 2020-07-11 | 2020-07-17 | 6 | 12 | 150 | 180 | 2020-07-13 | 2020-07-19 | 6 | 17 | 1500 | 1350 | 2020-07-21 | 2020-07-28 | 7 | 9 | 500 | 400 | 2020-07-26 | 2020-08-02 | 7 | 5 | 500 | 700 | 2020-08-02 | 2020-08-10 | 8 | 8 | 2500 | 2200 | 2020-08-06 | 2020-08-14 | 8 | 4 | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
AN00035 | South | VER | SMALL | PremiumTowers |  | SiteReadyForInstallation | 7550 | 5035 | 2020-06-26 | 2020-06-28 | 2 | 500 | 580 | 2020-06-28 | 2020-07-02 | 4 | 500 | 675 | 2020-06-30 | 2020-07-04 | 2 | 600 | 780 | 2020-07-11 | 2020-07-16 | 5 | 12 | 150 | 120 | 2020-07-13 | 2020-07-18 | 5 | 16 | 1500 | 2250 | 2020-07-21 | 2020-07-26 | 5 | 8 | 500 | 350 | 2020-07-26 | 2020-08-01 | 6 | 6 | 500 | 400 | 2020-08-02 | 2020-08-08 | 6 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
AN00228 | South | CHI | MACRO | NaaS Owned |  | SiteReadyForInstallation | 7550 | 5115 | 2020-06-26 | 2020-06-27 | 1 | 500 | 500 | 2020-06-28 | 2020-07-02 | 4 | 500 | 825 | 2020-06-30 | 2020-07-04 | 2 | 600 | 540 | 2020-07-11 | 2020-07-16 | 5 | 12 | 150 | 135 | 2020-07-13 | 2020-07-19 | 6 | 17 | 1500 | 2100 | 2020-07-21 | 2020-07-27 | 6 | 8 | 500 | 450 | 2020-07-26 | 2020-08-01 | 6 | 5 | 500 | 700 | 2020-08-02 | 2020-08-08 | 6 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
AM00059 | North | MTY | MINI | NaaS Owned |  | SiteReadyForInstallation | 7550 | 4205 | 2020-06-26 | 2020-06-28 | 2 | 500 | 400 | 2020-06-28 | 2020-06-30 | 2 | 500 | 375 | 2020-06-30 | 2020-07-02 | 2 | 600 | 780 | 2020-07-11 | 2020-07-13 | 2 | 11 | 150 | 165 | 2020-07-13 | 2020-07-16 | 3 | 16 | 1500 | 1500 | 2020-07-21 | 2020-07-25 | 4 | 9 | 500 | 700 | 2020-07-26 | 2020-07-31 | 5 | 6 | 500 | 450 | 2020-08-02 | 2020-08-07 | 5 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
AM00227 | North | ZAC | SMALL | NeatTowers |  | SiteReadyForInstallation | 7550 | 3925 | 2020-06-26 | 2020-06-28 | 2 | 500 | 560 | 2020-06-28 | 2020-06-29 | 1 | 500 | 425 | 2020-06-30 | 2020-07-01 | 2 | 600 | 540 | 2020-07-11 | 2020-07-12 | 1 | 11 | 150 | 165 | 2020-07-13 | 2020-07-14 | 1 | 15 | 1500 | 1200 | 2020-07-21 | 2020-07-23 | 2 | 9 | 500 | 600 | 2020-07-26 | 2020-07-28 | 2 | 5 | 500 | 600 | 2020-08-02 | 2020-08-02 | 0 | 5 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00226 | Center | GTO | SMALL | SuperTowers |  | SiteReadyForInstallation | 7550 | 4115 | 2020-06-26 | 2020-06-27 | 1 | 500 | 420 | 2020-06-28 | 2020-07-03 | 5 | 500 | 775 | 2020-06-30 | 2020-07-05 | 2 | 600 | 420 | 2020-07-11 | 2020-07-17 | 6 | 12 | 150 | 165 | 2020-07-13 | 2020-07-19 | 6 | 16 | 1500 | 1500 | 2020-07-21 | 2020-07-28 | 7 | 9 | 500 | 700 | 2020-07-26 | 2020-08-02 | 7 | 5 | 500 | 300 | 2020-08-02 | 2020-08-09 | 7 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00227 | Center | QRO | MACRO | PremiumTowers |  | SiteReadyForInstallation | 7550 | 3825 | 2020-06-26 | 2020-06-27 | 1 | 500 | 400 | 2020-06-28 | 2020-06-29 | 1 | 500 | 625 | 2020-06-30 | 2020-07-02 | 3 | 600 | 900 | 2020-07-11 | 2020-07-13 | 2 | 11 | 150 | 120 | 2020-07-13 | 2020-07-16 | 3 | 17 | 1500 | 1200 | 2020-07-21 | 2020-07-24 | 3 | 8 | 500 | 250 | 2020-07-26 | 2020-07-30 | 4 | 6 | 500 | 450 | 2020-08-02 | 2020-08-06 | 4 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00229 | South | VER | MINI | NaaS Owned |  | SiteReadyForInstallation | 7550 | 4695 | 2020-06-26 | 2020-06-28 | 2 | 500 | 460 | 2020-06-28 | 2020-06-28 | 0 | 500 | 775 | 2020-06-30 | 2020-06-30 | 2 | 600 | 660 | 2020-07-11 | 2020-07-11 | 0 | 11 | 150 | 180 | 2020-07-13 | 2020-07-13 | 0 | 15 | 1500 | 1500 | 2020-07-21 | 2020-07-22 | 1 | 9 | 500 | 600 | 2020-07-26 | 2020-07-27 | 1 | 5 | 500 | 700 | 2020-08-02 | 2020-08-04 | 2 | 8 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00170 | South | CHI | SMALL | NaaS Owned |  | SiteReadyForInstallation | 7550 | 4575 | 2020-06-26 | 2020-06-28 | 2 | 500 | 460 | 2020-06-28 | 2020-07-01 | 3 | 500 | 675 | 2020-06-30 | 2020-07-03 | 2 | 600 | 840 | 2020-07-11 | 2020-07-14 | 3 | 11 | 150 | 120 | 2020-07-13 | 2020-07-17 | 4 | 16 | 1500 | 1200 | 2020-07-21 | 2020-07-26 | 5 | 9 | 500 | 700 | 2020-07-26 | 2020-08-01 | 6 | 6 | 500 | 700 | 2020-08-02 | 2020-08-08 | 6 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00179 | North | ZAC | MACRO | PremiumTowers |  | SiteReadyForInstallation | 7550 | 4155 | 2020-06-26 | 2020-06-27 | 1 | 500 | 580 | 2020-06-28 | 2020-06-30 | 2 | 500 | 575 | 2020-06-30 | 2020-07-03 | 3 | 600 | 600 | 2020-07-11 | 2020-07-14 | 3 | 11 | 150 | 150 | 2020-07-13 | 2020-07-16 | 3 | 16 | 1500 | 1650 | 2020-07-21 | 2020-07-25 | 4 | 9 | 500 | 500 | 2020-07-26 | 2020-07-31 | 5 | 6 | 500 | 250 | 2020-08-02 | 2020-08-08 | 6 | 8 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00244 | North | GTO | MINI | NaaS Owned |  | SiteReadyForInstallation | 7550 | 3685 | 2020-06-26 | 2020-06-28 | 2 | 500 | 580 | 2020-06-28 | 2020-06-28 | 0 | 500 | 375 | 2020-06-30 | 2020-06-30 | 2 | 600 | 780 | 2020-07-11 | 2020-07-12 | 1 | 12 | 150 | 165 | 2020-07-13 | 2020-07-15 | 2 | 17 | 1500 | 1050 | 2020-07-21 | 2020-07-24 | 3 | 9 | 500 | 600 | 2020-07-26 | 2020-07-29 | 3 | 5 | 500 | 300 | 2020-08-02 | 2020-08-05 | 3 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00265 | Center | QRO | SMALL | NaaS Owned |  | SiteReadyForInstallation | 7550 | 4815 | 2020-06-26 | 2020-06-27 | 1 | 500 | 440 | 2020-06-28 | 2020-07-01 | 3 | 500 | 675 | 2020-06-30 | 2020-07-04 | 3 | 600 | 900 | 2020-07-11 | 2020-07-16 | 5 | 12 | 150 | 165 | 2020-07-13 | 2020-07-19 | 6 | 18 | 1500 | 1650 | 2020-07-21 | 2020-07-28 | 7 | 9 | 500 | 700 | 2020-07-26 | 2020-08-03 | 8 | 6 | 500 | 450 | 2020-08-02 | 2020-08-10 | 8 | 7 | 2500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-10 |  | - | - | 250 |  | 2020-08-14 |  | - | - | 200 |  | 2020-08-22 |  | - | 55
PI00309 | Center | VER | MACRO | SuperTowers |  | TX_Ready | 7550 | 3095 | 2020-06-29 | 2020-06-30 | 1 | 500 | 460 | 2020-07-01 | 2020-07-03 | 2 | 500 | 525 | 2020-07-03 | 2020-07-06 | 3 | 600 | 660 | 2020-07-14 | 2020-07-18 | 4 | 12 | 150 | 135 | 2020-07-16 | 2020-07-20 | 4 | 17 | 1500 | 1200 | 2020-07-24 | 2020-07-28 | 4 | 8 | 500 | 250 | 2020-07-29 | 2020-08-03 | 5 | 6 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00188 | South | CHI | MINI | PremiumTowers |  | TX_Ready | 7550 | 4415 | 2020-06-29 | 2020-07-01 | 2 | 500 | 520 | 2020-07-01 | 2020-07-01 | 0 | 500 | 625 | 2020-07-03 | 2020-07-03 | 2 | 600 | 420 | 2020-07-14 | 2020-07-14 | 0 | 11 | 150 | 180 | 2020-07-16 | 2020-07-16 | 0 | 15 | 1500 | 2250 | 2020-07-24 | 2020-07-24 | 0 | 8 | 500 | 600 | 2020-07-29 | 2020-07-29 | 0 | 5 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00269 | South | MTY | SMALL | NaaS Owned |  | TX_Ready | 7550 | 3585 | 2020-06-29 | 2020-07-01 | 2 | 500 | 440 | 2020-07-01 | 2020-07-02 | 1 | 500 | 675 | 2020-07-03 | 2020-07-04 | 2 | 600 | 720 | 2020-07-14 | 2020-07-16 | 2 | 12 | 150 | 165 | 2020-07-16 | 2020-07-19 | 3 | 17 | 1500 | 1350 | 2020-07-24 | 2020-07-28 | 4 | 9 | 500 | 400 | 2020-07-29 | 2020-08-03 | 5 | 6 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00213 | North | ZAC | MACRO | NaaS Owned |  | TX_Ready | 7550 | 4285 | 2020-06-29 | 2020-07-01 | 2 | 500 | 480 | 2020-07-01 | 2020-07-05 | 4 | 500 | 825 | 2020-07-03 | 2020-07-08 | 3 | 600 | 480 | 2020-07-14 | 2020-07-19 | 5 | 11 | 150 | 165 | 2020-07-16 | 2020-07-21 | 5 | 16 | 1500 | 2250 | 2020-07-24 | 2020-07-30 | 6 | 9 | 500 | 250 | 2020-07-29 | 2020-08-05 | 7 | 6 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00225 | North | GTO | MINI | NeatTowers |  | TX_Ready | 7550 | 3145 | 2020-06-29 | 2020-06-30 | 1 | 500 | 440 | 2020-07-01 | 2020-07-02 | 1 | 500 | 525 | 2020-07-03 | 2020-07-04 | 2 | 600 | 780 | 2020-07-14 | 2020-07-15 | 1 | 11 | 150 | 150 | 2020-07-16 | 2020-07-18 | 2 | 16 | 1500 | 1050 | 2020-07-24 | 2020-07-27 | 3 | 9 | 500 | 350 | 2020-07-29 | 2020-08-02 | 4 | 6 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00240 | Center | QRO | SMALL | SuperTowers |  | TX_Ready | 7550 | 3075 | 2020-06-29 | 2020-06-30 | 1 | 500 | 420 | 2020-07-01 | 2020-07-02 | 1 | 500 | 625 | 2020-07-03 | 2020-07-04 | 2 | 600 | 480 | 2020-07-14 | 2020-07-16 | 2 | 12 | 150 | 180 | 2020-07-16 | 2020-07-19 | 3 | 17 | 1500 | 1050 | 2020-07-24 | 2020-07-27 | 3 | 8 | 500 | 500 | 2020-07-29 | 2020-08-02 | 4 | 6 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00241 | Center | MTY | MACRO | SuperTowers |  | TX_Ready | 7550 | 3295 | 2020-06-29 | 2020-06-30 | 1 | 500 | 560 | 2020-07-01 | 2020-07-03 | 2 | 500 | 575 | 2020-07-03 | 2020-07-06 | 3 | 600 | 660 | 2020-07-14 | 2020-07-18 | 4 | 12 | 150 | 135 | 2020-07-16 | 2020-07-21 | 5 | 18 | 1500 | 1200 | 2020-07-24 | 2020-07-30 | 6 | 9 | 500 | 300 | 2020-07-29 | 2020-08-05 | 7 | 6 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
AN00231 | South | ZAC | MINI | PremiumTowers |  | TX_Ready | 7550 | 3065 | 2020-06-29 | 2020-06-30 | 1 | 500 | 440 | 2020-07-01 | 2020-07-02 | 1 | 500 | 425 | 2020-07-03 | 2020-07-04 | 2 | 600 | 900 | 2020-07-14 | 2020-07-15 | 1 | 11 | 150 | 120 | 2020-07-16 | 2020-07-17 | 1 | 15 | 1500 | 1050 | 2020-07-24 | 2020-07-25 | 1 | 8 | 500 | 250 | 2020-07-29 | 2020-07-30 | 1 | 5 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
AN00262 | South | GTO | SMALL | NaaS Owned |  | TX_Ready | 7550 | 4025 | 2020-06-29 | 2020-06-30 | 1 | 500 | 420 | 2020-07-01 | 2020-07-03 | 2 | 500 | 775 | 2020-07-03 | 2020-07-05 | 2 | 600 | 780 | 2020-07-14 | 2020-07-17 | 3 | 12 | 150 | 135 | 2020-07-16 | 2020-07-19 | 3 | 16 | 1500 | 1800 | 2020-07-24 | 2020-07-25 | 1 | 6 | 500 | 250 | 2020-07-29 | 2020-08-15 | 17 | 21 | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00256 | North | QRO | MACRO | NaaS Owned |  | SiteReadyForPower | 7550 | 4075 | 2020-06-29 | 2020-06-30 | 1 | 500 | 440 | 2020-07-01 | 2020-07-01 | 0 | 500 | 725 | 2020-07-03 | 2020-07-03 | 2 | 600 | 660 | 2020-07-14 | 2020-07-14 | 0 | 11 | 150 | 120 | 2020-07-16 | 2020-07-16 | 0 | 15 | 1500 | 2250 | 2020-07-24 | 2020-07-24 | 0 | 8 | 500 |  | 2020-07-29 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00257 | North | VER | MINI | NeatTowers |  | SiteReadyForPower | 7550 | 3585 | 2020-06-29 | 2020-07-01 | 2 | 500 | 540 | 2020-07-01 | 2020-07-03 | 2 | 500 | 825 | 2020-07-03 | 2020-07-05 | 2 | 600 | 720 | 2020-07-14 | 2020-07-16 | 2 | 11 | 150 | 135 | 2020-07-16 | 2020-07-19 | 3 | 16 | 1500 | 1500 | 2020-07-24 | 2020-07-24 | 0 | 5 | 500 |  | 2020-07-29 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00277 | Center | CHI | SMALL | NeatTowers |  | SiteReadyForPower | 7550 | 2925 | 2020-06-29 | 2020-07-01 | 2 | 500 | 560 | 2020-07-01 | 2020-07-05 | 4 | 500 | 625 | 2020-07-03 | 2020-07-08 | 3 | 600 | 540 | 2020-07-14 | 2020-07-19 | 5 | 11 | 150 | 135 | 2020-07-16 | 2020-07-22 | 6 | 17 | 1500 | 1200 | 2020-07-24 | 2020-07-31 | 7 | 9 | 500 |  | 2020-07-29 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00308 | Center | MTY | MACRO | SuperTowers |  | SiteReadyForPower | 7550 | 2495 | 2020-06-29 | 2020-06-30 | 1 | 500 | 580 | 2020-07-01 | 2020-07-06 | 5 | 500 | 475 | 2020-07-03 | 2020-07-09 | 3 | 600 | 540 | 2020-07-14 | 2020-07-21 | 7 | 12 | 150 | 165 | 2020-07-16 | 2020-07-23 | 7 | 17 | 1500 | 900 | 2020-07-24 | 2020-08-01 | 8 | 9 | 500 |  | 2020-07-29 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00313 | South | ZAC | MINI | PremiumTowers |  | SiteReadyForPower | 7550 | 2535 | 2020-06-29 | 2020-06-30 | 1 | 500 | 540 | 2020-07-01 | 2020-07-02 | 1 | 500 | 525 | 2020-07-03 | 2020-07-04 | 2 | 600 | 420 | 2020-07-14 | 2020-07-15 | 1 | 11 | 150 | 165 | 2020-07-16 | 2020-07-17 | 1 | 15 | 1500 | 1050 | 2020-07-24 | 2020-07-25 | 1 | 8 | 500 |  | 2020-07-29 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
AP00049 | South | GTO | SMALL | NaaS Owned |  | SiteReadyForPower | 7550 | 3375 | 2020-06-29 | 2020-06-30 | 1 | 500 | 540 | 2020-07-01 | 2020-07-03 | 2 | 500 | 525 | 2020-07-03 | 2020-07-05 | 2 | 600 | 360 | 2020-07-14 | 2020-07-17 | 3 | 12 | 150 | 180 | 2020-07-16 | 2020-07-19 | 3 | 16 | 1500 | 1950 | 2020-07-24 | 2020-07-28 | 4 | 9 | 500 |  | 2020-07-29 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00135 | North | QRO | MACRO | NaaS Owned |  | SiteReadyForPower | 7550 | 3505 | 2020-06-29 | 2020-07-01 | 2 | 500 | 460 | 2020-07-01 | 2020-07-05 | 4 | 500 | 375 | 2020-07-03 | 2020-07-07 | 2 | 600 | 420 | 2020-07-14 | 2020-07-18 | 4 | 11 | 150 | 120 | 2020-07-16 | 2020-07-21 | 5 | 16 | 1500 | 2250 | 2020-07-24 | 2020-07-30 | 6 | 9 | 500 |  | 2020-07-29 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 2500 |  | 2020-08-09 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 250 |  | 2020-08-17 |  | - | - | 200 |  | 2020-08-25 |  | - | 55
PI00184 | North | VER | MINI | SuperTowers |  | SiteReadyForPower | 7550 | 3715 | 2020-07-06 | 2020-07-07 | 1 | 500 | 540 | 2020-07-08 | 2020-07-09 | 1 | 500 | 625 | 2020-07-10 | 2020-07-12 | 3 | 600 | 600 | 2020-07-21 | 2020-07-23 | 2 | 11 | 150 | 165 | 2020-07-23 | 2020-07-26 | 3 | 17 | 1500 | 1950 | 2020-07-31 | 2020-08-03 | 3 | 8 | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
AP00092 | Center | CHI | SMALL | PremiumTowers |  | SiteReadyForPower | 7550 | 2665 | 2020-07-06 | 2020-07-08 | 2 | 500 | 400 | 2020-07-08 | 2020-07-09 | 1 | 500 | 525 | 2020-07-10 | 2020-07-12 | 3 | 600 | 540 | 2020-07-21 | 2020-07-24 | 3 | 12 | 150 | 165 | 2020-07-23 | 2020-07-26 | 3 | 17 | 1500 | 1200 | 2020-07-31 | 2020-08-04 | 4 | 9 | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
AP00146 | Center | MTY | MACRO | NaaS Owned |  | SiteReadyForPower | 7550 | 3835 | 2020-07-06 | 2020-07-08 | 2 | 500 | 480 | 2020-07-08 | 2020-07-11 | 3 | 500 | 775 | 2020-07-10 | 2020-07-14 | 3 | 600 | 780 | 2020-07-21 | 2020-07-26 | 5 | 12 | 150 | 165 | 2020-07-23 | 2020-07-28 | 5 | 17 | 1500 | 1800 | 2020-07-31 | 2020-08-05 | 5 | 8 | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
AP00231 | South | ZAC | MINI | NaaS Owned |  | SiteReadyForCW | 7550 | 1975 | 2020-07-06 | 2020-07-08 | 2 | 500 | 500 | 2020-07-08 | 2020-07-09 | 1 | 500 | 575 | 2020-07-10 | 2020-07-11 | 2 | 600 | 900 | 2020-07-21 | 2020-07-23 | 2 | 12 | 150 | 150 | 2020-07-23 | 2020-07-23 | 0 | 14 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
AP00235 | South | GTO | SMALL | NeatTowers |  | SiteReadyForCW | 7550 | 2185 | 2020-07-06 | 2020-07-08 | 2 | 500 | 460 | 2020-07-08 | 2020-07-10 | 2 | 500 | 825 | 2020-07-10 | 2020-07-13 | 3 | 600 | 900 | 2020-07-21 | 2020-07-25 | 4 | 12 | 150 | 150 | 2020-07-23 | 2020-07-27 | 4 | 17 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
AP00239 | North | QRO | MACRO | SuperTowers |  | SiteReadyForCW | 7550 | 1485 | 2020-07-06 | 2020-07-08 | 2 | 500 | 400 | 2020-07-08 | 2020-07-12 | 4 | 500 | 725 | 2020-07-10 | 2020-07-14 | 2 | 600 | 360 | 2020-07-21 | 2020-07-25 | 4 | 11 | 150 | 165 | 2020-07-23 | 2020-07-28 | 5 | 16 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
PI00189 | North | VER | MINI | PremiumTowers |  | SiteReadyForCW | 7550 | 1705 | 2020-07-06 | 2020-07-07 | 1 | 500 | 420 | 2020-07-08 | 2020-07-11 | 3 | 500 | 625 | 2020-07-10 | 2020-07-13 | 2 | 600 | 660 | 2020-07-21 | 2020-07-25 | 4 | 12 | 150 | 165 | 2020-07-23 | 2020-07-27 | 4 | 16 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
PI00282 | Center | CHI | SMALL | NaaS Owned |  | SiteReadyForCW | 7550 | 1615 | 2020-07-06 | 2020-07-07 | 1 | 500 | 460 | 2020-07-08 | 2020-07-09 | 1 | 500 | 675 | 2020-07-10 | 2020-07-11 | 2 | 600 | 480 | 2020-07-21 | 2020-07-23 | 2 | 12 | 150 | 135 | 2020-07-23 | 2020-07-23 | 0 | 14 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
PI00284 | Center | MTY | MACRO | NaaS Owned |  | SiteReadyForCW | 7550 | 2005 | 2020-07-06 | 2020-07-08 | 2 | 500 | 520 | 2020-07-08 | 2020-07-10 | 2 | 500 | 825 | 2020-07-10 | 2020-07-13 | 3 | 600 | 660 | 2020-07-21 | 2020-07-25 | 4 | 12 | 150 | 150 | 2020-07-23 | 2020-07-27 | 4 | 17 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
LO00158 | South | ZAC | MINI | PremiumTowers |  | SiteReadyForCW | 7550 | 1565 | 2020-07-06 | 2020-07-08 | 2 | 500 | 440 | 2020-07-08 | 2020-07-10 | 2 | 500 | 525 | 2020-07-10 | 2020-07-12 | 2 | 600 | 600 | 2020-07-21 | 2020-07-24 | 3 | 12 | 150 | 150 | 2020-07-23 | 2020-07-27 | 4 | 17 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
LO00159 | South | GTO | SMALL | NaaS Owned |  | SiteReadyForCW | 7550 | 1375 | 2020-07-06 | 2020-07-07 | 1 | 500 | 400 | 2020-07-08 | 2020-07-10 | 2 | 500 | 375 | 2020-07-10 | 2020-07-12 | 2 | 600 | 600 | 2020-07-21 | 2020-07-24 | 3 | 12 | 150 | 135 | 2020-07-23 | 2020-07-27 | 4 | 17 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
CA00351 | North | QRO | MACRO | NaaS Owned |  | SiteReadyForCW | 7550 | 1695 | 2020-07-06 | 2020-07-07 | 1 | 500 | 420 | 2020-07-08 | 2020-07-12 | 4 | 500 | 375 | 2020-07-10 | 2020-07-14 | 2 | 600 | 900 | 2020-07-21 | 2020-07-26 | 5 | 12 | 150 | 180 | 2020-07-23 | 2020-07-28 | 5 | 16 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
CA00514 | North | VER | MINI | SuperTowers |  | SiteReadyForCW | 7550 | 1685 | 2020-07-06 | 2020-07-07 | 1 | 500 | 420 | 2020-07-08 | 2020-07-13 | 5 | 500 | 725 | 2020-07-10 | 2020-07-16 | 3 | 600 | 540 | 2020-07-21 | 2020-07-27 | 6 | 11 | 150 | 150 | 2020-07-23 | 2020-07-29 | 6 | 16 | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
JU00157 | Center | CHI | SMALL | PremiumTowers |  | SiteAcquired | 7550 | 1425 | 2020-07-06 | 2020-07-08 | 2 | 500 | 580 | 2020-07-08 | 2020-07-09 | 1 | 500 | 425 | 2020-07-10 | 2020-07-12 | 3 | 600 | 420 | 2020-07-21 | 2020-07-24 | 3 | 12 | 150 |  | 2020-07-23 |  | - | - | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
JU00247 | Center | MTY | MACRO | NaaS Owned |  | SiteAcquired | 7550 | 1655 | 2020-07-06 | 2020-07-07 | 1 | 500 | 440 | 2020-07-08 | 2020-07-08 | 0 | 500 | 675 | 2020-07-10 | 2020-07-10 | 2 | 600 | 540 | 2020-07-21 | 2020-07-22 | 1 | 12 | 150 |  | 2020-07-23 |  | - | - | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
JU00229 | South | ZAC | MINI | NaaS Owned |  | SiteAcquired | 7550 | 1505 | 2020-07-06 | 2020-07-08 | 2 | 500 | 420 | 2020-07-08 | 2020-07-09 | 1 | 500 | 725 | 2020-07-10 | 2020-07-11 | 2 | 600 | 360 | 2020-07-21 | 2020-07-21 | 0 | 10 | 150 |  | 2020-07-23 |  | - | - | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
JU00415 | South | GTO | SMALL | NeatTowers |  | SiteAcquired | 7550 | 1855 | 2020-07-06 | 2020-07-08 | 2 | 500 | 460 | 2020-07-08 | 2020-07-11 | 3 | 500 | 675 | 2020-07-10 | 2020-07-10 | -1 | 600 | 720 | 2020-07-21 | 2020-07-25 | 4 | 15 | 150 |  | 2020-07-23 |  | - | - | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
LA00134 | North | QRO | MACRO | SuperTowers |  | SiteSurveyCompleted | 7550 | 1125 | 2020-07-06 | 2020-07-08 | 2 | 500 | 400 | 2020-07-08 | 2020-07-11 | 3 | 500 | 725 | 2020-07-10 | 2020-07-11 | 0 | 600 |  | 2020-07-21 |  | - | - | 150 |  | 2020-07-23 |  | - | - | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
LA00613 | North | VER | MINI | PremiumTowers |  | SiteSurveyCompleted | 7550 | 1045 | 2020-07-06 | 2020-07-07 | 1 | 500 | 420 | 2020-07-08 | 2020-07-09 | 1 | 500 | 625 | 2020-07-10 | 2020-07-10 | 1 | 600 |  | 2020-07-21 |  | - | - | 150 |  | 2020-07-23 |  | - | - | 1500 |  | 2020-07-31 |  | - | - | 500 |  | 2020-08-05 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 2500 |  | 2020-08-16 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 250 |  | 2020-08-24 |  | - | - | 200 |  | 2020-09-01 |  | - | 55
LI01455 | Center | CHI | SMALL | SuperTowers |  | SiteDesignReady | 7550 | 460 | 2020-07-13 | 2020-07-20 | 7 | 500 | 460 | 2020-07-15 | 2020-07-16 | 1 | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
LI01461 | Center | MTY | MINI | PremiumTowers |  | SiteDesignReady | 7550 | 480 | 2020-07-13 | 2020-07-15 | 2 | 500 | 480 | 2020-07-15 | 2020-07-16 | 1 | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
LI01476 | South | ZAC | SMALL | NaaS Owned |  | SiteDesignReady | 7550 | 560 | 2020-07-13 | 2020-07-15 | 2 | 500 | 560 | 2020-07-15 | 2020-07-15 | 0 | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
LI01542 | South | GTO | MACRO | NaaS Owned |  | SiteDesignReady | 7550 | 540 | 2020-07-13 | 2020-07-13 | 0 | 500 | 540 | 2020-07-15 | 2020-07-16 | 1 | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
LI02051 | North | QRO | MINI | NeatTowers |  | SiteDesignStarted | 7550 | 0 | 2020-07-12 | 2020-07-14 | 2 | 500 |  | 2020-07-14 |  | - | 500 |  | 2020-07-16 |  | - | 600 |  | 2020-07-27 |  | - | - | 150 |  | 2020-07-29 |  | - | - | 1500 |  | 2020-08-06 |  | - | - | 500 |  | 2020-08-11 |  | - | - | 500 |  | 2020-08-18 |  | - | - | 2500 |  | 2020-08-22 |  | - | - | 500 |  | 2020-08-26 |  | - | - | 250 |  | 2020-08-30 |  | - | - | 200 |  | 2020-09-07 |  | - | 55
LI02052 | North | VER | SMALL | NeatTowers |  | SiteDesignStarted | 7550 | 0 | 2020-07-13 | 2020-07-14 | 1 | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
LI01472 | Center | CHI | MACRO | SuperTowers |  | SiteDesignStarted | 7550 | 0 | 2020-07-13 | 2020-07-14 | 1 | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
LI01483 | Center | MTY | MINI | PremiumTowers |  | SiteDesignStarted | 7550 | 0 | 2020-07-13 | 2020-07-14 | 1 | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
LI01550 | South | ZAC | SMALL | NaaS Owned |  | SiteDesignStarted | 7550 | 0 | 2020-07-14 | 2020-07-14 | 0 | 500 |  | 2020-07-16 |  | - | 500 |  | 2020-07-18 |  | - | 600 |  | 2020-07-29 |  | - | - | 150 |  | 2020-07-31 |  | - | - | 1500 |  | 2020-08-08 |  | - | - | 500 |  | 2020-08-13 |  | - | - | 500 |  | 2020-08-20 |  | - | - | 2500 |  | 2020-08-24 |  | - | - | 500 |  | 2020-08-28 |  | - | - | 250 |  | 2020-09-01 |  | - | - | 200 |  | 2020-09-09 |  | - | 55
PI00220 | South | GTO | MACRO | NaaS Owned |  | SiteDesignStarted | 7550 | 0 | 2020-07-13 | 2020-07-13 | 0 | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
PI00246 | North | QRO | MINI | SuperTowers |  | SiteDesignNotStarted | 7550 | 0 | 2020-07-13 |  |  | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
AM00004 | North | VER | SMALL | PremiumTowers |  | SiteDesignNotStarted | 7550 | 0 | 2020-07-13 |  |  | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
AM00226 | Center | CHI | MACRO | NaaS Owned |  | SiteDesignNotStarted | 7550 | 0 | 2020-07-13 |  |  | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
AP00017 | Center | MTY | MINI | NaaS Owned |  | SiteDesignNotStarted | 7550 | 0 | 2020-07-13 |  |  | 500 |  | 2020-07-15 |  | - | 500 |  | 2020-07-17 |  | - | 600 |  | 2020-07-28 |  | - | - | 150 |  | 2020-07-30 |  | - | - | 1500 |  | 2020-08-07 |  | - | - | 500 |  | 2020-08-12 |  | - | - | 500 |  | 2020-08-19 |  | - | - | 2500 |  | 2020-08-23 |  | - | - | 500 |  | 2020-08-27 |  | - | - | 250 |  | 2020-08-31 |  | - | - | 200 |  | 2020-09-08 |  | - | 55
Formulas:
SiteDesignReady_BL = Table_SiteMilestoneTracking[[#This Row],[SiteDesignStarted_BL]]+t0_SiteDesignDelayBL
SiteSurveyCompleted_BL = Table_SiteMilestoneTracking[[#This Row],[SiteDesignReady_BL]]+t1_SiteSurveyBL
SiteAcquired_BL = Table_SiteMilestoneTracking[[#This Row],[SiteSurveyCompleted_BL]]+t2_SiteAcquisitionBL
SiteReadyForCW_BL = Table_SiteMilestoneTracking[[#This Row],[SiteAcquired_BL]]+t2a_SiteCWReadinessBL
Power Construction = Table_SiteMilestoneTracking[[#This Row],[SiteReadyForCW_BL]]+t3_CivilWorksBL
Tx = Table_SiteMilestoneTracking[[#This Row],[SiteReadyForPower_BL]]+t4_PowerInstallBL
Installation & Commissioning = Table_SiteMilestoneTracking[[#This Row],[TXReady_BL]]+t5_TxintegrationBL
Integration = Table_SiteMilestoneTracking[[#This Row],[SiteReadyForInstallation_BL]]+t6_InstallationBL
SiteOnAir_BL = Table_SiteMilestoneTracking[[#This Row],[SiteReadyForIntegration_BL]]+t7_IntegrationBL
SiteAccepted_BL = Table_SiteMilestoneTracking[[#This Row],[SiteOnAir_BL]]+t8_AcceptanceBL
SiteInOperations_BL = Table_SiteMilestoneTracking[[#This Row],[SiteAccepted_BL]]+t9_HandoverBL
Note on A3: Unique Site Identifier
Note on B3: Region where site is located
Note on C3: District or State where site is located
Note on D3: Site Configuration Type
Note on E3: Tower Construction Company Assigned to Site
Note on F3: Tower ID where Equipment will be installed
Note on G3: Current Milestone Depends on the last actual recorded milestone.
Note on H3: Planned Total Cost of Site Deployment using Three-Point Estimate
Note on I3: Accumulated Cost in Current Milestone
Note on J3: Planned Site Design Start Date
Note on K3: Site Design Actual Start date
Note on L3: Site Design Start Delay Actual Dates vs Planned Dates in Days
Note on M3: Planned Site Design Cost using ThreeCost Estimate
Note on N3: Site Design Actual Cost
Note on O3: Planned Site Design Completion Date using Three-Point Estimate
Note on P3: Actual Site Design Completion
Note on Q3: Site Design Completion Delay Actual Dates vs Planned Dates in Days
Note on R3: Planned Cost of Site Survey using Three-Point Estimate
Note on S3: Actual Cost of Site Survey
Note on T3: Site Survey Planned Completition date using Three-Point Estimate
Note on U3: Site Survey Actual Completion Date
Note on V3: Site Survey Actual Dates vs Planned Dates in Days
Note on W3: Planned Cost of Site Acquisition using Three-Point Estimate
Note on X3: Site Acquisition Actual Cost
Note on Y3: Site Acquisition Planned Completion Date Using Three-Point Estimate
Note on Z3: Site Acquisition Planned Completion Date
Note on AA3: Site Acquisition Delay Actual Dates vs Planned Dates in Days
Note on AB3: Actual Time in days from Site Survey to Site Acuired
Note on AE3: Site Ready for CW Planned Completion Date
Note on AF3: Site Acquisition Actual Completion Date
Note on AG3: Site Ready for CW Delay Actual Dates vs Planned Dates in Days
Note on AH3: Actual Time in days from Site Design to Site Ready for CW
Note on AI3: Planned Cost of Civil Works using Three-Point Estimate
Note on AJ3: Actual Cost of Civil Works
Note on AK3: Site Ready for Power Planned Completion Date
Note on AL3: Site Ready for Power Actual Completion Date
Note on AM3: Site Ready for Power Delay Actual Dates vs Planned Dates in Days
Note on AN3: Actual Time in days from Site Ready for CW to Site Ready for Power
Note on AO3: Planned Cost of Power Construciton using Three-Point Estimate
Note on AP3: Actual Cost of Power Installation
Note on AQ3: TX Ready Planned Completion Date using Three-Point Estimate
Note on AR3: TX Ready Actual Completion Date
Note on AS3: TX Ready Delay Actual Dates vs Planned Dates in Days
Note on AT3: Actual Time in days from Power Installation to TX Ready
Note on AU3: Planned Cost of TX Integration using Three-Point Estimate
Note on AV3: Actual Cost of TX Installation
Note on AW3: Site Ready for Installation Planned Date using Three-Point Estimate
Note on AX3: Site Ready for Installation Actual Date
Note on AY3: Site Ready for Installation Delay Actual Dates vs Planned Dates in Days
Note on AZ3: Actual Time in days from Tx Integration to Site Installation
Note on BA3: Planned Cost of Equipment Installation using Three-Point Estimate
Note on BB3: Actual Cost of Equipment Installation
Note on BC3: Site Ready for Integration Planned Date using Three-Point Estimate
Note on BD3: Site Ready for Integration Actual Date
Note on BE3: Site Ready for Integration Delay Actual Dates vs Planned Dates in Days
Note on BF3: Actual Time in days from Installation to Site Integration
Note on BG3: Planned Cost of Integration using Three-Point Estimate
Note on BH3: Actual Cost of Integration
Note on BI3: Site on Air Planned Date using Three-Point Estimate
Note on BJ3: Site On Air Actual Date
Note on BK3: Site On Air Delay Actual Dates vs Planned Dates in Days
Note on BL3: Actual Time in days from Integration to Site on Air
Note on BM3: ATP Planned Cost using Three-Point Estimate
Note on BN3: Actual cost of ATP
Note on BO3: Site Accepted Planned Date using Three-Point Estimate
Note on BP3: Site Accepted Actual Date
Note on BQ3: Site Accepted Delay Actual Dates vs Planned Dates in Days
Note on BR3: Actual Time in days from Site on air to Site Accepted
Note on BS3: Handover to Operations Planned Cost using Three-Point Estimate
Note on BT3: Actual cost of Handover to Operations
Note on BU3: Site In Operations Planned Date using Three-Point Estimate
Note on BV3: Site In Operations Actual Date
Note on BW3: Site in Operations Delay Actual Dates vs Planned Dates in Days
Note on BX3: Planned days from Site Design to Site in Operations
Note on BY3: Actual days from Site Design to Site in Operations
Note on BZ3: End to End Delay Actual Dates vs Planned Dates in Days
Note on CA3: Delay from Site Accepted from Site in Operations

## 6. Summary Tracking Sheet
Deployment Tracking Summary
|  |  |  | 100 |  | 96 |  | 500 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 90 |  | 500 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) |  |  |  |  | 600 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) |  |  |  |  | 150 | EarnedValue (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 80 |  | 1500 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 70 |  | 500 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 60 |  | 500 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 51 |  | 2500 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 40 |  | 500 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 30 |  | 250 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 20 |  | 200 | Earned Value (EV) |  | Planned Value (PV) |  | Actual Cost (AC) | 100 |  | 10 |  | Earned Value | Planned Value | Actual Cost
Year | Week | StartDate | EndDate | SiteDesignStarted_BL | SiteDesignStarted_BL(SUM) | SiteDesignStarted_AC | SiteDesignStarted_AC(SUM) | c0_SiteDesignEV | c0_SiteDesignEV(SUM) | c0_SiteDesignCostBL | c0_SiteDesignCostBL(SUM) | c0_SiteDesignCostAC | c0_SiteDesignCostAC(SUM) | SiteDesignReady_BL | SiteDesignReady_BL(SUM) | SiteDesignReady_AC | SiteDesignReady_AC(SUM) | c1_SiteSurveyEV | c1_SiteSurveyEV(SUM) | c1_SiteSurveyCostBL | c1_SiteSurveyCostBL(SUM) | c1_SiteSurveyCostAC | c1_SiteSurveyCostAC(SUM) | SiteSurveyCompleted_BL | SiteSurveyCompleted_BL(SUM) | SiteSurveyCompleted_AC | SiteSurveyCompleted_AC(SUM) | c2_SiteAcquisitionEV | c2_SiteAcquisitionEV(SUM) | c2_SiteAcquisitionCostBL | c2_SiteAcquisitionCostBL(SUM) | c2_SiteAcquisitionCostAC | c2_SiteAcquisitionCostAC(SUM) | SiteAcquired_BL | SiteAcquired_BL(SUM) | SiteAcquired_AC | SiteAcquired_AC(SUM) | c2a_SiteCWReadinessEV | c2a_SiteCWReadinessEV(SUM) | c2a_SiteCWReadinessCostBL | c2a_SiteCWReadinessCostBL(SUM) | c2a_SiteCWReadinessCostAC | c2a_SiteCWReadinessCostAC(SUM) | ReadyForCW_BL | ReadyForCW_BL(SUM) | ReadyForCW_AC | ReadyForCW_AC(SUM) | c3_CivilWorksEV | c3_CivilWorksEV(SUM) | c3_CivilWorksCostBL | c3_CivilWorksCostBL(SUM) | c3_CivilWorksCostAC | c3_CivilWorksCostAC(SUM) | ReadyForPower_BL | ReadyForPower_BL(SUM) | ReadyForPower_AC | ReadyForPower_AC(SUM) | c4_PowerInstallEV | c4_PowerInstallEV(SUM) | c4_PowerInstallCostBL | c4_PowerInstallCostBL(SUM) | c4_PowerInstallCostAC | c4_PowerInstallCostAC(SUM) | TXReady_BL | TXReady_BL(SUM) | TXReady_AC | TXReady_AC(SUM) | c5_TxIntegrationEV | c5_TxIntegrationEV(SUM) | c5_TxIntegrationCostBL | c5_TxIntegrationCostBL(SUM) | c5_TxIntegrationCostAC | c5_TxIntegrationCostAC(SUM) | ReadyForInstallation_BL | ReadyForInstallation_BL(SUM) | ReadyForInstallation_AC | ReadyForInstallation_AC(SUM) | c6_InstallationEV | c6_InstallationEV(SUM) | c6_InstallationCostBL | c6_InstallationCostBL(SUM) | c6_InstallationCostAC | c6_InstallationCostAC(SUM) | ReadyForIntegration_BL | ReadyForIntegration_BL(SUM) | ReadyForIntegration_AC | ReadyForIntegration_AC(SUM) | c7_IntegrationEV | c7_IntegrationEV(SUM) | c7_IntegrationCostBL | c7_IntegrationCostBL(SUM) | c7_IntegrationCostAC | c7_IntegrationCostAC(SUM) | SiteOnAir_BL | SiteOnAir_BL(SUM) | SiteOnAir_AC | SiteOnAir_AC(SUM) | c8_AcceptanceEV | c8_AcceptanceEV(SUM) | c8_AcceptanceCostBL | c8_AcceptanceCostBL(SUM) | c8_AcceptanceCostAC | c8_AcceptanceCostAC(SUM) | SiteAccepted_BL | SiteAccepted_BL(SUM) | SiteAccepted_AC | SiteAccepted_AC(SUM) | c9_HandoverEV | c9_HandoverEV(SUM) | c9_HandoverCostBL2 | c9_HandoverCostBL(SUM) | c9_HandoverCostAC | c9_HandoverCostAC(SUM) | SiteInOperations_BL | SiteInOperations_BL(SUM) | SiteInOperations_AC | SiteInOperations_AC(SUM) | AccumulatedEV | AccumulatedPV | AccumulatedAC | ScheduleVariance(SV) | CostVariance(CV) | SPI | CPI
2020 | 1 | 2019-12-30 | 2020-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 2 | 2020-01-06 | 2020-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 3 | 2020-01-13 | 2020-01-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 4 | 2020-01-20 | 2020-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 5 | 2020-01-27 | 2020-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 6 | 2020-02-03 | 2020-02-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 7 | 2020-02-10 | 2020-02-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 8 | 2020-02-17 | 2020-02-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 9 | 2020-02-24 | 2020-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 10 | 2020-03-02 | 2020-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 11 | 2020-03-09 | 2020-03-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 12 | 2020-03-16 | 2020-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 13 | 2020-03-23 | 2020-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 14 | 2020-03-30 | 2020-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 15 | 2020-04-06 | 2020-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 16 | 2020-04-13 | 2020-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 17 | 2020-04-20 | 2020-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 18 | 2020-04-27 | 2020-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 19 | 2020-05-04 | 2020-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 20 | 2020-05-11 | 2020-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 21 | 2020-05-18 | 2020-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | / | /
2020 | 22 | 2020-05-25 | 2020-05-31 | 7 | 7 | 2 | 2 | 500 | 500 | 500 | 500 | 500 | 500 | 1 | 1 | 1 | 1 | 0 | 0 | 500 | 500 | 425 | 425 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 1000 | 925 | -500 | -425 | 0.5 | 0.54054
2020 | 23 | 2020-06-01 | 2020-06-07 | 9 | 16 | 8 | 10 | 3000 | 3500 | 3000 | 3500 | 2900 | 3400 | 6 | 7 | 6 | 7 | 0 | 0 | 3000 | 3500 | 1700 | 2125 | 6 | 7 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 7000 | 5525 | -3500 | -2025 | 0.5 | 0.63348
2020 | 24 | 2020-06-08 | 2020-06-14 | 10 | 26 | 10 | 20 | 4500 | 8000 | 4500 | 8000 | 4440 | 7840 | 9 | 16 | 9 | 16 | 500 | 500 | 4500 | 8000 | 5325 | 7450 | 9 | 16 | 9 | 14 | 600 | 600 | 4200 | 4200 | 420 | 420 | 7 | 7 | 1 | 1 | 150 | 150 | 150 | 150 | 150 | 150 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9250 | 20350 | 15860 | -11100 | -6610 | 0.45455 | 0.58323
2020 | 25 | 2020-06-15 | 2020-06-21 | 12 | 38 | 18 | 38 | 5500 | 13500 | 11000 | 19000 | 5280 | 13120 | 22 | 38 | 11 | 27 | 2000 | 2500 | 5000 | 13000 | 7950 | 15400 | 10 | 26 | 12 | 26 | 3600 | 4200 | 5400 | 9600 | 3780 | 4200 | 9 | 16 | 6 | 7 | 600 | 750 | 900 | 1050 | 615 | 765 | 6 | 7 | 4 | 5 | 1500 | 1500 | 1500 | 1500 | 2250 | 2250 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22450 | 44150 | 35735 | -21700 | -13285 | 0.50849 | 0.62824
2020 | 26 | 2020-06-22 | 2020-06-28 | 13 | 51 | 13 | 51 | 6500 | 20000 | 6500 | 25500 | 6220 | 19340 | 13 | 51 | 13 | 40 | 5000 | 7500 | 6000 | 19000 | 6375 | 21775 | 12 | 38 | 11 | 37 | 5400 | 9600 | 6000 | 15600 | 5400 | 9600 | 10 | 26 | 9 | 16 | 1500 | 2250 | 1350 | 2400 | 1515 | 2280 | 9 | 16 | 10 | 15 | 7500 | 9000 | 9000 | 10500 | 9750 | 12000 | 6 | 7 | 5 | 6 | 500 | 500 | 500 | 500 | 650 | 650 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48850 | 73500 | 65645 | -24650 | -16795 | 0.66463 | 0.74415
2020 | 27 | 2020-06-29 | 2020-07-05 | 16 | 67 | 16 | 67 | 13000 | 33000 | 8000 | 33500 | 12640 | 31980 | 16 | 67 | 26 | 66 | 5000 | 12500 | 14500 | 33500 | 14600 | 36375 | 29 | 67 | 24 | 61 | 6600 | 16200 | 7200 | 22800 | 7500 | 17100 | 12 | 38 | 11 | 27 | 1500 | 3750 | 1500 | 3900 | 1470 | 3750 | 10 | 26 | 10 | 25 | 6000 | 15000 | 13500 | 24000 | 7800 | 19800 | 9 | 16 | 4 | 10 | 1500 | 2000 | 3000 | 3500 | 1450 | 2100 | 6 | 7 | 3 | 4 | 500 | 500 | 500 | 500 | 650 | 650 | 1 | 1 | 1 | 1 | 0 | 0 | 2500 | 2500 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82950 | 124200 | 111755 | -41250 | -28805 | 0.66787 | 0.74225
2020 | 28 | 2020-07-06 | 2020-07-12 | 20 | 87 | 19 | 86 | 9500 | 42500 | 9500 | 43000 | 8740 | 40720 | 19 | 86 | 19 | 85 | 6500 | 19000 | 9500 | 43000 | 10550 | 46925 | 19 | 86 | 18 | 79 | 8400 | 24600 | 7800 | 30600 | 8580 | 25680 | 13 | 51 | 14 | 41 | 1950 | 5700 | 1800 | 5700 | 1920 | 5670 | 12 | 38 | 13 | 38 | 18000 | 33000 | 15000 | 39000 | 17250 | 37050 | 10 | 26 | 12 | 22 | 5500 | 7500 | 4500 | 8000 | 5150 | 7250 | 9 | 16 | 11 | 15 | 2000 | 2500 | 3000 | 3500 | 2150 | 2800 | 6 | 7 | 4 | 5 | 5000 | 5000 | 15000 | 17500 | 4300 | 4300 | 6 | 7 | 2 | 2 | 500 | 500 | 500 | 500 | 460 | 460 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140300 | 190800 | 170855 | -50500 | -30555 | 0.73532 | 0.82116
2020 | 29 | 2020-07-13 | 2020-07-19 | 13 | 100 | 9 | 95 | 2500 | 45000 | 7000 | 50000 | 2460 | 43180 | 14 | 100 | 5 | 90 | 11500 | 30500 | 7000 | 50000 | 4875 | 51800 | 14 | 100 | 7 | 86 | 15000 | 39600 | 9600 | 40200 | 16020 | 41700 | 16 | 67 | 25 | 66 | 3450 | 9150 | 4350 | 10050 | 3495 | 9165 | 29 | 67 | 23 | 61 | 19500 | 52500 | 18000 | 57000 | 21750 | 58800 | 12 | 38 | 13 | 35 | 5000 | 12500 | 11000 | 19000 | 4400 | 11650 | 22 | 38 | 10 | 25 | 3500 | 6000 | 4500 | 8000 | 3500 | 6300 | 9 | 16 | 7 | 12 | 12500 | 17500 | 22500 | 40000 | 11100 | 15400 | 9 | 16 | 5 | 7 | 2500 | 3000 | 3000 | 3500 | 2345 | 2805 | 6 | 7 | 5 | 6 | 500 | 500 | 1750 | 1750 | 500 | 500 | 7 | 7 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216250 | 279500 | 241300 | -63250 | -25050 | 0.7737 | 0.89619
2020 | 30 | 2020-07-20 | 2020-07-26 | 0 | 100 | 1 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 5000 | 35500 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 10200 | 49800 | 11400 | 51600 | 10560 | 52260 | 19 | 86 | 17 | 83 | 1500 | 10650 | 2850 | 12900 | 1470 | 10635 | 19 | 86 | 10 | 71 | 25500 | 78000 | 43500 | 100500 | 25950 | 84750 | 29 | 67 | 17 | 52 | 6500 | 19000 | 6500 | 25500 | 6350 | 18000 | 13 | 51 | 13 | 38 | 6000 | 12000 | 11000 | 19000 | 5900 | 12200 | 22 | 38 | 12 | 24 | 22500 | 40000 | 25000 | 65000 | 19950 | 35350 | 10 | 26 | 9 | 16 | 2000 | 5000 | 4500 | 8000 | 1875 | 4680 | 9 | 16 | 4 | 10 | 750 | 1250 | 2250 | 4000 | 750 | 1250 | 9 | 16 | 3 | 5 | 200 | 200 | 1400 | 1400 | 200 | 200 | 7 | 7 | 1 | 1 | 296400 | 387900 | 314305 | -91500 | -17905 | 0.76411 | 0.94303
2020 | 31 | 2020-07-27 | 2020-08-02 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 4500 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 600 | 50400 | 8400 | 60000 | 540 | 52800 | 14 | 100 | 1 | 84 | 1350 | 12000 | 2100 | 15000 | 1410 | 12045 | 14 | 100 | 9 | 80 | 22500 | 100500 | 28500 | 129000 | 22650 | 107400 | 19 | 86 | 15 | 67 | 8000 | 27000 | 8000 | 33500 | 7900 | 25900 | 16 | 67 | 16 | 54 | 7000 | 19000 | 6500 | 25500 | 6250 | 18450 | 13 | 51 | 14 | 38 | 30000 | 70000 | 30000 | 95000 | 26500 | 61850 | 12 | 38 | 12 | 28 | 5500 | 10500 | 5000 | 13000 | 5200 | 9880 | 10 | 26 | 11 | 21 | 2500 | 3750 | 2500 | 6500 | 2500 | 3750 | 10 | 26 | 10 | 15 | 400 | 600 | 1800 | 3200 | 400 | 600 | 9 | 16 | 2 | 3 | 378750 | 480700 | 387655 | -101950 | -8905 | 0.78791 | 0.97703
2020 | 32 | 2020-08-03 | 2020-08-09 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 4500 | 105000 | 21000 | 150000 | 4950 | 112350 | 14 | 100 | 3 | 70 | 2500 | 29500 | 9500 | 43000 | 1900 | 27800 | 19 | 86 | 5 | 59 | 5500 | 24500 | 8000 | 33500 | 5250 | 23700 | 16 | 67 | 11 | 49 | 25000 | 95000 | 72500 | 167500 | 21350 | 83200 | 29 | 67 | 10 | 38 | 3500 | 14000 | 6000 | 19000 | 3340 | 13220 | 12 | 38 | 7 | 28 | 1000 | 4750 | 3000 | 9500 | 1000 | 4750 | 12 | 38 | 4 | 19 | 800 | 1400 | 2000 | 5200 | 800 | 1400 | 10 | 26 | 4 | 7 | 421550 | 602700 | 426245 | -181150 | -4695 | 0.69944 | 0.98899
2020 | 33 | 2020-08-10 | 2020-08-16 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 500 | 30000 | 7000 | 50000 | 250 | 28050 | 14 | 100 | 1 | 60 | 1000 | 25500 | 9500 | 43000 | 1150 | 24850 | 19 | 86 | 2 | 51 | 5000 | 100000 | 47500 | 215000 | 4400 | 87600 | 19 | 86 | 2 | 40 | 1000 | 15000 | 14500 | 33500 | 930 | 14150 | 29 | 67 | 2 | 30 | 250 | 5000 | 3250 | 12750 | 250 | 5000 | 13 | 51 | 1 | 20 | 400 | 1800 | 2400 | 7600 | 400 | 1800 | 12 | 38 | 2 | 9 | 429700 | 686850 | 433625 | -257150 | -3925 | 0.62561 | 0.99095
2020 | 34 | 2020-08-17 | 2020-08-23 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 0 | 30000 | 0 | 50000 | 0 | 28050 | 0 | 100 | 0 | 60 | 0 | 25500 | 7000 | 50000 | 0 | 24850 | 14 | 100 | 0 | 51 | 0 | 100000 | 32500 | 247500 | 0 | 87600 | 13 | 99 | 0 | 40 | 0 | 15000 | 9500 | 43000 | 0 | 14150 | 19 | 86 | 0 | 30 | 0 | 5000 | 4000 | 16750 | 0 | 5000 | 16 | 67 | 0 | 20 | 200 | 2000 | 2600 | 10200 | 200 | 2000 | 13 | 51 | 1 | 10 | 429900 | 742450 | 433825 | -312550 | -3925 | 0.57903 | 0.99095
2020 | 35 | 2020-08-24 | 2020-08-30 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 0 | 30000 | 0 | 50000 | 0 | 28050 | 0 | 100 | 0 | 60 | 0 | 25500 | 0 | 50000 | 0 | 24850 | 0 | 100 | 0 | 51 | 0 | 100000 | 2500 | 250000 | 0 | 87600 | 1 | 100 | 0 | 40 | 0 | 15000 | 7000 | 50000 | 0 | 14150 | 14 | 100 | 0 | 30 | 0 | 5000 | 5000 | 21750 | 0 | 5000 | 20 | 87 | 0 | 20 | 0 | 2000 | 3200 | 13400 | 0 | 2000 | 16 | 67 | 0 | 10 | 429900 | 760150 | 433825 | -330250 | -3925 | 0.56555 | 0.99095
2020 | 36 | 2020-08-31 | 2020-09-06 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 0 | 30000 | 0 | 50000 | 0 | 28050 | 0 | 100 | 0 | 60 | 0 | 25500 | 0 | 50000 | 0 | 24850 | 0 | 100 | 0 | 51 | 0 | 100000 | 0 | 250000 | 0 | 87600 | 0 | 100 | 0 | 40 | 0 | 15000 | 0 | 50000 | 0 | 14150 | 0 | 100 | 0 | 30 | 0 | 5000 | 3250 | 25000 | 0 | 5000 | 13 | 100 | 0 | 20 | 0 | 2000 | 3800 | 17200 | 0 | 2000 | 19 | 86 | 0 | 10 | 429900 | 767200 | 433825 | -337300 | -3925 | 0.56035 | 0.99095
2020 | 37 | 2020-09-07 | 2020-09-13 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 0 | 30000 | 0 | 50000 | 0 | 28050 | 0 | 100 | 0 | 60 | 0 | 25500 | 0 | 50000 | 0 | 24850 | 0 | 100 | 0 | 51 | 0 | 100000 | 0 | 250000 | 0 | 87600 | 0 | 100 | 0 | 40 | 0 | 15000 | 0 | 50000 | 0 | 14150 | 0 | 100 | 0 | 30 | 0 | 5000 | 0 | 25000 | 0 | 5000 | 0 | 100 | 0 | 20 | 0 | 2000 | 2800 | 20000 | 0 | 2000 | 14 | 100 | 0 | 10 | 429900 | 770000 | 433825 | -340100 | -3925 | 0.55831 | 0.99095
2020 | 38 | 2020-09-14 | 2020-09-20 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 0 | 30000 | 0 | 50000 | 0 | 28050 | 0 | 100 | 0 | 60 | 0 | 25500 | 0 | 50000 | 0 | 24850 | 0 | 100 | 0 | 51 | 0 | 100000 | 0 | 250000 | 0 | 87600 | 0 | 100 | 0 | 40 | 0 | 15000 | 0 | 50000 | 0 | 14150 | 0 | 100 | 0 | 30 | 0 | 5000 | 0 | 25000 | 0 | 5000 | 0 | 100 | 0 | 20 | 0 | 2000 | 0 | 20000 | 0 | 2000 | 0 | 100 | 0 | 10 | 429900 | 770000 | 433825 | -340100 | -3925 | 0.55831 | 0.99095
2020 | 39 | 2020-09-21 | 2020-09-27 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 0 | 30000 | 0 | 50000 | 0 | 28050 | 0 | 100 | 0 | 60 | 0 | 25500 | 0 | 50000 | 0 | 24850 | 0 | 100 | 0 | 51 | 0 | 100000 | 0 | 250000 | 0 | 87600 | 0 | 100 | 0 | 40 | 0 | 15000 | 0 | 50000 | 0 | 14150 | 0 | 100 | 0 | 30 | 0 | 5000 | 0 | 25000 | 0 | 5000 | 0 | 100 | 0 | 20 | 0 | 2000 | 0 | 20000 | 0 | 2000 | 0 | 100 | 0 | 10 | 429900 | 770000 | 433825 | -340100 | -3925 | 0.55831 | 0.99095
2020 | 40 | 2020-09-28 | 2020-10-04 | 0 | 100 | 0 | 96 | 0 | 45000 | 0 | 50000 | 0 | 43180 | 0 | 100 | 0 | 90 | 0 | 40000 | 0 | 50000 | 0 | 51800 | 0 | 100 | 0 | 86 | 0 | 50400 | 0 | 60000 | 0 | 52800 | 0 | 100 | 0 | 84 | 0 | 12000 | 0 | 15000 | 0 | 12045 | 0 | 100 | 0 | 80 | 0 | 105000 | 0 | 150000 | 0 | 112350 | 0 | 100 | 0 | 70 | 0 | 30000 | 0 | 50000 | 0 | 28050 | 0 | 100 | 0 | 60 | 0 | 25500 | 0 | 50000 | 0 | 24850 | 0 | 100 | 0 | 51 | 0 | 100000 | 0 | 250000 | 0 | 87600 | 0 | 100 | 0 | 40 | 0 | 15000 | 0 | 50000 | 0 | 14150 | 0 | 100 | 0 | 30 | 0 | 5000 | 0 | 25000 | 0 | 5000 | 0 | 100 | 0 | 20 | 0 | 2000 | 0 | 20000 | 0 | 2000 | 0 | 100 | 0 | 10 | 429900 | 770000 | 433825 | -340100 | -3925 | 0.55831 | 0.99095
[120 empty] | At project end, EV = PV |  |  | At project end, SV = 0
Formulas:
StartDate = DATE(Table_SiteMilestoneTrackingSummary[[#This Row],[Year]],1,-2)-WEEKDAY(DATE(Table_SiteMilestoneTrackingSummary[[#This Row],[Year]],1,3))+Table_SiteMilestoneTrackingSummary[[#This Row],[Week]]*7
EndDate = Table_SiteMilestoneTrackingSummary[[#This Row],[StartDate]]+6
Note on E3: Planned Sites in DesignStarted Milestone by week
Note on F3: Planned Sites accumulated for this milestone at week
Note on G3: Actual Sites in DesignStarted Milestone by week
Note on DO3: David Valencia: Accumulated Earned Value (EV) of all the work done that week, regardless of milestone for each site. This way, we can estimate Overall Project Progress, even though a site has yet to be delivered, and is going through each milestone.
Note on DP3: David Valencia: Accumulated planned budget to spend up to each week
Note on DQ3: David Valencia: Accumulated Actual Costs up to the week, for cost performance tracking
Note on DR3: David Valencia: Refer to DOCX for explanation of this variance. Tells how much the project is on time, ahead of schedule, or delayed
Note on DS3: David Valencia: Refer to DOCX for explanation, this variance tells how much the project is under budget, on budget, or above budget
Note on DT3: David Valencia: Schedule Performance Indicator (SPI) refer to DOCX for details
Note on DU3: David Valencia: Cost Performance Indicator (CPI), refer to DOCX for details

## A. Schedule Visuals
Deployment Schedule Visuals
Schedule Baseline | Schedule Actual
Site-accumulates per milestone, by week | Site-accumulates per milestone, by week
SiteDesignStarted: Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteDesignReady Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteReadyforCW Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteReadyforPower Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
TXReady Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteReadyForInstall Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
ReadyForIntegration Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteOnAir Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteAccepted Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteInOperations Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.

## B. Cost & Variance Visuals
Deployment Costs Visuals
Cost Baseline (Planned Value) | Actual Costs (AC) - Accumulated
Accumulated cost, by week.
Cost Variance (CV) in USD
Earned Value (EV) - Accumulated | Difference between Actual Cost (AC) and Earned Value (EV) -> CV = EV - AC
If positive, work is costing less than planned
If negative, work is costing more than planned
Schedule Variance (SV) in USD
Difference between Planned ValuE (PV) and Earned Value (EV) -> CV = EV - PV
If positive, work is being carried out ahead of schedule
If negative, work is being carried out behind schedule

## C. Deployment KPIs
Deployment KPIs
Phase | KPI_Name | KPI_Value | Type | Remark | Column1 | Column2 | Column3
KPIs for Design Tracking
Planning & Pre-Work | TotalNumberOfSites | 100 | - | Total Number of Sites in Tracking Sheets
Planning & Pre-Work | Average Design Time per Site | 2.7111 | Days | Average Design Timr from Design Start to Design Ready
Planning & Pre-Work | LLD Rework Rate | 4% |  | For cases where the LLD has to be revised due to changes in TowerCo, transmission solution, or particular site configuration, this is considered a rework event
KPIs for Deployment Execution Tracking (Global)
Execution | No. sites on-time | 15 |  | Number of Sites that his current Milestones was reached according BL
Execution | %sites on-time | 15% |  | % Sites that his current Milestones was reached according BL
Execution | No. sites behind schedule | 81 |  | Number of Sites that his current Milestones was reached with Delay
Execution | %sites behing schedule | 81% |  | % Sites that his current Milestones was reached with Delay
Execution | No. sites completed | 10 |  | Number of Sites that has reached "Site in Operation" Milestones
Execution | %Overall Progress | 55.83% |  | Calculated through Earned Value Management (EVM)
Execution | (AVG) Time from Site Design Ready to Site Ready for CW | 16.3375 | Days | Time spent in the Site Survey if it has not yet been carried out, plus last details of Site Acquisition.
Execution | (AVG) Time from Ready for CW to Ready for Power-On | 8.3286 | Days | Time spent in civil works (construction) measured in days
Execution | (AVG) Time from Ready for Power-On to TX Ready | 5.95 | Days | Time allocated for the Mains Power company to connect power to the site, or for an energy partner to implement an off-grid power solution.
Execution | (AVG) Time from TX Ready to Site Ready for Installation | 7.2353 | Days | Time estimated for a TX service provider to integrate the selected transport solution (e.g. fiber, xDSL, microwave).
Execution | (AVG) Time from Site Ready for Installation to Ready for Integration | 4.3 | Days | Time allocated for equipment installation and basic commissioning.
Execution | (AVG) Time from Ready for Integration to Site on Air | 4.1 | Days | Time spent in integrating the site to the network.
Execution | (AVG) Time from Site on Air to Site Accepted | 4.65 | Days | Time spent for acceptance (technical report delivery, review and approval) and potential closure of punch-list.
KPIs for Transfer to Operations
Close & Transfer | % Sites Delivered on Time | 10% |  | Percentage of sites that has reached Delivered to Operations Milestone in the Planned Dates or before.
Close & Transfer | % Sites Accepted on Time | 10% |  | Percentage of sites that has reached Site Acceptance Milestone in the Planned Dates or before.
Close & Transfer | % Sites Delivered behind schedule | 90% |  | Percentage of sites that has reached Delivered to Operations Milestone in the Planned after planned date.
Close & Transfer | % Sites Accepted with Delays | 90% |  | Percentage of sites that has reached Site Acceptance Milestone after planned dates.
Close & Transfer | % Accuracy for Schedule Baseline | 18.52% |  | Degree at which the Schedule Baseline (Gantt Chart) was close to actual Schedule.
Close & Transfer | % Accuracy for Cost Baseline | 55.86% |  | Degree at which the Cost Baseline (and Budget) was close to actual costs.
Close & Transfer | (AVG) Time from Site Accepted to Site in Operations | 11.7 |  | Time dedicated to transfer the integrated site to operations, with the associated documentation.
Close & Transfer | (AVG) E2E Time from Site Design Ready to Site in Operations | 61.9 |  | Total time dedicated for the deployment of that single site.
Week-by-week KPIs
| INPUT: WEEK FOR Week-by-week KPIs | 30 |  | USED TO CALCULATE WEEKLY-FOCUSED KPIs
| Budget At Completion (BAC) | 770000 | USD | Planned Value Accumulated at end of Project
| Earned Value At Week 30 | 296400 | USD | Earned Value accumulated at end of Required week
| Planned Value At Week 30 | 387900 | USD | Baseline Value at Required Week
| Actual Costs At Week 30 | 314305 | USD | Actual Cost Calculated as the Required Week
| Schedule Variance (SV) At Week 30 | -91500 | USD | Schedule Variance at the required Week
| Cost Variance (CV) At Week 30 | -17905 | USD | Cost Variance at the required Week
| SPI At Week 30 | 0.76411 |  | Schedule Performance Indicator
| CPI At Week 30 | 0.94303 |  | Cost Performance Indicator
| EAC2 (Estimate At Completion) based on CPI | 816514.3387 |  | Forecast cost at completion according to CPI
| Actual % Complete of Project at Week 30 | 38.49% |  | Actual Percentage of sites Delivered in Required Week
| Planned % Complete of Project at Week 30 | 50.38% |  | Percentage of Total sites Delivered to operations in Required Week
| Sites planned to be delivered by week #30 | 7 |  | Number of sites Delivered to operations in Required Week
| Sites actually delivered by week #30 | 1 |  | By week: Finds how many sites reached the "SiteInOperations" Milestone from the summary counts
| % Sites Delivered by week #30 | 1% |  | Percentage of total sites that reached Handover to operation Milestone at week 40
| Sites In Process by week #30 | 99 |  | Global: Substracts total # of sites, minus the sites delivered
| % Sites in Process | 99% |  | Percentage of total Sites that has not reached teh final Milestone
___ End of Weekly KPIs
GLOBAL KPIs
Execution | Budget At Completion (BAC) | 770000
Execution | Earned Value (EV) so far | 429900
Execution | Sites delivered so far (@SiteInOperations) | 10 |  | Global: Counts how many sites have the "SiteInOperations" Milestone marked
Execution | Sites in process (@other milestones) | 90
Execution | # Sites @SiteDesignNotStarted | 4 |  | SiteDesignNotStarted
Execution | # Sites @SiteDesignStarted | 6 |  | SiteDesignStarted
Execution | # Sites @SiteDesignReady | 4 |  | SiteDesignReady
Execution | # Sites @SiteSurveyCompleted | 2 |  | SiteSurveyCompleted
Execution | # Sites @SiteAcquired | 4 |  | SiteAcquired
Execution | # Sites @SiteReadyForCW | 10 |  | SiteReadyForCW
Execution | # Sites @SiteReadyForPower | 10 |  | SiteReadyForPower
Execution | # Sites @TX_Ready | 9 |  | TX_Ready
Execution | # Sites @SiteReadyForInstallation | 11 |  | SiteReadyForInstallation
Execution | # Sites @SiteReadyForIntegration | 10 |  | SiteReadyForIntegration
Execution | # Sites @SiteOnAir | 10 |  | SiteOnAir
Execution | # Sites @SiteAccepted | 10 |  | SiteAccepted
Execution | # Sites @SiteInOperations | 10 |  | SiteInOperations
Execution | Total Sites In Process (all but SiteInOperations) | 90 |  | All sites that are not SiteInOperations
Execution | Design Started on Time | 2 |  | SiteDesignStarted
Execution | Design Started with Delay | 4 |  | SiteDesignStarted
Execution | Design Ready on Time | 1 |  | SiteDesignReady
Execution | Design Ready with Delay | 3 |  | SiteDesignReady | SiteDesignReady
Execution | Site Surveys on Time | 1 |  | SiteSurveyCompleted
Execution | Sites Surveys with Delay | 1 |  | SiteSurveyCompleted
Execution | Sites Acquired on Time | 1 |  | SiteAcquired
Execution | Sites Acquired with Dealy | 3 |  | SiteAcquired
Execution | Sites Ready for CW on Time | 2 |  | SiteReadyForCW
Execution | Sites Ready for CW with Delay | 8 |  | SiteReadyForCW
Execution | Sites Ready for PWR on Time | 2 |  | SiteReadyForPower
Execution | Sites Ready for PWR with Delay | 8 |  | SiteReadyForPower
Execution | TX Ready on Time | 1 |  | TX_Ready
Execution | TX Ready with Delay | 8 |  | TX_Ready
Execution | Site Ready for Installation on Time | 1 |  | SiteReadyForInstallation
Execution | Site Ready for Installation with Delay | 10 |  | SiteReadyForInstallation
Execution | Site Ready for Integration on Time | 1 |  | SiteReadyForIntegration
Execution | Site Ready for Integration with Delay | 9 |  | SiteReadyForIntegration
Execution | Site on Air on Time | 1 |  | SiteOnAir
Execution | Site on Air with Delay | 9 |  | SiteOnAir
Execution | Site Accepted on Time | 1 |  | SiteAccepted
Execution | Site Accepted with Delay | 9 |  | SiteAccepted
Execution | Sites in Operations on Time | 1 |  | SiteInOperations
Execution | Sites in Operations with Delay | 9 |  | SiteInOperations
| Total Sites with their Milestones reached with delay | 81 |  | milestones with a delay
| Total Sites with their Milestones reached on time | 15 |  | milestones on time
Planning & Pre-Work | AVG LowLevelDesigns per Week (AC) | 13.5556
Planning & Pre-Work | AVG Design Time (hrs) per Site [AC] | 0.33889
BL TO AC KPIs
Planning & Pre-Work | SiteDesignStarted_BL to SiteDesignStarted_AC | 0 | MIN | MIN Delta from SiteDesignStarted_BL to SiteDesignStarted_AC | SiteDesignStarted
Planning & Pre-Work | SiteDesignStarted_BL to SiteDesignStarted_AC | 7 | MAX | MAX Delta from SiteDesignStarted_BL to SiteDesignStarted_AC | SiteDesignStarted | LI01455 | Center
Planning & Pre-Work | SiteDesignStarted_BL to SiteDesignStarted_AC | 1.5417 | AVG | AVG Delta from SiteDesignStarted_BL to SiteDesignStarted_AC | SiteDesignStarted
Execution | Site Design Ready BL to Site Design Ready AC | 0 | MIN | MIN Delta from Site Design Ready BL to Site Design Ready AC | SiteDesignReady
Execution | Site Design Ready BL to Site Design Ready AC | 6 | MAX | MAX Delta from Site Design Ready BL to Site Design Ready AC | SiteDesignReady | #REF! | #REF!
Execution | Site Design Ready BL to Site Design Ready AC | 1.5417 | AVG | AVG Delta from Site Design Ready BL to Site Design Ready AC | SiteDesignReady
Execution | Site Ready for CW_BL to Site Ready for CW_AC | 0 | MIN | MIN Delta from Site Ready for CW_BL to Site Ready for CW_AC | SiteReadyForCW
Execution | Site Ready for CW_BL to Site Ready for CW_AC | 8 | MAX | MAX Delta from Site Ready for CW_BL to Site Ready for CW_AC | SiteReadyForCW | FE00941 | Center
Execution | Site Ready for CW_BL to Site Ready for CW_AC | 3.725 | AVG | AVG Delta from Site Ready for CW_BL to Site Ready for CW_AC | SiteReadyForCW
Execution | Ready for Power On BL to Ready for Power On AC | 0 | MIN | MIN Delta from Ready for Power On BL to Ready for Power On AC | SiteReadyForPower
Execution | Ready for Power On BL to Ready for Power On AC | 8 | MAX | MAX Delta from Ready for Power On BL to Ready for Power On AC | SiteReadyForPower | PI00308 | Center
Execution | Ready for Power On BL to Ready for Power On AC | 4.0714 | AVG | AVG Delta from Ready for Power On BL to Ready for Power On AC | SiteReadyForPower
Execution | Ready for TX BL to Ready for TX AC | 0 | MIN | MIN Delta from Ready for TX BL to Ready for TX AC | TX_Ready
Execution | Ready for TX BL to Ready for TX AC | 17 | MAX | MAX Delta from Ready for TX BL to Ready for TX AC | TX_Ready | AN00262 | South
Execution | Ready for TX BL to Ready for TX AC | 5.0667 | AVG | AVG Delta from Ready for TX BL to Ready for TX AC | TX_Ready
Execution | Ready for Install BL to Ready for Install AC | 0 | MIN | MIN Delta from Ready for Install BL to Ready for Install AC | SiteReadyForInstallation
Execution | Ready for Install BL to Ready for Install AC | 8 | MAX | MAX Delta from Ready for Install BL to Ready for Install AC | SiteReadyForInstallation | ED00640 | Center
Execution | Ready for Install BL to Ready for Install AC | 5.2157 | AVG | AVG Delta from Ready for Install BL to Ready for Install AC | SiteReadyForInstallation
Execution | Ready for Integration BL to Ready for Integration AC | 0 | MIN | MIN Delta from Ready for Integration BL to Ready for Integration AC | SiteReadyForIntegration
Execution | Ready for Integration BL to Ready for Integration AC | 9 | MAX | MAX Delta from Ready for Integration BL to Ready for Integration AC | SiteReadyForIntegration | CA00135 | North
Execution | Ready for Integration BL to Ready for Integration AC | 5.625 | AVG | AVG Delta from Ready for Integration BL to Ready for Integration AC | SiteReadyForIntegration
Execution | SiteOnAir_BL to SiteOnAir_AC | 0 | MIN | MIN Delta from SiteOnAir_BL to SiteOnAir_AC | SiteOnAir | CA00135 | North
Execution | SiteOnAir_BL to SiteOnAir_AC | 9 | MAX | MAX Delta from SiteOnAir_BL to SiteOnAir_AC | SiteOnAir
Execution | SiteOnAir_BL to SiteOnAir_AC | 5.5 | AVG | AVG Delta from SiteOnAir_BL to SiteOnAir_AC | SiteOnAir
Execution | Site Accepted BL to Site Accepted AC | 0 | MIN | MIN Delta from Site Accepted BL to Site Accepted AC | SiteAccepted
Execution | Site Accepted BL to Site Accepted AC | 10 | MAX | MAX Delta from Site Accepted BL to Site Accepted AC | SiteAccepted | ED00640 | Center
Execution | Site Accepted BL to Site Accepted AC | 5.9 | AVG | AVG Delta from Site Accepted BL to Site Accepted AC | SiteAccepted
Close & Transfer | Site In Operations BL to Site In Operations AC | 0 | MIN | MIN Delta from Site In Operations BL to Site In Operations AC | SiteInOperations
Close & Transfer | Site In Operations BL to Site In Operations AC | 18 | MAX | MAX Delta from Site In Operations BL to Site In Operations AC | SiteInOperations | CA00257 | Center
Close & Transfer | Site In Operations BL to Site In Operations AC | 9.6 | AVG | AVG Delta from Site In Operations BL to Site In Operations AC | SiteInOperations
Phase to Phase KPIs
Planning & Pre-Work | SiteDesignStarted_BL to SiteDesignReady_BL | 2 | MIN | MIN Time from SiteDesignStarted_BL to SiteDesignReady_BL | SiteDesignStarted
Planning & Pre-Work | SiteDesignStarted_BL to SiteDesignReady_BL | 2 | MAX | MAX Time from SiteDesignStarted_BL to SiteDesignReady_BL | SiteDesignStarted
Planning & Pre-Work | SiteDesignStarted_BL to SiteDesignReady_BL | 2 | AVG | AVG Time from SiteDesignStarted_BL to SiteDesignReady_BL | SiteDesignStarted
Planning & Pre-Work | SiteDesignStarted_AC to SiteDesignReady_AC | -4 | MIN | MIN Time from SiteDesignStarted_AC to SiteDesignReady_AC | SiteDesignStarted
Planning & Pre-Work | SiteDesignStarted_AC to SiteDesignReady_AC | 6 | MAX | MAX Time from SiteDesignStarted_AC to SiteDesignReady_AC | SiteDesignStarted
Planning & Pre-Work | SiteDesignStarted_AC to SiteDesignReady_AC | 1.5417 | AVG | AVG Time from SiteDesignStarted_AC to SiteDesignReady_AC | SiteDesignStarted
Execution | Site Design Ready to Site Ready for CW (BL) | 15 | MIN | MIN Time from Site Design Ready to Site Ready for CW (BL) | SiteDesignReady
Execution | Site Design Ready to Site Ready for CW (BL) | 15 | MAX | MAX Time from Site Design Ready to Site Ready for CW (BL) | SiteDesignReady
Execution | Site Design Ready to Site Ready for CW (BL) | 15 | AVG | AVG Time from Site Design Ready to Site Ready for CW (BL) | SiteDesignReady
Execution | Site Design Ready to Site Ready for CW (AC) | 14 | MIN | MIN Time from Site Design Ready to Site Ready for CW (AC) | SiteDesignReady
Execution | Site Design Ready to Site Ready for CW (AC) | 18 | MAX | MAX Time from Site Design Ready to Site Ready for CW (AC) | SiteDesignReady
Execution | Site Design Ready to Site Ready for CW (AC) | 16.3375 | AVG | AVG Time from Site Design Ready to Site Ready for CW (AC) | SiteDesignReady
Execution | Ready for CW to Ready to Power-On (BL) | 8 | MIN | MIN Time from Ready for CW to Ready to Power-On (BL) | SiteReadyForCW
Execution | Ready for CW to Ready to Power-On (BL) | 8 | MAX | MAX Time from Ready for CW to Ready to Power-On (BL) | SiteReadyForCW
Execution | Ready for CW to Ready to Power-On (BL) | 8 | AVG | AVG Time from Ready for CW to Ready to Power-On (BL) | SiteReadyForCW
Execution | Ready for CW to Ready to Power-On (AC) | 3 | MIN | MIN Time from Ready for CW to Ready to Power-On (AC) | SiteReadyForCW
Execution | Ready for CW to Ready to Power-On (AC) | 9 | MAX | MAX Time from Ready for CW to Ready to Power-On (AC) | SiteReadyForCW
Execution | Ready for CW to Ready to Power-On (AC) | 8.3286 | AVG | AVG Time from Ready for CW to Ready to Power-On (AC) | SiteReadyForCW
Execution | Ready for Power-On to TX Ready (BL) | 5 | MIN | MIN Time from Ready for Power-On to TX Ready (BL) | SiteReadyForPower
Execution | Ready for Power-On to TX Ready (BL) | 5 | MAX | MAX Time from Ready for Power-On to TX Ready (BL) | SiteReadyForPower
Execution | Ready for Power-On to TX Ready (BL) | 5 | AVG | AVG Time from Ready for Power-On to TX Ready (BL) | SiteReadyForPower
Execution | Ready for Power-On to TX Ready (AC) | 5 | MIN | MIN Time from Ready for Power-On to TX Ready (AC) | SiteReadyForPower
Execution | Ready for Power-On to TX Ready (AC) | 21 | MAX | MAX Time from Ready for Power-On to TX Ready (AC) | SiteReadyForPower
Execution | Ready for Power-On to TX Ready (AC) | 5.95 | AVG | AVG Time from Ready for Power-On to TX Ready (AC) | SiteReadyForPower
Execution | TX Ready to Site Ready for Installation (BL) | 7 | MIN | MIN Time from TX Ready to Site Ready for Installation (BL) | TX_Ready
Execution | TX Ready to Site Ready for Installation (BL) | 7 | MAX | MAX Time from TX Ready to Site Ready for Installation (BL) | TX_Ready
Execution | TX Ready to Site Ready for Installation (BL) | 7 | AVG | AVG Time from TX Ready to Site Ready for Installation (BL) | TX_Ready
Execution | TX Ready to Site Ready for Installation (AC) | 0 | MIN | MIN Time from TX Ready to Site Ready for Installation (AC) | TX_Ready
Execution | TX Ready to Site Ready for Installation (AC) | 8 | MAX | MAX Time from TX Ready to Site Ready for Installation (AC) | TX_Ready
Execution | TX Ready to Site Ready for Installation (AC) | 7.2353 | AVG | AVG Time from TX Ready to Site Ready for Installation (AC) | TX_Ready
Execution | Site Ready for Installation to Ready for Integration (BL) | 4 | MIN | MIN Time from Site Ready for Installation to Ready for Integration (BL) | SiteReadyForInstallation
Execution | Site Ready for Installation to Ready for Integration (BL) | 4 | MAX | MAX Time from Site Ready for Installation to Ready for Integration (BL) | SiteReadyForInstallation
Execution | Site Ready for Installation to Ready for Integration (BL) | 4 | AVG | AVG Time from Site Ready for Installation to Ready for Integration (BL) | SiteReadyForInstallation
Execution | Site Ready for Installation to Ready for Integration (AC) | 0 | MIN | MIN Time from Site Ready for Installation to Ready for Integration (AC) | SiteReadyForInstallation
Execution | Site Ready for Installation to Ready for Integration (AC) | 5 | MAX | MAX Time from Site Ready for Installation to Ready for Integration (AC) | SiteReadyForInstallation
Execution | Site Ready for Installation to Ready for Integration (AC) | 4.3 | AVG | AVG Time from Site Ready for Installation to Ready for Integration (AC) | SiteReadyForInstallation
Execution | Ready for Integration to Site on Air (BL) | 4 | MIN | MIN Time from Ready for Integration to Site on Air (BL) | SiteReadyForIntegration
Execution | Ready for Integration to Site on Air (BL) | 4 | MAX | MAX Time from Ready for Integration to Site on Air (BL) | SiteReadyForIntegration
Execution | Ready for Integration to Site on Air (BL) | 4 | AVG | AVG Time from Ready for Integration to Site on Air (BL) | SiteReadyForIntegration
Execution | Ready for Integration to Site on Air (AC) | 0 | MIN | MIN Time from Ready for Integration to Site on Air (AC) | SiteReadyForIntegration
Execution | Ready for Integration to Site on Air (AC) | 5 | MAX | MAX Time from Ready for Integration to Site on Air (AC) | SiteReadyForIntegration
Execution | Ready for Integration to Site on Air (AC) | 4.1 | AVG | AVG Time from Ready for Integration to Site on Air (AC) | SiteReadyForIntegration
Execution | Site on Air to Site Accepted (BL) | 4 | MIN | MIN Time from Site on Air to Site Accepted (BL) | SiteOnAir
Execution | Site on Air to Site Accepted (BL) | 4 | MAX | MAX Time from Site on Air to Site Accepted (BL) | SiteOnAir
Execution | Site on Air to Site Accepted (BL) | 4 | AVG | AVG Time from Site on Air to Site Accepted (BL) | SiteOnAir
Execution | Site on Air to Site Accepted (AC) | 1 | MIN | MIN Time from Site on Air to Site Accepted (AC) | SiteOnAir
Execution | Site on Air to Site Accepted (AC) | 12 | MAX | MAX Time from Site on Air to Site Accepted (AC) | SiteOnAir
Execution | Site on Air to Site Accepted (AC) | 4.65 | AVG | AVG Time from Site on Air to Site Accepted (AC) | SiteOnAir
Close & Transfer | Site Accepted to Site in Operations (BL) | 8 | MIN | MIN Time from Site Accepted to Site in Operations (BL) | SiteAccepted
Close & Transfer | Site Accepted to Site in Operations (BL) | 8 | MAX | MAX Time from Site Accepted to Site in Operations (BL) | SiteAccepted
Close & Transfer | Site Accepted to Site in Operations (BL) | 8 | AVG | AVG Time from Site Accepted to Site in Operations (BL) | SiteAccepted
Close & Transfer | Site Accepted to Site in Operations (AC) | 8 | MIN | MIN Time from Site Accepted to Site in Operations (AC) | SiteAccepted
Close & Transfer | Site Accepted to Site in Operations (AC) | 18 | MAX | MAX Time from Site Accepted to Site in Operations (AC) | SiteAccepted
Close & Transfer | Site Accepted to Site in Operations (AC) | 11.7 | AVG | AVG Time from Site Accepted to Site in Operations (AC) | SiteAccepted
Close & Transfer | Site Design Ready BL to Site in Operations BL | 55 | MIN | MIN Time from Site Design Ready BL to Site in Operations BL | SiteInOperations
Close & Transfer | Site Design Ready BL to Site in Operations BL | 55 | MAX | MAX Time from Site Design Ready BL to Site in Operations BL | SiteInOperations
Close & Transfer | Site Design Ready BL to Site in Operations BL | 55 | AVG | AVG Time from Site Design Ready BL to Site in Operations BL | SiteInOperations
Close & Transfer | Site Design Ready AC to Site in Operations AC | 55 | MIN | MIN Time from Site Design Ready AC to Site in Operations AC | SiteInOperations
Close & Transfer | Site Design Ready AC to Site in Operations AC | 71 | MAX | MAX Time from Site Design Ready AC to Site in Operations AC | SiteInOperations
Close & Transfer | Site Design Ready AC to Site in Operations AC | 61.9 | AVG | AVG Time from Site Design Ready AC to Site in Operations AC | SiteInOperations
Close & Transfer | E2E BL to E2E AC | 0 | MIN | MIN Delta between site E2E BL to E2E AC
Close & Transfer | E2E BL to E2E AC | 16 | MAX | MAX Delta between site E2E BL to E2E AC
Close & Transfer | E2E BL to E2E AC | 6.9 | AVG | AVG Delta between site E2E BL to E2E AC
Note on C3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Identify KPIs that are not mentioned in the document. Decide if we keep or delete those which are not mentioned

## D. Dashboard
Deployment Dashboard |  | Week | 30
Global Statistics |  |  |  | Sites Delivered | Sites Delayed vs On-Time
Total Sites | 100
Sites Delivered (SiteInOperations) | 10
Sites In Process (other milestones) | 90
% Progress Planned at week 30 | 50.38%
% Progress Achieved at week 30 | 55.83%
Value of Work Completed (EV) at Week 30 | 429900
Actual Costs (AC) at Week 30 | 296400
Planned Value (PV) at Week 30 | 387900 |  |  |  |  | (Pending to Build Chart from KPIs)
Total Planned Value (BAC) | 770000
Schedule Variance (SV) at Week 30 | -91500 | -91500
Cost Variance (CV) at Week 30 | -17905 | -17905
SPI | 0.76411 | 0.76411
CPI | 0.94303 | 0.94303
Estimate At Completion, based on CPI | 816514.3387
TOP OFFENDERS Schedule
Rank | SiteId | CurMilestone | Delay Vs Baseline | Region
1 | CA00257 | SiteInOperations | 18 | Center
2 | AN00262 | TX_Ready | 17 | South
3 | CA00135 | SiteReadyForIntegration | 9 | North
4 | CA00135 | SiteReadyForIntegration | 9 | North
5 | FE00941 | SiteReadyForCW | 8 | Center

## E. Site_Milestones_List
SiteMilestoneID | SiteMilestoneName
0 | SiteDesignNotStarted
1 | SiteDesignStarted
2 | SiteDesignReady
3 | SiteSurveyCompleted
4 | SiteAcquired
5 | SiteReadyForCW
6 | SiteReadyForPower
7 | TX_Ready
8 | SiteReadyForInstallation
9 | SiteReadyForIntegration
10 | SiteOnAir
11 | SiteAccepted
12 | SiteInOperations