## Cover
Fiber Construction Gantt Diagram
<Release Date>

## Aerial
GANTT CHART FOR FIBER CONSTRUCTION TEMPLATE
WBS |  | TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE
WBS
1 | Permit Acquisition
1.1 |  | Produce Documentation for permit requests | 2020-01-05 | 2020-01-15 | 0 | 10 | Vendor#1 | 100%
1.2 |  | Right of Ways and Property Permits | 2020-01-15 | 2020-02-14 | 10 | 30 | Vendor#1 | 60%
1.3 |  | Administrative Construction Licensing | 2020-02-14 | 2020-03-15 | 40 | 30 | Vendor#1 | 40%
2 | Path Survey & Terrain Analysis
2.1 |  | Technical Survey (preparation and generation of report) | 2020-03-15 | 2020-03-25 | 70 | 10 | Vendor#1 | 100%
2.2 |  | Engineering and Structural Evaluation | 2020-03-25 | 2020-04-04 | 80 | 10 | Vendor#1 | 80%
3 | Construction
3.1 |  | Soil excavation and ground cleaning | 2020-04-04 | 2020-04-14 | 90 | 10 | Vendor#1 | 100%
3.2 |  | Pole storage and inspection | 2020-04-14 | 2020-04-19 | 100 | 5 | Vendor#1 | 60%
3.3 |  | Pole hole digging | 2020-04-19 | 2020-04-24 | 105 | 5 | Vendor#1 | 40%
3.4 |  | Pole planting | 2020-04-24 | 2020-04-29 | 110 | 5 | Vendor#1 | 20%
3.5 |  | Concrete Casting | 2020-04-29 | 2020-05-09 | 115 | 10 | Vendor#1 | 100%
3.6 |  | Pole stays | 2020-05-09 | 2020-05-14 | 125 | 5 | Vendor#1 | 100%
3.7 |  | Cable pole supports | 2020-05-14 | 2020-05-19 | 130 | 5 | Vendor#1 | 100%
3.8 |  | Pole labeling | 2020-05-19 | 2020-05-23 | 135 | 4 | Vendor#1 | 100%
4 | Fiber Cable Installation and Commissioning
4.1 |  | Fiber drum storage and inspection | 2020-05-23 | 2020-05-25 | 139 | 2 | Vendor#1 | 100%
4.2 |  | Installation and verification of ADSS terminations and supports | 2020-05-25 | 2020-05-30 | 141 | 5 | Vendor#1 | 80%
4.3 |  | ADSS leveling | 2020-05-30 | 2020-06-09 | 146 | 10 | Vendor#1 | 60%
4.4 |  | Cable tensioning | 2020-06-09 | 2020-06-19 | 156 | 10 |  | 100%
4.5 |  | Commissioning | 2020-06-19 | 2020-06-24 | 166 | 5 | Vendor#1 | 100%
5 | In-building access
5.1 |  | In building access point construction | 2020-06-24 | 2020-06-29 | 171 | 5 |  | 100%
5.2 |  | In building cable routing | 2020-06-29 | 2020-07-01 | 176 | 2 |  | 100%
5.3 |  | ODF termination | 2020-07-01 | 2020-07-02 | 178 | 1 | Vendor#1 | 100%
Formulas:
END DATE = [START DATE]+[DURATION* (WORK DAYS)]
START DATE = [END DATE, row above]

## Underground
GANTT CHART FOR FIBER CONSTRUCTION TEMPLATE
WBS |  | TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE
WBS
1 | Permit Acquisition
1.1 |  | Produce Documentation for permit requests | 2020-01-05 | 2020-01-15 | 0 | 10 | Vendor#1 | 100%
1.2 |  | Right of Ways and Property Permits | 2020-01-15 | 2020-02-14 | 10 | 30 | Vendor#1 | 60%
1.3 |  | Administrative Construction Licensing | 2020-02-14 | 2020-03-15 | 40 | 30 | Vendor#1 | 40%
2 | Path Survey & Terrain Analysis
2.1 |  | Technical Survey (preparation and generation of report) | 2020-03-15 | 2020-03-25 | 70 | 10 | Vendor#1 | 100%
2.2 |  | Engineering and Structural Evaluation | 2020-03-25 | 2020-04-04 | 80 | 10 | Vendor#1 | 80%
3 | Construction
3.1 |  | Soil excavation and ground cleaning | 2020-04-04 | 2020-04-14 | 90 | 10 | Vendor#1 | 100%
3.2 |  | Duct storage and inspection | 2020-04-14 | 2020-04-19 | 100 | 5 | Vendor#1 | 60%
3.3 |  | Trench digging | 2020-04-19 | 2020-05-09 | 105 | 20 | Vendor#1 | 40%
3.4 |  | Duct casting in concrete | 2020-05-09 | 2020-06-03 | 125 | 25 | Vendor#1 | 20%
3.5 |  | Trench backfilling | 2020-06-03 | 2020-06-18 | 150 | 15 | Vendor#1 | 100%
3.6 |  | Manhole installation | 2020-06-18 | 2020-06-28 | 165 | 10 | Vendor#1 | 100%
3.7 |  | Pavement restoration | 2020-06-28 | 2020-07-13 | 175 | 15 | Vendor#1 | 100%
4 | Fiber Cable Installation and Commissioning
4.1 |  | Fiber drum storage and inspection | 2020-07-13 | 2020-07-15 | 190 | 2 | Vendor#1 | 100%
4.2 |  | Cable insertion in ducts | 2020-07-15 | 2020-07-20 | 192 | 5 | Vendor#1 | 80%
4.3 |  | Fiber Splicing | 2020-07-20 | 2020-07-26 | 197 | 6 | Vendor#1 | 100%
4.4 |  | Commissioning | 2020-07-26 | 2020-07-31 | 203 | 5 | Vendor#1 | 100%
5 | In-building access
5.1 |  | In building access point construction | 2020-07-31 | 2020-08-05 | 208 | 5 | Vendor#1 | 100%
5.2 |  | In building cable routing | 2020-08-05 | 2020-08-07 | 213 | 2 | Vendor#1 | 100%
5.3 |  | ODF termination | 2020-08-07 | 2020-08-08 | 215 | 1 | Vendor#1 | 100%
Formulas:
END DATE = [START DATE]+[DURATION* (WORK DAYS)]
START DATE = [END DATE, row above]