## Cover
Fiber Construction Project Tracking
<Release Date>

## 1. Instructions
Fiber Construction Tracking template
Instructions:
1. Selected milestones are indicated in "Milestones" sheet (The NaaS Operator can adjust "Expected Duration Estimate" to automatically update Baseline Values in the "Fiber Tracking Sheet")
2. Use "Fiber Tracking Sheet" to track dates for Fiber Construction Milestones (only Actual Dates, and the initial baseline date need to be updated)
3. "Summary Tracking Sheet" and "Tracking Graphs" sheet are automatically completed with data from "Fiber Tracking" sheet
Notes:
BL = Baseline
AC = Actual
Explanation of tracking milestones | Times are per span
t1_TechnicalPathSurveyBL | Time to perform detailed path survey
t2_PathEngineeringDocumentBL | Generation of construction engineering document, describing technical solution and implementation plan
t3_PathConstructionWorkOrderBL | Approval of engineering plan and GO confirmation received (materials available, construction ready to commence)
t4_CivilWorksBL | Time to complete civil works (pole planting, underground burial, trenching)
t5_MechanicalWorksBL | Time to complete additional mechanical works (installation of pole stays and supports, laying of ducts, trench compacting and backfilling)
t6_CablingWorksBL | Installation of cables (via messenger wires, ADSS aerial cables, blowing into ducts, etc)
t7_ConstructionAcceptanceBL | Infrastrucuture has passed self-acceptance
t8_ReadyForOperationBL | Optical fiber post-install testing has passed self-acceptance
t9_PathInOperationsBL | All fiber fusions confirmed. Cable is connecting network endpoints, and ready for commercial operation
E2E_Path_xx | End to end time lag
E2E_Site_deltaT | Time difference with respect to baseline
Remark | Notes

## 2. Milestones
FIBER CONSTRUCTION MILESTONES
Project Title: Site Construction Project
Date Prepared: May 27th, 2020
ID | Expected Duration Estimate
t1_TechnicalPathSurveyBL | 4
t2_PathEngineeringDocumentBL | 14
t3_PathConstructionWorkOrderBL | 2
t4_CivilWorksBL | 20
t5_MechanicalWorksBL | 10
t6_CablingWorksBL | 9
t7_ConstructionAcceptanceBL | 2
t8_ReadyForOperationBL | 5
t9_PathInOperationsBL | 10

## 3. Fiber Tracking
Construction Tracking per site
Path Span | TechnicalPathSurvey_BL | TechnicalPathSurvey_AC | PathEngineeringDocument_BL | PathEngineeringDocument_AC | PathConstructionWorkOrder_BL | PathConstructionWorkOrder_AC | CivilWorks_BL | CivilWorks_AC | MechanicalWorks_BL | MechanicalWorks_AC | CablingWorks_BL | CablingWorks_AC | ConstructionAcceptance_BL | ConstructionAcceptance_AC | ReadyForOperation_BL | ReadyForOperation_AC | PathInOperation_BL | PathInOperation_AC | E2E_Path_BL | E2E_Path_AC | E2E_Site_deltaT | Remark
Span1 | 2020-06-01 | 2020-06-05 | 2020-06-19 | 2020-06-14 04:00 | 2020-06-21 | 2020-06-24 16:00 | 2020-07-11 | 2020-06-30 16:00 | 2020-07-21 | 2020-07-06 20:00 | 2020-07-30 | 2020-07-09 20:00 | 2020-08-01 | 2020-07-13 08:00 | 2020-08-06 | 2020-07-17 20:00 | 2020-08-16 | 2020-07-20 20:00 | 76 | 45.8333 | -30.1667
Span2 | 2020-06-01 | 2020-06-02 | 2020-06-19 | 2020-06-16 04:00 | 2020-06-21 | 2020-06-21 16:00 | 2020-07-11 | 2020-06-25 16:00 | 2020-07-21 | 2020-07-06 20:00 | 2020-07-30 | 2020-07-06 20:00 | 2020-08-01 | 2020-07-10 08:00 | 2020-08-06 | 2020-07-15 20:00 | 2020-08-16 | 2020-07-25 20:00 | 76 | 53.8333 | -22.1667
Span3 | 2020-06-01 | 2020-06-04 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-25 16:00 | 2020-07-11 | 2020-06-28 16:00 | 2020-07-21 | 2020-07-06 20:00 | 2020-07-30 | 2020-07-07 20:00 | 2020-08-01 | 2020-07-12 08:00 | 2020-08-06 | 2020-07-16 20:00 | 2020-08-16 | 2020-07-23 20:00 | 76 | 49.8333 | -26.1667
Span4 | 2020-06-01 | 2020-06-04 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-22 16:00 | 2020-07-11 | 2020-06-26 16:00 | 2020-07-21 | 2020-07-05 20:00 | 2020-07-30 | 2020-07-06 20:00 | 2020-08-01 | 2020-07-14 08:00 | 2020-08-06 | 2020-07-12 20:00 | 2020-08-16 | 2020-07-23 20:00 | 76 | 49.8333 | -26.1667
Span5 | 2020-06-01 | 2020-06-02 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-22 16:00 | 2020-07-11 | 2020-06-28 16:00 | 2020-07-21 | 2020-07-04 20:00 | 2020-07-30 | 2020-07-10 20:00 | 2020-08-01 | 2020-07-10 08:00 | 2020-08-06 | 2020-07-14 20:00 | 2020-08-16 | 2020-07-20 20:00 | 76 | 48.8333 | -27.1667
Span6 | 2020-06-01 | 2020-06-03 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-24 16:00 | 2020-07-11 | 2020-06-27 16:00 | 2020-07-21 | 2020-07-02 20:00 | 2020-07-30 | 2020-07-10 20:00 | 2020-08-01 | 2020-07-13 08:00 | 2020-08-06 | 2020-07-13 20:00 | 2020-08-16 | 2020-07-24 20:00 | 76 | 51.8333 | -24.1667
Span7 | 2020-06-01 | 2020-06-04 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-22 16:00 | 2020-07-11 | 2020-06-28 16:00 | 2020-07-21 | 2020-07-05 20:00 | 2020-07-30 | 2020-07-10 20:00 | 2020-08-01 | 2020-07-12 08:00 | 2020-08-06 | 2020-07-14 20:00 | 2020-08-16 | 2020-07-24 20:00 | 76 | 50.8333 | -25.1667
Span8 | 2020-06-08 | 2020-06-11 | 2020-06-26 | 2020-06-22 04:00 | 2020-06-28 | 2020-06-28 16:00 | 2020-07-18 | 2020-07-05 16:00 | 2020-07-28 | 2020-07-09 20:00 | 2020-08-06 | 2020-07-18 20:00 | 2020-08-08 | 2020-07-21 08:00 | 2020-08-13 | 2020-07-24 20:00 | 2020-08-23 | 2020-07-30 20:00 | 76 | 49.8333 | -26.1667
Span9 | 2020-06-08 | 2020-06-12 | 2020-06-26 | 2020-06-22 04:00 | 2020-06-28 | 2020-06-29 16:00 | 2020-07-18 | 2020-07-03 16:00 | 2020-07-28 | 2020-07-08 20:00 | 2020-08-06 | 2020-07-15 20:00 | 2020-08-08 | 2020-07-20 08:00 | 2020-08-13 | 2020-07-24 20:00 | 2020-08-23 | 2020-07-29 20:00 | 76 | 47.8333 | -28.1667
Span10 | 2020-06-08 | 2020-06-10 | 2020-06-26 | 2020-06-24 04:00 | 2020-06-28 | 2020-07-02 16:00 | 2020-07-18 | 2020-07-03 16:00 | 2020-07-28 | 2020-07-12 20:00 | 2020-08-06 | 2020-07-18 20:00 | 2020-08-08 | 2020-07-18 08:00 | 2020-08-13 | 2020-07-20 20:00 | 2020-08-23 | 2020-07-31 20:00 | 76 | 51.8333 | -24.1667
Span11 | 2020-06-08 | 2020-06-13 | 2020-06-26 | 2020-06-22 04:00 | 2020-06-28 | 2020-06-29 16:00 | 2020-07-18 | 2020-07-06 16:00 | 2020-07-28 | 2020-07-13 20:00 | 2020-08-06 | 2020-07-13 20:00 | 2020-08-08 | 2020-07-17 08:00 | 2020-08-13 | 2020-07-23 20:00 | 2020-08-23 | 2020-08-01 20:00 | 76 | 49.8333 | -26.1667
Span12 | 2020-06-08 | 2020-06-11 | 2020-06-26 | 2020-06-25 04:00 | 2020-06-28 | 2020-06-28 16:00 | 2020-07-18 | 2020-07-03 16:00 | 2020-07-28 | 2020-07-10 20:00 | 2020-08-06 | 2020-07-12 20:00 | 2020-08-08 | 2020-07-17 08:00 | 2020-08-13 | 2020-07-19 20:00 | 2020-08-23 | 2020-07-28 20:00 | 76 | 47.8333 | -28.1667
Span13 | 2020-06-08 | 2020-06-09 | 2020-06-26 | 2020-06-21 04:00 | 2020-06-28 | 2020-06-28 16:00 | 2020-07-18 | 2020-07-06 16:00 | 2020-07-28 | 2020-07-11 20:00 | 2020-08-06 | 2020-07-19 20:00 | 2020-08-08 | 2020-07-17 08:00 | 2020-08-13 | 2020-07-23 20:00 | 2020-08-23 | 2020-07-27 20:00 | 76 | 48.8333 | -27.1667
Span14 | 2020-06-08 | 2020-06-09 | 2020-06-26 | 2020-06-24 04:00 | 2020-06-28 | 2020-07-02 16:00 | 2020-07-18 | 2020-07-04 16:00 | 2020-07-28 | 2020-07-09 20:00 | 2020-08-06 | 2020-07-15 20:00 | 2020-08-08 | 2020-07-17 08:00 | 2020-08-13 | 2020-07-20 20:00 | 2020-08-23 | 2020-08-01 20:00 | 76 | 53.8333 | -22.1667
Span15 | 2020-06-08 | 2020-06-12 | 2020-06-26 | 2020-06-21 04:00 | 2020-06-28 | 2020-06-27 16:00 | 2020-07-18 | 2020-07-06 16:00 | 2020-07-28 | 2020-07-08 20:00 | 2020-08-06 | 2020-07-13 20:00 | 2020-08-08 | 2020-07-16 08:00 | 2020-08-13 | 2020-07-24 20:00 | 2020-08-23 | 2020-07-28 20:00 | 76 | 46.8333 | -29.1667
Span16 | 2020-06-08 | 2020-06-11 | 2020-06-26 | 2020-06-24 04:00 | 2020-06-28 | 2020-07-02 16:00 | 2020-07-18 | 2020-07-02 16:00 | 2020-07-28 | 2020-07-11 20:00 | 2020-08-06 | 2020-07-13 20:00 | 2020-08-08 | 2020-07-19 08:00 | 2020-08-13 | 2020-07-22 20:00 | 2020-08-23 | 2020-07-30 20:00 | 76 | 49.8333 | -26.1667
Span17 | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-06-30 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-11 16:00 | 2020-08-04 | 2020-07-19 20:00 | 2020-08-13 | 2020-07-23 20:00 | 2020-08-15 | 2020-07-26 08:00 | 2020-08-20 | 2020-07-27 20:00 | 2020-08-30 | 2020-08-06 20:00 | 76 | 51.8333 | -24.1667
Span18 | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-06 16:00 | 2020-07-25 | 2020-07-13 16:00 | 2020-08-04 | 2020-07-19 20:00 | 2020-08-13 | 2020-07-26 20:00 | 2020-08-15 | 2020-07-25 08:00 | 2020-08-20 | 2020-07-30 20:00 | 2020-08-30 | 2020-08-08 20:00 | 76 | 53.8333 | -22.1667
Span19 | 2020-06-15 | 2020-06-18 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-12 16:00 | 2020-08-04 | 2020-07-19 20:00 | 2020-08-13 | 2020-07-23 20:00 | 2020-08-15 | 2020-07-27 08:00 | 2020-08-20 | 2020-07-30 20:00 | 2020-08-30 | 2020-08-07 20:00 | 76 | 50.8333 | -25.1667
Span20 | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-12 16:00 | 2020-08-04 | 2020-07-19 20:00 | 2020-08-13 | 2020-07-26 20:00 | 2020-08-15 | 2020-07-25 08:00 | 2020-08-20 | 2020-07-29 20:00 | 2020-08-30 | 2020-08-04 20:00 | 76 | 49.8333 | -26.1667
Span21 | 2020-06-15 | 2020-06-15 | 2020-07-03 | 2020-06-30 04:00 | 2020-07-05 | 2020-07-09 16:00 | 2020-07-25 | 2020-07-10 16:00 | 2020-08-04 | 2020-07-18 20:00 | 2020-08-13 | 2020-07-20 20:00 | 2020-08-15 | 2020-07-25 08:00 | 2020-08-20 | 2020-07-29 20:00 | 2020-08-30 | 2020-08-07 20:00 | 76 | 53.8333 | -22.1667
Span22 | 2020-06-15 | 2020-06-19 | 2020-07-03 | 2020-06-27 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-14 16:00 | 2020-08-04 | 2020-07-16 20:00 | 2020-08-13 | 2020-07-22 20:00 | 2020-08-15 | 2020-07-27 08:00 | 2020-08-20 | 2020-07-26 20:00 | 2020-08-30 | 2020-08-05 20:00 | 76 | 47.8333 | -28.1667
Span23 | 2020-06-15 | 2020-06-19 | 2020-07-03 | 2020-06-29 04:00 | 2020-07-05 | 2020-07-07 16:00 | 2020-07-25 | 2020-07-14 16:00 | 2020-08-04 | 2020-07-18 20:00 | 2020-08-13 | 2020-07-22 20:00 | 2020-08-15 | 2020-07-28 08:00 | 2020-08-20 | 2020-07-26 20:00 | 2020-08-30 | 2020-08-05 20:00 | 76 | 47.8333 | -28.1667
Span24 | 2020-06-15 | 2020-06-17 | 2020-07-03 | 2020-06-28 04:00 | 2020-07-05 | 2020-07-07 16:00 | 2020-07-25 | 2020-07-12 16:00 | 2020-08-04 | 2020-07-17 20:00 | 2020-08-13 | 2020-07-20 20:00 | 2020-08-15 | 2020-07-28 08:00 | 2020-08-20 | 2020-07-28 20:00 | 2020-08-30 | 2020-08-07 20:00 | 76 | 51.8333 | -24.1667
Span25 | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-06-30 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-13 16:00 | 2020-08-04 | 2020-07-16 20:00 | 2020-08-13 | 2020-07-21 20:00 | 2020-08-15 | 2020-07-27 08:00 | 2020-08-20 | 2020-07-27 20:00 | 2020-08-30 | 2020-08-04 20:00 | 76 | 49.8333 | -26.1667
Span26 | 2020-06-15 | 2020-06-18 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-08 16:00 | 2020-07-25 | 2020-07-10 16:00 | 2020-08-04 | 2020-07-15 20:00 | 2020-08-13 | 2020-07-24 20:00 | 2020-08-15 | 2020-07-27 08:00 | 2020-08-20 | 2020-07-27 20:00 | 2020-08-30 | 2020-08-03 20:00 | 76 | 46.8333 | -29.1667
Span27 | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-07 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-10 | 2020-07-25 20:00 | 2020-08-19 | 2020-08-01 20:00 | 2020-08-21 | 2020-08-01 08:00 | 2020-08-26 | 2020-08-04 20:00 | 2020-09-05 | 2020-08-10 20:00 | 76 | 47.8333 | -28.1667
Span28 | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-10 16:00 | 2020-07-31 | 2020-07-15 16:00 | 2020-08-10 | 2020-07-24 20:00 | 2020-08-19 | 2020-07-31 20:00 | 2020-08-21 | 2020-08-01 08:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-09-05 | 2020-08-12 20:00 | 76 | 49.8333 | -26.1667
Span29 | 2020-06-21 | 2020-06-23 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-12 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-10 | 2020-07-24 20:00 | 2020-08-19 | 2020-07-27 20:00 | 2020-08-21 | 2020-07-31 08:00 | 2020-08-26 | 2020-08-04 20:00 | 2020-09-05 | 2020-08-12 20:00 | 76 | 50.8333 | -25.1667
Span30 | 2020-06-21 | 2020-06-21 | 2020-07-09 | 2020-07-03 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-10 | 2020-07-24 20:00 | 2020-08-19 | 2020-07-31 20:00 | 2020-08-21 | 2020-07-31 08:00 | 2020-08-26 | 2020-08-02 20:00 | 2020-09-05 | 2020-08-11 20:00 | 76 | 51.8333 | -24.1667
Span31 | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-03 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-10 | 2020-07-22 20:00 | 2020-08-19 | 2020-08-01 20:00 | 2020-08-21 | 2020-07-29 08:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-09-05 | 2020-08-12 20:00 | 76 | 49.8333 | -26.1667
Span32 | 2020-06-21 | 2020-06-22 | 2020-07-09 | 2020-07-05 04:00 | 2020-07-11 | 2020-07-12 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-10 | 2020-07-25 20:00 | 2020-08-19 | 2020-07-30 20:00 | 2020-08-21 | 2020-07-31 08:00 | 2020-08-26 | 2020-08-05 20:00 | 2020-09-05 | 2020-08-10 20:00 | 76 | 49.8333 | -26.1667
Span33 | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-10 | 2020-07-24 20:00 | 2020-08-19 | 2020-07-30 20:00 | 2020-08-21 | 2020-07-31 08:00 | 2020-08-26 | 2020-08-04 20:00 | 2020-09-05 | 2020-08-14 20:00 | 76 | 51.8333 | -24.1667
Span34 | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-08 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-15 16:00 | 2020-08-10 | 2020-07-23 20:00 | 2020-08-19 | 2020-07-26 20:00 | 2020-08-21 | 2020-07-29 08:00 | 2020-08-26 | 2020-08-01 20:00 | 2020-09-05 | 2020-08-10 20:00 | 76 | 47.8333 | -28.1667
Span35 | 2020-06-21 | 2020-06-23 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-10 | 2020-07-22 20:00 | 2020-08-19 | 2020-07-31 20:00 | 2020-08-21 | 2020-08-02 08:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-09-05 | 2020-08-10 20:00 | 76 | 48.8333 | -27.1667
Span36 | 2020-06-21 | 2020-06-26 | 2020-07-09 | 2020-07-07 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-10 | 2020-07-23 20:00 | 2020-08-19 | 2020-07-30 20:00 | 2020-08-21 | 2020-08-03 08:00 | 2020-08-26 | 2020-08-05 20:00 | 2020-09-05 | 2020-08-13 20:00 | 76 | 48.8333 | -27.1667
Span37 | 2020-06-21 | 2020-06-25 | 2020-07-09 | 2020-07-03 04:00 | 2020-07-11 | 2020-07-14 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-10 | 2020-07-23 20:00 | 2020-08-19 | 2020-07-27 20:00 | 2020-08-21 | 2020-08-02 08:00 | 2020-08-26 | 2020-08-05 20:00 | 2020-09-05 | 2020-08-13 20:00 | 76 | 49.8333 | -26.1667
Span38 | 2020-06-21 | 2020-06-23 | 2020-07-09 | 2020-07-07 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-10 | 2020-07-25 20:00 | 2020-08-19 | 2020-07-28 20:00 | 2020-08-21 | 2020-07-31 08:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-09-05 | 2020-08-12 20:00 | 76 | 50.8333 | -25.1667
Span39 | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-12 04:00 | 2020-07-18 | 2020-07-20 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-17 | 2020-07-30 20:00 | 2020-08-26 | 2020-08-06 20:00 | 2020-08-28 | 2020-08-06 08:00 | 2020-09-02 | 2020-08-11 20:00 | 2020-09-12 | 2020-08-17 20:00 | 76 | 46.8333 | -29.1667
Span40 | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-10 04:00 | 2020-07-18 | 2020-07-21 16:00 | 2020-08-07 | 2020-07-23 16:00 | 2020-08-17 | 2020-08-01 20:00 | 2020-08-26 | 2020-08-06 20:00 | 2020-08-28 | 2020-08-09 08:00 | 2020-09-02 | 2020-08-11 20:00 | 2020-09-12 | 2020-08-19 20:00 | 76 | 48.8333 | -27.1667
Span41 | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-17 | 2020-08-01 20:00 | 2020-08-26 | 2020-08-01 20:00 | 2020-08-28 | 2020-08-05 08:00 | 2020-09-02 | 2020-08-09 20:00 | 2020-09-12 | 2020-08-18 20:00 | 76 | 47.8333 | -28.1667
Span42 | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-23 16:00 | 2020-08-17 | 2020-07-31 20:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-08-28 | 2020-08-07 08:00 | 2020-09-02 | 2020-08-12 20:00 | 2020-09-12 | 2020-08-20 20:00 | 76 | 49.8333 | -26.1667
Span43 | 2020-06-28 | 2020-06-30 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-17 | 2020-07-29 20:00 | 2020-08-26 | 2020-08-05 20:00 | 2020-08-28 | 2020-08-06 08:00 | 2020-09-02 | 2020-08-12 20:00 | 2020-09-12 | 2020-08-18 20:00 | 76 | 49.8333 | -26.1667
Span44 | 2020-06-28 | 2020-06-29 | 2020-07-16 | 2020-07-12 04:00 | 2020-07-18 | 2020-07-18 16:00 | 2020-08-07 | 2020-07-24 16:00 | 2020-08-17 | 2020-07-28 20:00 | 2020-08-26 | 2020-08-08 20:00 | 2020-08-28 | 2020-08-06 08:00 | 2020-09-02 | 2020-08-11 20:00 | 2020-09-12 | 2020-08-21 20:00 | 76 | 53.8333 | -22.1667
Span45 | 2020-06-28 | 2020-07-03 | 2020-07-16 | 2020-07-14 04:00 | 2020-07-18 | 2020-07-20 16:00 | 2020-08-07 | 2020-07-27 16:00 | 2020-08-17 | 2020-07-29 20:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-08-28 | 2020-08-06 08:00 | 2020-09-02 | 2020-08-10 20:00 | 2020-09-12 | 2020-08-18 20:00 | 76 | 46.8333 | -29.1667
Span46 | 2020-06-28 | 2020-06-29 | 2020-07-16 | 2020-07-14 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-27 16:00 | 2020-08-17 | 2020-07-30 20:00 | 2020-08-26 | 2020-08-02 20:00 | 2020-08-28 | 2020-08-06 08:00 | 2020-09-02 | 2020-08-10 20:00 | 2020-09-12 | 2020-08-18 20:00 | 76 | 50.8333 | -25.1667
Span47 | 2020-06-28 | 2020-06-28 | 2020-07-16 | 2020-07-13 04:00 | 2020-07-18 | 2020-07-22 16:00 | 2020-08-07 | 2020-07-26 16:00 | 2020-08-17 | 2020-07-31 20:00 | 2020-08-26 | 2020-08-06 20:00 | 2020-08-28 | 2020-08-07 08:00 | 2020-09-02 | 2020-08-08 20:00 | 2020-09-12 | 2020-08-19 20:00 | 76 | 52.8333 | -23.1667
Span48 | 2020-06-28 | 2020-07-01 | 2020-07-16 | 2020-07-14 04:00 | 2020-07-18 | 2020-07-17 16:00 | 2020-08-07 | 2020-07-27 16:00 | 2020-08-17 | 2020-08-01 20:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-08-28 | 2020-08-05 08:00 | 2020-09-02 | 2020-08-11 20:00 | 2020-09-12 | 2020-08-19 20:00 | 76 | 49.8333 | -26.1667
Span49 | 2020-06-28 | 2020-06-30 | 2020-07-16 | 2020-07-12 04:00 | 2020-07-18 | 2020-07-21 16:00 | 2020-08-07 | 2020-07-24 16:00 | 2020-08-17 | 2020-08-01 20:00 | 2020-08-26 | 2020-08-05 20:00 | 2020-08-28 | 2020-08-09 08:00 | 2020-09-02 | 2020-08-12 20:00 | 2020-09-12 | 2020-08-20 20:00 | 76 | 51.8333 | -24.1667
Span50 | 2020-06-28 | 2020-06-28 | 2020-07-16 | 2020-07-10 04:00 | 2020-07-18 | 2020-07-22 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-17 | 2020-07-29 20:00 | 2020-08-26 | 2020-08-03 20:00 | 2020-08-28 | 2020-08-06 08:00 | 2020-09-02 | 2020-08-08 20:00 | 2020-09-12 | 2020-08-17 20:00 | 76 | 50.8333 | -25.1667
Span51 | 2020-06-28 | 2020-07-01 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-18 16:00 | 2020-08-07 | 2020-07-24 16:00 | 2020-08-17 | 2020-07-28 20:00 | 2020-08-26 | 2020-08-07 20:00 | 2020-08-28 | 2020-08-07 08:00 | 2020-09-02 | 2020-08-10 20:00 | 2020-09-12 | 2020-08-17 20:00 | 76 | 47.8333 | -28.1667
Span52 | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-14 04:00 | 2020-07-21 | 2020-07-20 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-20 | 2020-08-04 20:00 | 2020-08-29 | 2020-08-05 20:00 | 2020-08-31 | 2020-08-10 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-21 20:00 | 76 | 49.8333 | -26.1667
Span53 | 2020-07-01 | 2020-07-01 | 2020-07-19 | 2020-07-14 04:00 | 2020-07-21 | 2020-07-21 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-20 | 2020-08-04 20:00 | 2020-08-29 | 2020-08-11 20:00 | 2020-08-31 | 2020-08-09 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-19 20:00 | 76 | 49.8333 | -26.1667
Span54 | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-18 04:00 | 2020-07-21 | 2020-07-25 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-20 | 2020-08-04 20:00 | 2020-08-29 | 2020-08-07 20:00 | 2020-08-31 | 2020-08-12 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-24 20:00 | 76 | 53.8333 | -22.1667
Span55 | 2020-07-01 | 2020-07-05 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-20 | 2020-08-05 20:00 | 2020-08-29 | 2020-08-08 20:00 | 2020-08-31 | 2020-08-09 08:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-15 | 2020-08-22 20:00 | 76 | 48.8333 | -27.1667
Span56 | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-18 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-25 16:00 | 2020-08-20 | 2020-07-31 20:00 | 2020-08-29 | 2020-08-07 20:00 | 2020-08-31 | 2020-08-08 08:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-15 | 2020-08-21 20:00 | 76 | 50.8333 | -25.1667
Span57 | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-17 04:00 | 2020-07-21 | 2020-07-22 16:00 | 2020-08-10 | 2020-07-28 16:00 | 2020-08-20 | 2020-08-03 20:00 | 2020-08-29 | 2020-08-07 20:00 | 2020-08-31 | 2020-08-11 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-20 20:00 | 76 | 49.8333 | -26.1667
Span58 | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-25 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-20 | 2020-08-01 20:00 | 2020-08-29 | 2020-08-06 20:00 | 2020-08-31 | 2020-08-10 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-22 20:00 | 76 | 50.8333 | -25.1667
Span59 | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-17 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-27 16:00 | 2020-08-20 | 2020-08-01 20:00 | 2020-08-29 | 2020-08-10 20:00 | 2020-08-31 | 2020-08-10 08:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-15 | 2020-08-24 20:00 | 76 | 53.8333 | -22.1667
Span60 | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-13 04:00 | 2020-07-21 | 2020-07-25 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-20 | 2020-08-02 20:00 | 2020-08-29 | 2020-08-09 20:00 | 2020-08-31 | 2020-08-09 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-20 20:00 | 76 | 48.8333 | -27.1667
Span61 | 2020-07-01 | 2020-07-01 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-20 | 2020-08-04 20:00 | 2020-08-29 | 2020-08-06 20:00 | 2020-08-31 | 2020-08-11 08:00 | 2020-09-05 | 2020-08-14 20:00 | 2020-09-15 | 2020-08-23 20:00 | 76 | 53.8333 | -22.1667
Span62 | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-18 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-20 | 2020-08-01 20:00 | 2020-08-29 | 2020-08-07 20:00 | 2020-08-31 | 2020-08-08 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-23 20:00 | 76 | 51.8333 | -24.1667
Span63 | 2020-07-01 | 2020-07-05 | 2020-07-19 | 2020-07-14 04:00 | 2020-07-21 | 2020-07-20 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-20 | 2020-07-31 20:00 | 2020-08-29 | 2020-08-11 20:00 | 2020-08-31 | 2020-08-11 08:00 | 2020-09-05 | 2020-08-13 20:00 | 2020-09-15 | 2020-08-21 20:00 | 76 | 47.8333 | -28.1667
Span64 | 2020-07-01 | 2020-07-06 | 2020-07-19 | 2020-07-17 04:00 | 2020-07-21 | 2020-07-22 16:00 | 2020-08-10 | 2020-07-27 16:00 | 2020-08-20 | 2020-08-04 20:00 | 2020-08-29 | 2020-08-09 20:00 | 2020-08-31 | 2020-08-08 08:00 | 2020-09-05 | 2020-08-14 20:00 | 2020-09-15 | 2020-08-23 20:00 | 76 | 48.8333 | -27.1667
Span65 | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-20 | 2020-08-01 20:00 | 2020-08-29 | 2020-08-07 20:00 | 2020-08-31 | 2020-08-10 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-24 20:00 | 76 | 53.8333 | -22.1667
Span66 | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-15 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-28 16:00 | 2020-08-20 | 2020-08-01 20:00 | 2020-08-29 | 2020-08-08 20:00 | 2020-08-31 | 2020-08-09 08:00 | 2020-09-05 | 2020-08-14 20:00 | 2020-09-15 | 2020-08-23 20:00 | 76 | 51.8333 | -24.1667
Span67 | 2020-07-01 | 2020-07-05 | 2020-07-19 | 2020-07-13 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-20 | 2020-08-01 20:00 | 2020-08-29 | 2020-08-05 20:00 | 2020-08-31 | 2020-08-10 08:00 | 2020-09-05 | 2020-08-15 20:00 | 2020-09-15 | 2020-08-20 20:00 | 76 | 46.8333 | -29.1667
Span68 | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-27 | 2020-08-08 20:00 | 2020-09-05 | 2020-08-17 20:00 | 2020-09-07 | 2020-08-18 08:00 | 2020-09-12 | 2020-08-22 20:00 | 2020-09-22 | 2020-08-30 20:00 | 76 | 52.8333 | -23.1667
Span69 | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-06 16:00 | 2020-08-27 | 2020-08-12 20:00 | 2020-09-05 | 2020-08-18 20:00 | 2020-09-07 | 2020-08-20 08:00 | 2020-09-12 | 2020-08-18 20:00 | 2020-09-22 | 2020-08-31 20:00 | 76 | 53.8333 | -22.1667
Span70 | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-24 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-06 16:00 | 2020-08-27 | 2020-08-08 20:00 | 2020-09-05 | 2020-08-14 20:00 | 2020-09-07 | 2020-08-17 08:00 | 2020-09-12 | 2020-08-19 20:00 | 2020-09-22 | 2020-08-30 20:00 | 76 | 50.8333 | -25.1667
Span71 | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-20 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-27 | 2020-08-10 20:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-07 | 2020-08-18 08:00 | 2020-09-12 | 2020-08-21 20:00 | 2020-09-22 | 2020-08-26 20:00 | 76 | 48.8333 | -27.1667
Span72 | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-22 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-27 | 2020-08-09 20:00 | 2020-09-05 | 2020-08-13 20:00 | 2020-09-07 | 2020-08-15 08:00 | 2020-09-12 | 2020-08-18 20:00 | 2020-09-22 | 2020-08-28 20:00 | 76 | 49.8333 | -26.1667
Span73 | 2020-07-08 | 2020-07-12 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-27 | 2020-08-11 20:00 | 2020-09-05 | 2020-08-13 20:00 | 2020-09-07 | 2020-08-15 08:00 | 2020-09-12 | 2020-08-18 20:00 | 2020-09-22 | 2020-08-28 20:00 | 76 | 47.8333 | -28.1667
Span74 | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-27 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-27 | 2020-08-10 20:00 | 2020-09-05 | 2020-08-16 20:00 | 2020-09-07 | 2020-08-18 08:00 | 2020-09-12 | 2020-08-19 20:00 | 2020-09-22 | 2020-08-26 20:00 | 76 | 46.8333 | -29.1667
Span75 | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-20 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-27 | 2020-08-11 20:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-07 | 2020-08-19 08:00 | 2020-09-12 | 2020-08-23 20:00 | 2020-09-22 | 2020-08-28 20:00 | 76 | 50.8333 | -25.1667
Span76 | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-08-01 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-27 | 2020-08-09 20:00 | 2020-09-05 | 2020-08-17 20:00 | 2020-09-07 | 2020-08-15 08:00 | 2020-09-12 | 2020-08-23 20:00 | 2020-09-22 | 2020-08-29 20:00 | 76 | 50.8333 | -25.1667
Span77 | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-20 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-01 16:00 | 2020-08-27 | 2020-08-11 20:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-07 | 2020-08-16 08:00 | 2020-09-12 | 2020-08-21 20:00 | 2020-09-22 | 2020-08-30 20:00 | 76 | 51.8333 | -24.1667
Span78 | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-27 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-27 | 2020-08-09 20:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-07 | 2020-08-20 08:00 | 2020-09-12 | 2020-08-23 20:00 | 2020-09-22 | 2020-08-30 20:00 | 76 | 51.8333 | -24.1667
Span79 | 2020-07-08 | 2020-07-12 | 2020-07-26 | 2020-07-22 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-27 | 2020-08-07 20:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-07 | 2020-08-17 08:00 | 2020-09-12 | 2020-08-22 20:00 | 2020-09-22 | 2020-08-31 20:00 | 76 | 50.8333 | -25.1667
Span80 | 2020-07-08 | 2020-07-13 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-02 16:00 | 2020-08-27 | 2020-08-08 20:00 | 2020-09-05 | 2020-08-17 20:00 | 2020-09-07 | 2020-08-19 08:00 | 2020-09-12 | 2020-08-20 20:00 | 2020-09-22 | 2020-08-29 20:00 | 76 | 47.8333 | -28.1667
Span81 | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-27 | 2020-08-11 20:00 | 2020-09-05 | 2020-08-13 20:00 | 2020-09-07 | 2020-08-18 08:00 | 2020-09-12 | 2020-08-23 20:00 | 2020-09-22 | 2020-08-31 20:00 | 76 | 53.8333 | -22.1667
Span82 | 2020-07-08 | 2020-07-08 | 2020-07-26 | 2020-07-24 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-27 | 2020-08-07 20:00 | 2020-09-05 | 2020-08-12 20:00 | 2020-09-07 | 2020-08-19 08:00 | 2020-09-12 | 2020-08-22 20:00 | 2020-09-22 | 2020-08-29 20:00 | 76 | 52.8333 | -23.1667
Span83 | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-31 16:00 | 2020-08-17 | 2020-08-06 16:00 | 2020-08-27 | 2020-08-09 20:00 | 2020-09-05 | 2020-08-18 20:00 | 2020-09-07 | 2020-08-17 08:00 | 2020-09-12 | 2020-08-18 20:00 | 2020-09-22 | 2020-08-30 20:00 | 76 | 52.8333 | -23.1667
Span84 | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-02 16:00 | 2020-08-27 | 2020-08-11 20:00 | 2020-09-05 | 2020-08-14 20:00 | 2020-09-07 | 2020-08-19 08:00 | 2020-09-12 | 2020-08-20 20:00 | 2020-09-22 | 2020-08-30 20:00 | 76 | 50.8333 | -25.1667
Span85 | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-25 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-27 | 2020-08-11 20:00 | 2020-09-05 | 2020-08-11 20:00 | 2020-09-07 | 2020-08-16 08:00 | 2020-09-12 | 2020-08-23 20:00 | 2020-09-22 | 2020-08-28 20:00 | 76 | 48.8333 | -27.1667
Span86 | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-27 | 2020-08-11 20:00 | 2020-09-05 | 2020-08-18 20:00 | 2020-09-07 | 2020-08-18 08:00 | 2020-09-12 | 2020-08-21 20:00 | 2020-09-22 | 2020-08-30 20:00 | 76 | 52.8333 | -23.1667
Span87 | 2020-07-15 | 2020-07-15 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-06 16:00 | 2020-08-24 | 2020-08-08 16:00 | 2020-09-03 | 2020-08-15 20:00 | 2020-09-12 | 2020-08-23 20:00 | 2020-09-14 | 2020-08-23 08:00 | 2020-09-19 | 2020-08-27 20:00 | 2020-09-29 | 2020-09-03 20:00 | 76 | 50.8333 | -25.1667
Span88 | 2020-07-15 | 2020-07-20 | 2020-08-02 | 2020-07-30 04:00 | 2020-08-04 | 2020-08-03 16:00 | 2020-08-24 | 2020-08-09 16:00 | 2020-09-03 | 2020-08-17 20:00 | 2020-09-12 | 2020-08-20 20:00 | 2020-09-14 | 2020-08-26 08:00 | 2020-09-19 | 2020-08-28 20:00 | 2020-09-29 | 2020-09-03 20:00 | 76 | 45.8333 | -30.1667
Span89 | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-08-01 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-09-03 | 2020-08-18 20:00 | 2020-09-12 | 2020-08-21 20:00 | 2020-09-14 | 2020-08-26 08:00 | 2020-09-19 | 2020-08-27 20:00 | 2020-09-29 | 2020-09-04 20:00 | 76 | 48.8333 | -27.1667
Span90 | 2020-07-15 | 2020-07-15 | 2020-08-02 | 2020-07-31 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-08 16:00 | 2020-09-03 | 2020-08-17 20:00 | 2020-09-12 | 2020-08-19 20:00 | 2020-09-14 | 2020-08-24 08:00 | 2020-09-19 | 2020-08-30 20:00 | 2020-09-29 | 2020-09-05 20:00 | 76 | 52.8333 | -23.1667
Span91 | 2020-07-15 | 2020-07-17 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-09-03 | 2020-08-16 20:00 | 2020-09-12 | 2020-08-21 20:00 | 2020-09-14 | 2020-08-26 08:00 | 2020-09-19 | 2020-08-28 20:00 | 2020-09-29 | 2020-09-02 20:00 | 76 | 47.8333 | -28.1667
Span92 | 2020-07-15 | 2020-07-19 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-06 16:00 | 2020-08-24 | 2020-08-11 16:00 | 2020-09-03 | 2020-08-17 20:00 | 2020-09-12 | 2020-08-23 20:00 | 2020-09-14 | 2020-08-26 08:00 | 2020-09-19 | 2020-08-27 20:00 | 2020-09-29 | 2020-09-02 20:00 | 76 | 45.8333 | -30.1667
Span93 | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-30 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-09-03 | 2020-08-17 20:00 | 2020-09-12 | 2020-08-20 20:00 | 2020-09-14 | 2020-08-23 08:00 | 2020-09-19 | 2020-08-27 20:00 | 2020-09-29 | 2020-09-02 20:00 | 76 | 46.8333 | -29.1667
Span94 | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-07 16:00 | 2020-08-24 | 2020-08-09 16:00 | 2020-09-03 | 2020-08-15 20:00 | 2020-09-12 | 2020-08-24 20:00 | 2020-09-14 | 2020-08-27 08:00 | 2020-09-19 | 2020-08-27 20:00 | 2020-09-29 | 2020-09-03 20:00 | 76 | 47.8333 | -28.1667
Span95 | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-29 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-12 16:00 | 2020-09-03 | 2020-08-15 20:00 | 2020-09-12 | 2020-08-22 20:00 | 2020-09-14 | 2020-08-23 08:00 | 2020-09-19 | 2020-08-26 20:00 | 2020-09-29 | 2020-09-06 20:00 | 76 | 50.8333 | -25.1667
Span96 | 2020-07-15 | 2020-07-19 | 2020-08-02 | 2020-08-01 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-08 16:00 | 2020-09-03 | 2020-08-18 20:00 | 2020-09-12 | 2020-08-20 20:00 | 2020-09-14 | 2020-08-26 08:00 | 2020-09-19 | 2020-08-26 20:00 | 2020-09-29 | 2020-09-06 20:00 | 76 | 49.8333 | -26.1667
Span97 | 2020-07-15 | 2020-07-16 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-08 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-09-03 | 2020-08-19 20:00 | 2020-09-12 | 2020-08-19 20:00 | 2020-09-14 | 2020-08-25 08:00 | 2020-09-19 | 2020-08-26 20:00 | 2020-09-29 | 2020-09-02 20:00 | 76 | 48.8333 | -27.1667
Span98 | 2020-07-15 | 2020-07-17 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-12 16:00 | 2020-09-03 | 2020-08-16 20:00 | 2020-09-12 | 2020-08-19 20:00 | 2020-09-14 | 2020-08-22 08:00 | 2020-09-19 | 2020-08-28 20:00 | 2020-09-29 | 2020-09-05 20:00 | 76 | 50.8333 | -25.1667
Span99 | 2020-07-15 | 2020-07-19 | 2020-08-02 | 2020-07-29 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-12 16:00 | 2020-09-03 | 2020-08-16 20:00 | 2020-09-12 | 2020-08-20 20:00 | 2020-09-14 | 2020-08-23 08:00 | 2020-09-19 | 2020-08-27 20:00 | 2020-09-29 | 2020-09-04 20:00 | 76 | 47.8333 | -28.1667
Span100 | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-30 04:00 | 2020-08-04 | 2020-08-07 16:00 | 2020-08-24 | 2020-08-11 16:00 | 2020-09-03 | 2020-08-18 20:00 | 2020-09-12 | 2020-08-24 20:00 | 2020-09-14 | 2020-08-26 08:00 | 2020-09-19 | 2020-08-29 20:00 | 2020-09-29 | 2020-09-04 20:00 | 76 | 48.8333 | -27.1667
Formulas:
PathEngineeringDocument_BL = Table_SiteMilestonesTracking[[#This Row],[TechnicalPathSurvey_BL]]+t1_SiteSurveyBL+t2_SiteEngineeringDocumentBL
PathConstructionWorkOrder_BL = Table_SiteMilestonesTracking[[#This Row],[PathEngineeringDocument_BL]]+t3_SiteConstructionWorkOrderBL
CivilWorks_BL = Table_SiteMilestonesTracking[[#This Row],[PathConstructionWorkOrder_BL]]+t4_CivilWorksBL
MechanicalWorks_BL = Table_SiteMilestonesTracking[[#This Row],[CivilWorks_BL]]+t5_MechanicalWorksBL
CablingWorks_BL = Table_SiteMilestonesTracking[[#This Row],[MechanicalWorks_BL]]+t6_ElectricalWorksBL
ConstructionAcceptance_BL = Table_SiteMilestonesTracking[[#This Row],[CablingWorks_BL]]+t7_ConstructionAcceptanceBL
ReadyForOperation_BL = Table_SiteMilestonesTracking[[#This Row],[ConstructionAcceptance_BL]]+t8_ReadyForInstallationBL
PathInOperation_BL = Table_SiteMilestonesTracking[[#This Row],[ReadyForOperation_BL]]+t9_SiteInOperationsBL

## 4. Summary Tracking
Deployment Tracking Summary
|  |  |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
Year | Week | StartDate | EndDate | TechnicalSiteSurvey_BL | TechnicalSiteSurvey_BL(SUM) | TechnicalSiteSurvey_AC | TechnicalSiteSurvey_AC(SUM) | PathEngineeringDocument_BL | PathEngineeringDocument_BL(SUM) | PathEngineeringDocument_AC | PathEngineeringDocument_AC(SUM) | PathConstructionWorkOrder_BL | PathConstructionWorkOrder_BL(SUM) | PathConstructionWorkOrder_AC | PathConstructionWorkOrder_AC(SUM) | CivilWorks_BL | CivilWorks_BL(SUM) | CivilWorks_AC | CivilWorks_AC(SUM) | MechanicalWorks_BL | MechanicalWorks_BL(SUM) | MechanicalWorks_AC | MechanicalWorks_AC(SUM) | CablingWorks_BL | CablingWorks_BL(SUM) | CablingWorks_AC | CablingWorks_AC(SUM) | ConstructionAcceptance_BL | ConstructionAcceptance_BL(SUM) | ConstructionAcceptance_AC | ConstructionAcceptance_AC(SUM) | ReadyForOperation_BL | ReadyForOperation_BL(SUM) | ReadyForOperation_AC | ReadyForOperation_AC(SUM) | PathInOperations_BL | PathInOperations_BL(SUM) | PathInOperations_AC | PathInOperations_AC(SUM)
2020 | 1 | 2019-12-30 | 2020-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 2 | 2020-01-06 | 2020-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 3 | 2020-01-13 | 2020-01-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 4 | 2020-01-20 | 2020-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 5 | 2020-01-27 | 2020-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 6 | 2020-02-03 | 2020-02-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 7 | 2020-02-10 | 2020-02-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 8 | 2020-02-17 | 2020-02-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 9 | 2020-02-24 | 2020-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 10 | 2020-03-02 | 2020-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 11 | 2020-03-09 | 2020-03-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 12 | 2020-03-16 | 2020-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 13 | 2020-03-23 | 2020-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 14 | 2020-03-30 | 2020-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 15 | 2020-04-06 | 2020-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 16 | 2020-04-13 | 2020-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 17 | 2020-04-20 | 2020-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 18 | 2020-04-27 | 2020-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 19 | 2020-05-04 | 2020-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 20 | 2020-05-11 | 2020-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 21 | 2020-05-18 | 2020-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 22 | 2020-05-25 | 2020-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 23 | 2020-06-01 | 2020-06-07 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 24 | 2020-06-08 | 2020-06-14 | 9 | 16 | 9 | 16 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 25 | 2020-06-15 | 2020-06-21 | 22 | 38 | 11 | 27 | 7 | 7 | 8 | 9 | 7 | 7 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 26 | 2020-06-22 | 2020-06-28 | 13 | 51 | 13 | 40 | 9 | 16 | 9 | 18 | 9 | 16 | 10 | 11 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 27 | 2020-06-29 | 2020-07-05 | 16 | 67 | 26 | 66 | 10 | 26 | 12 | 30 | 10 | 26 | 10 | 21 | 0 | 0 | 7 | 13 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 28 | 2020-07-06 | 2020-07-12 | 19 | 86 | 19 | 85 | 12 | 38 | 17 | 47 | 12 | 38 | 8 | 29 | 7 | 7 | 9 | 22 | 0 | 0 | 11 | 15 | 0 | 0 | 8 | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
2020 | 29 | 2020-07-13 | 2020-07-19 | 14 | 100 | 14 | 99 | 29 | 67 | 20 | 67 | 13 | 51 | 16 | 45 | 9 | 16 | 16 | 38 | 0 | 0 | 11 | 26 | 0 | 0 | 8 | 16 | 0 | 0 | 10 | 14 | 0 | 0 | 7 | 8 | 0 | 0 | 0 | 0
2020 | 30 | 2020-07-20 | 2020-07-26 | 0 | 100 | 1 | 100 | 19 | 86 | 19 | 86 | 16 | 67 | 22 | 67 | 10 | 26 | 15 | 53 | 7 | 7 | 12 | 38 | 0 | 0 | 11 | 27 | 0 | 0 | 6 | 20 | 0 | 0 | 10 | 18 | 0 | 0 | 7 | 7
2020 | 31 | 2020-07-27 | 2020-08-02 | 0 | 100 | 0 | 100 | 14 | 100 | 14 | 100 | 19 | 86 | 19 | 86 | 12 | 38 | 17 | 70 | 9 | 16 | 22 | 60 | 7 | 7 | 13 | 40 | 7 | 7 | 17 | 37 | 0 | 0 | 10 | 28 | 0 | 0 | 9 | 16
2020 | 32 | 2020-08-03 | 2020-08-09 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 14 | 100 | 13 | 51 | 21 | 91 | 10 | 26 | 16 | 76 | 9 | 16 | 24 | 64 | 9 | 16 | 21 | 58 | 7 | 7 | 13 | 41 | 0 | 0 | 10 | 26
2020 | 33 | 2020-08-10 | 2020-08-16 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 16 | 67 | 9 | 100 | 12 | 38 | 16 | 92 | 10 | 26 | 16 | 80 | 10 | 26 | 14 | 72 | 9 | 16 | 26 | 67 | 7 | 7 | 12 | 38
2020 | 34 | 2020-08-17 | 2020-08-23 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 19 | 86 | 0 | 100 | 29 | 67 | 8 | 100 | 12 | 38 | 18 | 98 | 12 | 38 | 19 | 91 | 10 | 26 | 19 | 86 | 9 | 16 | 26 | 64
2020 | 35 | 2020-08-24 | 2020-08-30 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 19 | 86 | 0 | 100 | 29 | 67 | 2 | 100 | 13 | 51 | 9 | 100 | 12 | 38 | 14 | 100 | 10 | 26 | 19 | 83
2020 | 36 | 2020-08-31 | 2020-09-06 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 19 | 86 | 0 | 100 | 16 | 67 | 0 | 100 | 29 | 67 | 0 | 100 | 12 | 38 | 17 | 100
2020 | 37 | 2020-09-07 | 2020-09-13 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 19 | 86 | 0 | 100 | 19 | 86 | 0 | 100 | 13 | 51 | 0 | 100
2020 | 38 | 2020-09-14 | 2020-09-20 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 16 | 67 | 0 | 100
2020 | 39 | 2020-09-21 | 2020-09-27 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 19 | 86 | 0 | 100
2020 | 40 | 2020-09-28 | 2020-10-04 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100
Formulas:
StartDate = DATE(Table_SiteMilestoneTrackingSummary[[#This Row],[Year]],1,-2)-WEEKDAY(DATE(Table_SiteMilestoneTrackingSummary[[#This Row],[Year]],1,3))+Table_SiteMilestoneTrackingSummary[[#This Row],[Week]]*7
EndDate = Table_SiteMilestoneTrackingSummary[[#This Row],[StartDate]]+6

## 5. Tracking Graphs
Deployment Schedule Visuals
Schedule Baseline | Schedule Actual
Path-accumulates per milestone, by week | Path-accumulates per milestone, by week
TechnicalSiteSurvey Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteEngineeringDocument Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
FiberConstructionWorkOrder Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
CivilWorks Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
MechanicalWorks Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
CablingWorks Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
ConstructionAcceptance Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
ReadyForOperation Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
PathInOperations Baseline vs Actual
Path-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.