## Cover
Gantt diagram for Site Construction
<Release Date>

## Gantt
GANTT CHART FOR SITE CONSTRUCTION TEMPLATE
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE
Site Acquisition
| Documentation | 2020-01-05 | 2020-01-09 | 0 | 5 | Vendor#1 | 100%
| Preparation and signing of contract | 2020-01-09 | 2020-01-11 | 4 | 3 | Vendor#1 | 100%
| Permits | 2020-01-11 | 2020-01-25 | 6 | 15 | Vendor#1 | 60%
| Licensing | 2020-01-25 | 2020-02-08 | 20 | 15 | Vendor#1 | 40%
Site Survey and A&E Analysis
| Technical Site Survey (preparation and generation of report) | 2020-02-08 | 2020-02-11 | 34 | 4 | Vendor#1 | 100%
| Engineering and Structural Evaluation | 2020-02-11 | 2020-02-24 | 37 | 14 | Vendor#1 | 80%
Construction
| Soil excavation and ground cleaning | 2020-02-25 | 2020-02-26 | 51 | 2 | Vendor#1 | 100%
| Stoke and leveling | 2020-02-27 | 2020-02-27 | 53 | 1 | Vendor#1 | 80%
| Excavations for base and tower | 2020-02-28 | 2020-02-29 | 54 | 2 | Vendor#1 | 60%
| Steel assembling and leveling | 2020-03-01 | 2020-03-04 12:00 | 56 | 4 | Vendor#1 | 40%
| Dice shoring | 2020-03-05 12:00 | 2020-03-06 12:00 | 60 | 2 | Vendor#1 | 20%
| Bending concrete basis for equipment | 2020-03-07 12:00 | 2020-03-08 12:00 | 62 | 2 | Vendor#1 | 100%
| Concrete casting | 2020-03-09 12:00 | 2020-03-09 | 64 | 1 | Vendor#1 | 100%
| Base filings and compacting | 2020-03-10 | 2020-03-11 | 65 | 2 | Vendor#1 | 100%
| Main Power Installation | 2020-03-12 | 2020-03-14 | 67 | 3 | Vendor#1 | 100%
| Main Power connection | 2020-03-15 | 2020-03-16 | 70 | 2 | Vendor#1 | 100%
| Tower erection | 2020-03-17 | 2020-03-20 | 72 | 4 | Vendor#1 | 100%
| Rebuff enclosure bases assembling | 2020-03-21 | 2020-03-22 | 76 | 2 | Vendor#1 | 100%
| Perimeter Fence/wall installation | 2020-03-23 | 2020-03-25 | 78 | 3 | Vendor#1 | 100%
| Access door assembling | 2020-03-26 | 2020-03-26 | 81 | 1 | Vendor#1 | 100%
| Preparation of electrical and ground canalization | 2020-03-27 | 2020-03-28 | 82 | 2 | Vendor#1 | 100%
| Electrical and grounding registers installation | 2020-03-29 | 2020-03-30 | 84 | 2 | Vendor#1 | 100%
| Application of Gravel | 2020-03-31 | 2020-03-31 | 86 | 1 | Vendor#1 | 100%
Installation and Commissioning
MW I&C
| MW mounting | 2020-04-01 | 2020-04-01 | 87 | 1 | Vendor#1 | 100%
| MW LOS | 2020-04-02 | 2020-04-02 | 88 | 1 | Vendor#1 | 80%
| Commissioning | 2020-04-03 | 2020-04-03 | 89 | 1 | Vendor#1 | 60%
| RF I&C | [5 empty] | 0%
| Antennas mounting | 2020-04-04 | 2020-04-04 | 90 | 1 | Vendor#1 | 100%
| Feeders/F.O Cabling | 2020-04-05 | 2020-04-05 | 91 | 1 | Vendor#1 | 100%
| Shelter/Cabinets connections | 2020-04-06 | 2020-04-06 | 92 | 1 | Vendor#1 | 100%
| Commissioning | 2020-04-07 | 2020-04-07 | 93 | 1 | Vendor#1 | 100%
Integration
| Integration | 2020-04-08 | 2020-04-08 | 94 | 1 | Vendor#1 | 100%
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1