## Cover
Site Construction Milestones Tracking
<Release Date>

## Instructions
Site Construction Tracking template
Instructions:
1. 9 Milestones are considered as indicated in Milestones sheet (NaaS Operator can adjust "Expected Duration Estimate" to automatically update Baseline Values in the Site Tracking Sheet)
2. NaaS Operator utilizes Site Tracking Sheet to track dates for Site Construction Milestones (only Actual Dates need to be updated)
3. Summary Tracking Sheet and Schedule Visuals sheet are automatically completed with data from Site Tracking sheet
Notes:
BL = Baseline
AC = Actual

## Milestones
SITE CONSTRUCTION MILESTONES
Project Title: Site Construction Project
Date Prepared: May 27th, 2020
ID | Expected Duration Estimate
t1_TechnicalSiteSurveyBL | 4
t2_SiteEngineeringDocumentBL | 14
t3_SiteConstructionWorkOrderBL | 2
t4_CivilWorksBL | 20
t5_MechanicalWorksBL | 6
t6_ElectricalWorksBL | 9
t7_ConstructionAcceptanceBL | 2
t8_ReadyForInstallationBL | 5
t9_SiteInOperationsBL | 10

## Site Tracking Sheet
Construction Tracking per site
SiteID | Region | District | SiteConfig | TowerCo | TowerID | TechnicalSiteSurvey_BL | TechnicalSiteSurvey_AC | SiteEngineeringDocument_BL | SiteEngineeringDocument_AC | SiteConstructionWorkOrder_BL | SiteConstructionWorkOrder_AC | CivilWorks_BL | CivilWorks_AC | MechanicalWorks_BL | MechanicalWorks_AC | ElectricalWorks_BL | ElectricalWorks_AC | ConstructionAcceptance_BL | ConstructionAcceptance_AC | ReadyForInstallation_BL | ReadyForInstallation_AC | SiteInOperations_BL | SiteInOperations_AC | E2E_Site_BL | E2E_Site_AC | E2E_Site_deltaT | Remark
Site1 | North | MTY | MACRO | SuperTowers | ST0014 | 2020-06-01 | 2020-06-05 | 2020-06-19 | 2020-06-14 04:00 | 2020-06-21 | 2020-06-24 16:00 | 2020-07-11 | 2020-06-30 16:00 | 2020-07-17 | 2020-07-06 20:00 | 2020-07-26 | 2020-07-09 20:00 | 2020-07-28 | 2020-07-13 08:00 | 2020-08-02 | 2020-07-17 20:00 | 2020-08-12 | 2020-07-20 20:00 | 72 | 45.8333 | -26.1667
Site2 | North | ZAC | MINI | PremiumTowers | PT001211 | 2020-06-01 | 2020-06-02 | 2020-06-19 | 2020-06-16 04:00 | 2020-06-21 | 2020-06-21 16:00 | 2020-07-11 | 2020-06-25 16:00 | 2020-07-17 | 2020-07-06 20:00 | 2020-07-26 | 2020-07-06 20:00 | 2020-07-28 | 2020-07-10 08:00 | 2020-08-02 | 2020-07-15 20:00 | 2020-08-12 | 2020-07-25 20:00 | 72 | 53.8333 | -18.1667
Site3 | Center | GTO | SMALL | NaaS Owned | T00001 | 2020-06-01 | 2020-06-04 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-25 16:00 | 2020-07-11 | 2020-06-28 16:00 | 2020-07-17 | 2020-07-06 20:00 | 2020-07-26 | 2020-07-07 20:00 | 2020-07-28 | 2020-07-12 08:00 | 2020-08-02 | 2020-07-16 20:00 | 2020-08-12 | 2020-07-23 20:00 | 72 | 49.8333 | -22.1667
Site4 | Center | QRO | MACRO | NaaS Owned | T00013 | 2020-06-01 | 2020-06-04 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-22 16:00 | 2020-07-11 | 2020-06-26 16:00 | 2020-07-17 | 2020-07-05 20:00 | 2020-07-26 | 2020-07-06 20:00 | 2020-07-28 | 2020-07-14 08:00 | 2020-08-02 | 2020-07-12 20:00 | 2020-08-12 | 2020-07-23 20:00 | 72 | 49.8333 | -22.1667
Site5 | South | VER | MINI | NeatTowers | NT0041 | 2020-06-01 | 2020-06-02 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-22 16:00 | 2020-07-11 | 2020-06-28 16:00 | 2020-07-17 | 2020-07-04 20:00 | 2020-07-26 | 2020-07-10 20:00 | 2020-07-28 | 2020-07-10 08:00 | 2020-08-02 | 2020-07-14 20:00 | 2020-08-12 | 2020-07-20 20:00 | 72 | 48.8333 | -23.1667
Site6 | South | CHI | SMALL | NeatTowers | NT0111 | 2020-06-01 | 2020-06-03 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-24 16:00 | 2020-07-11 | 2020-06-27 16:00 | 2020-07-17 | 2020-07-02 20:00 | 2020-07-26 | 2020-07-10 20:00 | 2020-07-28 | 2020-07-13 08:00 | 2020-08-02 | 2020-07-13 20:00 | 2020-08-12 | 2020-07-24 20:00 | 72 | 51.8333 | -20.1667
Site7 | North | MTY | MACRO | SuperTowers | ST0524 | 2020-06-01 | 2020-06-04 | 2020-06-19 | 2020-06-17 04:00 | 2020-06-21 | 2020-06-22 16:00 | 2020-07-11 | 2020-06-28 16:00 | 2020-07-17 | 2020-07-05 20:00 | 2020-07-26 | 2020-07-10 20:00 | 2020-07-28 | 2020-07-12 08:00 | 2020-08-02 | 2020-07-14 20:00 | 2020-08-12 | 2020-07-24 20:00 | 72 | 50.8333 | -21.1667
Site8 | North | ZAC | MINI | PremiumTowers | PT044331 | 2020-06-08 | 2020-06-11 | 2020-06-26 | 2020-06-22 04:00 | 2020-06-28 | 2020-06-28 16:00 | 2020-07-18 | 2020-07-05 16:00 | 2020-07-24 | 2020-07-09 20:00 | 2020-08-02 | 2020-07-18 20:00 | 2020-08-04 | 2020-07-21 08:00 | 2020-08-09 | 2020-07-24 20:00 | 2020-08-19 | 2020-07-30 20:00 | 72 | 49.8333 | -22.1667
Site9 | Center | GTO | SMALL | NaaS Owned | T01110 | 2020-06-08 | 2020-06-12 | 2020-06-26 | 2020-06-22 04:00 | 2020-06-28 | 2020-06-29 16:00 | 2020-07-18 | 2020-07-03 16:00 | 2020-07-24 | 2020-07-08 20:00 | 2020-08-02 | 2020-07-15 20:00 | 2020-08-04 | 2020-07-20 08:00 | 2020-08-09 | 2020-07-24 20:00 | 2020-08-19 | 2020-07-29 20:00 | 72 | 47.8333 | -24.1667
Site10 | Center | QRO | MACRO | NaaS Owned | T00054 | 2020-06-08 | 2020-06-10 | 2020-06-26 | 2020-06-24 04:00 | 2020-06-28 | 2020-07-02 16:00 | 2020-07-18 | 2020-07-03 16:00 | 2020-07-24 | 2020-07-12 20:00 | 2020-08-02 | 2020-07-18 20:00 | 2020-08-04 | 2020-07-18 08:00 | 2020-08-09 | 2020-07-20 20:00 | 2020-08-19 | 2020-07-31 20:00 | 72 | 51.8333 | -20.1667
Site11 | South | VER | MINI | SuperTowers | ST0756 | 2020-06-08 | 2020-06-13 | 2020-06-26 | 2020-06-22 04:00 | 2020-06-28 | 2020-06-29 16:00 | 2020-07-18 | 2020-07-06 16:00 | 2020-07-24 | 2020-07-13 20:00 | 2020-08-02 | 2020-07-13 20:00 | 2020-08-04 | 2020-07-17 08:00 | 2020-08-09 | 2020-07-23 20:00 | 2020-08-19 | 2020-08-01 20:00 | 72 | 49.8333 | -22.1667
Site12 | South | CHI | SMALL | PremiumTowers | PT00984 | 2020-06-08 | 2020-06-11 | 2020-06-26 | 2020-06-25 04:00 | 2020-06-28 | 2020-06-28 16:00 | 2020-07-18 | 2020-07-03 16:00 | 2020-07-24 | 2020-07-10 20:00 | 2020-08-02 | 2020-07-12 20:00 | 2020-08-04 | 2020-07-17 08:00 | 2020-08-09 | 2020-07-19 20:00 | 2020-08-19 | 2020-07-28 20:00 | 72 | 47.8333 | -24.1667
Site13 | North | MTY | MACRO | NaaS Owned | T00612 | 2020-06-08 | 2020-06-09 | 2020-06-26 | 2020-06-21 04:00 | 2020-06-28 | 2020-06-28 16:00 | 2020-07-18 | 2020-07-06 16:00 | 2020-07-24 | 2020-07-11 20:00 | 2020-08-02 | 2020-07-19 20:00 | 2020-08-04 | 2020-07-17 08:00 | 2020-08-09 | 2020-07-23 20:00 | 2020-08-19 | 2020-07-27 20:00 | 72 | 48.8333 | -23.1667
Site14 | North | ZAC | MINI | NaaS Owned | T00803 | 2020-06-08 | 2020-06-09 | 2020-06-26 | 2020-06-24 04:00 | 2020-06-28 | 2020-07-02 16:00 | 2020-07-18 | 2020-07-04 16:00 | 2020-07-24 | 2020-07-09 20:00 | 2020-08-02 | 2020-07-15 20:00 | 2020-08-04 | 2020-07-17 08:00 | 2020-08-09 | 2020-07-20 20:00 | 2020-08-19 | 2020-08-01 20:00 | 72 | 53.8333 | -18.1667
Site15 | Center | GTO | SMALL | NeatTowers | NT00454 | 2020-06-08 | 2020-06-12 | 2020-06-26 | 2020-06-21 04:00 | 2020-06-28 | 2020-06-27 16:00 | 2020-07-18 | 2020-07-06 16:00 | 2020-07-24 | 2020-07-08 20:00 | 2020-08-02 | 2020-07-13 20:00 | 2020-08-04 | 2020-07-16 08:00 | 2020-08-09 | 2020-07-24 20:00 | 2020-08-19 | 2020-07-28 20:00 | 72 | 46.8333 | -25.1667
Site16 | Center | QRO | MACRO | SuperTowers | ST3123 | 2020-06-08 | 2020-06-11 | 2020-06-26 | 2020-06-24 04:00 | 2020-06-28 | 2020-07-02 16:00 | 2020-07-18 | 2020-07-02 16:00 | 2020-07-24 | 2020-07-11 20:00 | 2020-08-02 | 2020-07-13 20:00 | 2020-08-04 | 2020-07-19 08:00 | 2020-08-09 | 2020-07-22 20:00 | 2020-08-19 | 2020-07-30 20:00 | 72 | 49.8333 | -22.1667
Site17 | South | VER | MINI | PremiumTowers | PT99231 | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-06-30 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-11 16:00 | 2020-07-31 | 2020-07-19 20:00 | 2020-08-09 | 2020-07-23 20:00 | 2020-08-11 | 2020-07-26 08:00 | 2020-08-16 | 2020-07-27 20:00 | 2020-08-26 | 2020-08-06 20:00 | 72 | 51.8333 | -20.1667
Site18 | South | CHI | SMALL | NaaS Owned |  | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-06 16:00 | 2020-07-25 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-19 20:00 | 2020-08-09 | 2020-07-26 20:00 | 2020-08-11 | 2020-07-25 08:00 | 2020-08-16 | 2020-07-30 20:00 | 2020-08-26 | 2020-08-08 20:00 | 72 | 53.8333 | -18.1667
Site19 | North | MTY | MACRO | NaaS Owned |  | 2020-06-15 | 2020-06-18 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-12 16:00 | 2020-07-31 | 2020-07-19 20:00 | 2020-08-09 | 2020-07-23 20:00 | 2020-08-11 | 2020-07-27 08:00 | 2020-08-16 | 2020-07-30 20:00 | 2020-08-26 | 2020-08-07 20:00 | 72 | 50.8333 | -21.1667
Site20 | North | ZAC | MINI | PremiumTowers |  | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-12 16:00 | 2020-07-31 | 2020-07-19 20:00 | 2020-08-09 | 2020-07-26 20:00 | 2020-08-11 | 2020-07-25 08:00 | 2020-08-16 | 2020-07-29 20:00 | 2020-08-26 | 2020-08-04 20:00 | 72 | 49.8333 | -22.1667
Site21 | Center | GTO | SMALL | NaaS Owned |  | 2020-06-15 | 2020-06-15 | 2020-07-03 | 2020-06-30 04:00 | 2020-07-05 | 2020-07-09 16:00 | 2020-07-25 | 2020-07-10 16:00 | 2020-07-31 | 2020-07-18 20:00 | 2020-08-09 | 2020-07-20 20:00 | 2020-08-11 | 2020-07-25 08:00 | 2020-08-16 | 2020-07-29 20:00 | 2020-08-26 | 2020-08-07 20:00 | 72 | 53.8333 | -18.1667
Site22 | Center | QRO | MACRO | NaaS Owned |  | 2020-06-15 | 2020-06-19 | 2020-07-03 | 2020-06-27 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-14 16:00 | 2020-07-31 | 2020-07-16 20:00 | 2020-08-09 | 2020-07-22 20:00 | 2020-08-11 | 2020-07-27 08:00 | 2020-08-16 | 2020-07-26 20:00 | 2020-08-26 | 2020-08-05 20:00 | 72 | 47.8333 | -24.1667
Site23 | South | VER | MINI | SuperTowers |  | 2020-06-15 | 2020-06-19 | 2020-07-03 | 2020-06-29 04:00 | 2020-07-05 | 2020-07-07 16:00 | 2020-07-25 | 2020-07-14 16:00 | 2020-07-31 | 2020-07-18 20:00 | 2020-08-09 | 2020-07-22 20:00 | 2020-08-11 | 2020-07-28 08:00 | 2020-08-16 | 2020-07-26 20:00 | 2020-08-26 | 2020-08-05 20:00 | 72 | 47.8333 | -24.1667
Site24 | South | CHI | SMALL | PremiumTowers |  | 2020-06-15 | 2020-06-17 | 2020-07-03 | 2020-06-28 04:00 | 2020-07-05 | 2020-07-07 16:00 | 2020-07-25 | 2020-07-12 16:00 | 2020-07-31 | 2020-07-17 20:00 | 2020-08-09 | 2020-07-20 20:00 | 2020-08-11 | 2020-07-28 08:00 | 2020-08-16 | 2020-07-28 20:00 | 2020-08-26 | 2020-08-07 20:00 | 72 | 51.8333 | -20.1667
Site25 | North | MTY | MACRO | NaaS Owned |  | 2020-06-15 | 2020-06-16 | 2020-07-03 | 2020-06-30 04:00 | 2020-07-05 | 2020-07-05 16:00 | 2020-07-25 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-16 20:00 | 2020-08-09 | 2020-07-21 20:00 | 2020-08-11 | 2020-07-27 08:00 | 2020-08-16 | 2020-07-27 20:00 | 2020-08-26 | 2020-08-04 20:00 | 72 | 49.8333 | -22.1667
Site26 | North | ZAC | MINI | NaaS Owned |  | 2020-06-15 | 2020-06-18 | 2020-07-03 | 2020-07-01 04:00 | 2020-07-05 | 2020-07-08 16:00 | 2020-07-25 | 2020-07-10 16:00 | 2020-07-31 | 2020-07-15 20:00 | 2020-08-09 | 2020-07-24 20:00 | 2020-08-11 | 2020-07-27 08:00 | 2020-08-16 | 2020-07-27 20:00 | 2020-08-26 | 2020-08-03 20:00 | 72 | 46.8333 | -25.1667
Site27 | Center | GTO | SMALL | NeatTowers |  | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-07 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-06 | 2020-07-25 20:00 | 2020-08-15 | 2020-08-01 20:00 | 2020-08-17 | 2020-08-01 08:00 | 2020-08-22 | 2020-08-04 20:00 | 2020-09-01 | 2020-08-10 20:00 | 72 | 47.8333 | -24.1667
Site28 | Center | QRO | MACRO | SuperTowers |  | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-10 16:00 | 2020-07-31 | 2020-07-15 16:00 | 2020-08-06 | 2020-07-24 20:00 | 2020-08-15 | 2020-07-31 20:00 | 2020-08-17 | 2020-08-01 08:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-09-01 | 2020-08-12 20:00 | 72 | 49.8333 | -22.1667
Site29 | South | VER | MINI | PremiumTowers |  | 2020-06-21 | 2020-06-23 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-12 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-06 | 2020-07-24 20:00 | 2020-08-15 | 2020-07-27 20:00 | 2020-08-17 | 2020-07-31 08:00 | 2020-08-22 | 2020-08-04 20:00 | 2020-09-01 | 2020-08-12 20:00 | 72 | 50.8333 | -21.1667
Site30 | South | CHI | SMALL | SuperTowers |  | 2020-06-21 | 2020-06-21 | 2020-07-09 | 2020-07-03 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-06 | 2020-07-24 20:00 | 2020-08-15 | 2020-07-31 20:00 | 2020-08-17 | 2020-07-31 08:00 | 2020-08-22 | 2020-08-02 20:00 | 2020-09-01 | 2020-08-11 20:00 | 72 | 51.8333 | -20.1667
Site31 | North | MTY | MINI | PremiumTowers |  | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-03 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-06 | 2020-07-22 20:00 | 2020-08-15 | 2020-08-01 20:00 | 2020-08-17 | 2020-07-29 08:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-09-01 | 2020-08-12 20:00 | 72 | 49.8333 | -22.1667
Site32 | North | ZAC | SMALL | NaaS Owned |  | 2020-06-21 | 2020-06-22 | 2020-07-09 | 2020-07-05 04:00 | 2020-07-11 | 2020-07-12 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-06 | 2020-07-25 20:00 | 2020-08-15 | 2020-07-30 20:00 | 2020-08-17 | 2020-07-31 08:00 | 2020-08-22 | 2020-08-05 20:00 | 2020-09-01 | 2020-08-10 20:00 | 72 | 49.8333 | -22.1667
Site33 | Center | GTO | MACRO | NaaS Owned |  | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-06 | 2020-07-24 20:00 | 2020-08-15 | 2020-07-30 20:00 | 2020-08-17 | 2020-07-31 08:00 | 2020-08-22 | 2020-08-04 20:00 | 2020-09-01 | 2020-08-14 20:00 | 72 | 51.8333 | -20.1667
Site34 | Center | QRO | MINI | NeatTowers |  | 2020-06-21 | 2020-06-24 | 2020-07-09 | 2020-07-08 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-15 16:00 | 2020-08-06 | 2020-07-23 20:00 | 2020-08-15 | 2020-07-26 20:00 | 2020-08-17 | 2020-07-29 08:00 | 2020-08-22 | 2020-08-01 20:00 | 2020-09-01 | 2020-08-10 20:00 | 72 | 47.8333 | -24.1667
Site35 | South | VER | SMALL | NeatTowers |  | 2020-06-21 | 2020-06-23 | 2020-07-09 | 2020-07-06 04:00 | 2020-07-11 | 2020-07-13 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-06 | 2020-07-22 20:00 | 2020-08-15 | 2020-07-31 20:00 | 2020-08-17 | 2020-08-02 08:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-09-01 | 2020-08-10 20:00 | 72 | 48.8333 | -23.1667
Site36 | South | CHI | MACRO | SuperTowers |  | 2020-06-21 | 2020-06-26 | 2020-07-09 | 2020-07-07 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-06 | 2020-07-23 20:00 | 2020-08-15 | 2020-07-30 20:00 | 2020-08-17 | 2020-08-03 08:00 | 2020-08-22 | 2020-08-05 20:00 | 2020-09-01 | 2020-08-13 20:00 | 72 | 48.8333 | -23.1667
Site37 | North | MTY | MINI | PremiumTowers |  | 2020-06-21 | 2020-06-25 | 2020-07-09 | 2020-07-03 04:00 | 2020-07-11 | 2020-07-14 16:00 | 2020-07-31 | 2020-07-17 16:00 | 2020-08-06 | 2020-07-23 20:00 | 2020-08-15 | 2020-07-27 20:00 | 2020-08-17 | 2020-08-02 08:00 | 2020-08-22 | 2020-08-05 20:00 | 2020-09-01 | 2020-08-13 20:00 | 72 | 49.8333 | -22.1667
Site38 | North | ZAC | SMALL | NaaS Owned |  | 2020-06-21 | 2020-06-23 | 2020-07-09 | 2020-07-07 04:00 | 2020-07-11 | 2020-07-15 16:00 | 2020-07-31 | 2020-07-18 16:00 | 2020-08-06 | 2020-07-25 20:00 | 2020-08-15 | 2020-07-28 20:00 | 2020-08-17 | 2020-07-31 08:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-09-01 | 2020-08-12 20:00 | 72 | 50.8333 | -21.1667
Site39 | Center | GTO | MACRO | NaaS Owned |  | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-12 04:00 | 2020-07-18 | 2020-07-20 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-13 | 2020-07-30 20:00 | 2020-08-22 | 2020-08-06 20:00 | 2020-08-24 | 2020-08-06 08:00 | 2020-08-29 | 2020-08-11 20:00 | 2020-09-08 | 2020-08-17 20:00 | 72 | 46.8333 | -25.1667
Site40 | Center | QRO | MINI | SuperTowers |  | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-10 04:00 | 2020-07-18 | 2020-07-21 16:00 | 2020-08-07 | 2020-07-23 16:00 | 2020-08-13 | 2020-08-01 20:00 | 2020-08-22 | 2020-08-06 20:00 | 2020-08-24 | 2020-08-09 08:00 | 2020-08-29 | 2020-08-11 20:00 | 2020-09-08 | 2020-08-19 20:00 | 72 | 48.8333 | -23.1667
Site41 | South | VER | SMALL | PremiumTowers |  | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-13 | 2020-08-01 20:00 | 2020-08-22 | 2020-08-01 20:00 | 2020-08-24 | 2020-08-05 08:00 | 2020-08-29 | 2020-08-09 20:00 | 2020-09-08 | 2020-08-18 20:00 | 72 | 47.8333 | -24.1667
Site42 | South | CHI | MACRO | NaaS Owned |  | 2020-06-28 | 2020-07-02 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-23 16:00 | 2020-08-13 | 2020-07-31 20:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-08-24 | 2020-08-07 08:00 | 2020-08-29 | 2020-08-12 20:00 | 2020-09-08 | 2020-08-20 20:00 | 72 | 49.8333 | -22.1667
Site43 | North | MTY | MINI | NaaS Owned |  | 2020-06-28 | 2020-06-30 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-13 | 2020-07-29 20:00 | 2020-08-22 | 2020-08-05 20:00 | 2020-08-24 | 2020-08-06 08:00 | 2020-08-29 | 2020-08-12 20:00 | 2020-09-08 | 2020-08-18 20:00 | 72 | 49.8333 | -22.1667
Site44 | North | ZAC | SMALL | NeatTowers |  | 2020-06-28 | 2020-06-29 | 2020-07-16 | 2020-07-12 04:00 | 2020-07-18 | 2020-07-18 16:00 | 2020-08-07 | 2020-07-24 16:00 | 2020-08-13 | 2020-07-28 20:00 | 2020-08-22 | 2020-08-08 20:00 | 2020-08-24 | 2020-08-06 08:00 | 2020-08-29 | 2020-08-11 20:00 | 2020-09-08 | 2020-08-21 20:00 | 72 | 53.8333 | -18.1667
Site45 | Center | GTO | SMALL | SuperTowers |  | 2020-06-28 | 2020-07-03 | 2020-07-16 | 2020-07-14 04:00 | 2020-07-18 | 2020-07-20 16:00 | 2020-08-07 | 2020-07-27 16:00 | 2020-08-13 | 2020-07-29 20:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-08-24 | 2020-08-06 08:00 | 2020-08-29 | 2020-08-10 20:00 | 2020-09-08 | 2020-08-18 20:00 | 72 | 46.8333 | -25.1667
Site46 | Center | QRO | MACRO | PremiumTowers |  | 2020-06-28 | 2020-06-29 | 2020-07-16 | 2020-07-14 04:00 | 2020-07-18 | 2020-07-19 16:00 | 2020-08-07 | 2020-07-27 16:00 | 2020-08-13 | 2020-07-30 20:00 | 2020-08-22 | 2020-08-02 20:00 | 2020-08-24 | 2020-08-06 08:00 | 2020-08-29 | 2020-08-10 20:00 | 2020-09-08 | 2020-08-18 20:00 | 72 | 50.8333 | -21.1667
Site47 | South | VER | MINI | NaaS Owned |  | 2020-06-28 | 2020-06-28 | 2020-07-16 | 2020-07-13 04:00 | 2020-07-18 | 2020-07-22 16:00 | 2020-08-07 | 2020-07-26 16:00 | 2020-08-13 | 2020-07-31 20:00 | 2020-08-22 | 2020-08-06 20:00 | 2020-08-24 | 2020-08-07 08:00 | 2020-08-29 | 2020-08-08 20:00 | 2020-09-08 | 2020-08-19 20:00 | 72 | 52.8333 | -19.1667
Site48 | South | CHI | SMALL | NaaS Owned |  | 2020-06-28 | 2020-07-01 | 2020-07-16 | 2020-07-14 04:00 | 2020-07-18 | 2020-07-17 16:00 | 2020-08-07 | 2020-07-27 16:00 | 2020-08-13 | 2020-08-01 20:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-08-24 | 2020-08-05 08:00 | 2020-08-29 | 2020-08-11 20:00 | 2020-09-08 | 2020-08-19 20:00 | 72 | 49.8333 | -22.1667
Site49 | North | ZAC | MACRO | PremiumTowers |  | 2020-06-28 | 2020-06-30 | 2020-07-16 | 2020-07-12 04:00 | 2020-07-18 | 2020-07-21 16:00 | 2020-08-07 | 2020-07-24 16:00 | 2020-08-13 | 2020-08-01 20:00 | 2020-08-22 | 2020-08-05 20:00 | 2020-08-24 | 2020-08-09 08:00 | 2020-08-29 | 2020-08-12 20:00 | 2020-09-08 | 2020-08-20 20:00 | 72 | 51.8333 | -20.1667
Site50 | North | GTO | MINI | NaaS Owned |  | 2020-06-28 | 2020-06-28 | 2020-07-16 | 2020-07-10 04:00 | 2020-07-18 | 2020-07-22 16:00 | 2020-08-07 | 2020-07-25 16:00 | 2020-08-13 | 2020-07-29 20:00 | 2020-08-22 | 2020-08-03 20:00 | 2020-08-24 | 2020-08-06 08:00 | 2020-08-29 | 2020-08-08 20:00 | 2020-09-08 | 2020-08-17 20:00 | 72 | 50.8333 | -21.1667
Site51 | Center | QRO | SMALL | NaaS Owned |  | 2020-06-28 | 2020-07-01 | 2020-07-16 | 2020-07-11 04:00 | 2020-07-18 | 2020-07-18 16:00 | 2020-08-07 | 2020-07-24 16:00 | 2020-08-13 | 2020-07-28 20:00 | 2020-08-22 | 2020-08-07 20:00 | 2020-08-24 | 2020-08-07 08:00 | 2020-08-29 | 2020-08-10 20:00 | 2020-09-08 | 2020-08-17 20:00 | 72 | 47.8333 | -24.1667
Site52 | Center | VER | MACRO | SuperTowers |  | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-14 04:00 | 2020-07-21 | 2020-07-20 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-16 | 2020-08-04 20:00 | 2020-08-25 | 2020-08-05 20:00 | 2020-08-27 | 2020-08-10 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-21 20:00 | 72 | 49.8333 | -22.1667
Site53 | South | CHI | MINI | PremiumTowers |  | 2020-07-01 | 2020-07-01 | 2020-07-19 | 2020-07-14 04:00 | 2020-07-21 | 2020-07-21 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-16 | 2020-08-04 20:00 | 2020-08-25 | 2020-08-11 20:00 | 2020-08-27 | 2020-08-09 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-19 20:00 | 72 | 49.8333 | -22.1667
Site54 | South | MTY | SMALL | NaaS Owned |  | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-18 04:00 | 2020-07-21 | 2020-07-25 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-16 | 2020-08-04 20:00 | 2020-08-25 | 2020-08-07 20:00 | 2020-08-27 | 2020-08-12 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-24 20:00 | 72 | 53.8333 | -18.1667
Site55 | North | ZAC | MACRO | NaaS Owned |  | 2020-07-01 | 2020-07-05 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-16 | 2020-08-05 20:00 | 2020-08-25 | 2020-08-08 20:00 | 2020-08-27 | 2020-08-09 08:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-11 | 2020-08-22 20:00 | 72 | 48.8333 | -23.1667
Site56 | North | GTO | MINI | NeatTowers |  | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-18 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-25 16:00 | 2020-08-16 | 2020-07-31 20:00 | 2020-08-25 | 2020-08-07 20:00 | 2020-08-27 | 2020-08-08 08:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-11 | 2020-08-21 20:00 | 72 | 50.8333 | -21.1667
Site57 | Center | QRO | SMALL | SuperTowers |  | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-17 04:00 | 2020-07-21 | 2020-07-22 16:00 | 2020-08-10 | 2020-07-28 16:00 | 2020-08-16 | 2020-08-03 20:00 | 2020-08-25 | 2020-08-07 20:00 | 2020-08-27 | 2020-08-11 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-20 20:00 | 72 | 49.8333 | -22.1667
Site58 | Center | MTY | MACRO | SuperTowers |  | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-25 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-16 | 2020-08-01 20:00 | 2020-08-25 | 2020-08-06 20:00 | 2020-08-27 | 2020-08-10 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-22 20:00 | 72 | 50.8333 | -21.1667
Site59 | South | ZAC | MINI | PremiumTowers |  | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-17 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-27 16:00 | 2020-08-16 | 2020-08-01 20:00 | 2020-08-25 | 2020-08-10 20:00 | 2020-08-27 | 2020-08-10 08:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-11 | 2020-08-24 20:00 | 72 | 53.8333 | -18.1667
Site60 | South | GTO | SMALL | NaaS Owned |  | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-13 04:00 | 2020-07-21 | 2020-07-25 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-16 | 2020-08-02 20:00 | 2020-08-25 | 2020-08-09 20:00 | 2020-08-27 | 2020-08-09 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-20 20:00 | 72 | 48.8333 | -23.1667
Site61 | North | QRO | MACRO | NaaS Owned |  | 2020-07-01 | 2020-07-01 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-16 | 2020-08-04 20:00 | 2020-08-25 | 2020-08-06 20:00 | 2020-08-27 | 2020-08-11 08:00 | 2020-09-01 | 2020-08-14 20:00 | 2020-09-11 | 2020-08-23 20:00 | 72 | 53.8333 | -18.1667
Site62 | North | VER | MINI | NeatTowers |  | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-18 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-16 | 2020-08-01 20:00 | 2020-08-25 | 2020-08-07 20:00 | 2020-08-27 | 2020-08-08 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-23 20:00 | 72 | 51.8333 | -20.1667
Site63 | Center | CHI | SMALL | NeatTowers |  | 2020-07-01 | 2020-07-05 | 2020-07-19 | 2020-07-14 04:00 | 2020-07-21 | 2020-07-20 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-16 | 2020-07-31 20:00 | 2020-08-25 | 2020-08-11 20:00 | 2020-08-27 | 2020-08-11 08:00 | 2020-09-01 | 2020-08-13 20:00 | 2020-09-11 | 2020-08-21 20:00 | 72 | 47.8333 | -24.1667
Site64 | Center | MTY | MACRO | SuperTowers |  | 2020-07-01 | 2020-07-06 | 2020-07-19 | 2020-07-17 04:00 | 2020-07-21 | 2020-07-22 16:00 | 2020-08-10 | 2020-07-27 16:00 | 2020-08-16 | 2020-08-04 20:00 | 2020-08-25 | 2020-08-09 20:00 | 2020-08-27 | 2020-08-08 08:00 | 2020-09-01 | 2020-08-14 20:00 | 2020-09-11 | 2020-08-23 20:00 | 72 | 48.8333 | -23.1667
Site65 | South | ZAC | MINI | PremiumTowers |  | 2020-07-01 | 2020-07-02 | 2020-07-19 | 2020-07-16 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-29 16:00 | 2020-08-16 | 2020-08-01 20:00 | 2020-08-25 | 2020-08-07 20:00 | 2020-08-27 | 2020-08-10 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-24 20:00 | 72 | 53.8333 | -18.1667
Site66 | South | GTO | SMALL | NaaS Owned |  | 2020-07-01 | 2020-07-03 | 2020-07-19 | 2020-07-15 04:00 | 2020-07-21 | 2020-07-24 16:00 | 2020-08-10 | 2020-07-28 16:00 | 2020-08-16 | 2020-08-01 20:00 | 2020-08-25 | 2020-08-08 20:00 | 2020-08-27 | 2020-08-09 08:00 | 2020-09-01 | 2020-08-14 20:00 | 2020-09-11 | 2020-08-23 20:00 | 72 | 51.8333 | -20.1667
Site67 | North | QRO | MACRO | NaaS Owned |  | 2020-07-01 | 2020-07-05 | 2020-07-19 | 2020-07-13 04:00 | 2020-07-21 | 2020-07-23 16:00 | 2020-08-10 | 2020-07-26 16:00 | 2020-08-16 | 2020-08-01 20:00 | 2020-08-25 | 2020-08-05 20:00 | 2020-08-27 | 2020-08-10 08:00 | 2020-09-01 | 2020-08-15 20:00 | 2020-09-11 | 2020-08-20 20:00 | 72 | 46.8333 | -25.1667
Site68 | North | VER | MINI | SuperTowers |  | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-23 | 2020-08-08 20:00 | 2020-09-01 | 2020-08-17 20:00 | 2020-09-03 | 2020-08-18 08:00 | 2020-09-08 | 2020-08-22 20:00 | 2020-09-18 | 2020-08-30 20:00 | 72 | 52.8333 | -19.1667
Site69 | Center | CHI | SMALL | PremiumTowers |  | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-06 16:00 | 2020-08-23 | 2020-08-12 20:00 | 2020-09-01 | 2020-08-18 20:00 | 2020-09-03 | 2020-08-20 08:00 | 2020-09-08 | 2020-08-18 20:00 | 2020-09-18 | 2020-08-31 20:00 | 72 | 53.8333 | -18.1667
Site70 | Center | MTY | MACRO | NaaS Owned |  | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-24 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-06 16:00 | 2020-08-23 | 2020-08-08 20:00 | 2020-09-01 | 2020-08-14 20:00 | 2020-09-03 | 2020-08-17 08:00 | 2020-09-08 | 2020-08-19 20:00 | 2020-09-18 | 2020-08-30 20:00 | 72 | 50.8333 | -21.1667
Site71 | South | ZAC | MINI | NaaS Owned |  | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-20 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-23 | 2020-08-10 20:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-03 | 2020-08-18 08:00 | 2020-09-08 | 2020-08-21 20:00 | 2020-09-18 | 2020-08-26 20:00 | 72 | 48.8333 | -23.1667
Site72 | South | GTO | SMALL | NeatTowers |  | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-22 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-23 | 2020-08-09 20:00 | 2020-09-01 | 2020-08-13 20:00 | 2020-09-03 | 2020-08-15 08:00 | 2020-09-08 | 2020-08-18 20:00 | 2020-09-18 | 2020-08-28 20:00 | 72 | 49.8333 | -22.1667
Site73 | North | QRO | MACRO | SuperTowers |  | 2020-07-08 | 2020-07-12 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-23 | 2020-08-11 20:00 | 2020-09-01 | 2020-08-13 20:00 | 2020-09-03 | 2020-08-15 08:00 | 2020-09-08 | 2020-08-18 20:00 | 2020-09-18 | 2020-08-28 20:00 | 72 | 47.8333 | -24.1667
Site74 | North | VER | MINI | PremiumTowers |  | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-27 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-23 | 2020-08-10 20:00 | 2020-09-01 | 2020-08-16 20:00 | 2020-09-03 | 2020-08-18 08:00 | 2020-09-08 | 2020-08-19 20:00 | 2020-09-18 | 2020-08-26 20:00 | 72 | 46.8333 | -25.1667
Site75 | Center | CHI | SMALL | NaaS Owned |  | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-20 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-23 | 2020-08-11 20:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-03 | 2020-08-19 08:00 | 2020-09-08 | 2020-08-23 20:00 | 2020-09-18 | 2020-08-28 20:00 | 72 | 50.8333 | -21.1667
Site76 | Center | MTY | MACRO | NaaS Owned |  | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-08-01 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-23 | 2020-08-09 20:00 | 2020-09-01 | 2020-08-17 20:00 | 2020-09-03 | 2020-08-15 08:00 | 2020-09-08 | 2020-08-23 20:00 | 2020-09-18 | 2020-08-29 20:00 | 72 | 50.8333 | -21.1667
Site77 | South | ZAC | MINI | PremiumTowers |  | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-20 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-01 16:00 | 2020-08-23 | 2020-08-11 20:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-03 | 2020-08-16 08:00 | 2020-09-08 | 2020-08-21 20:00 | 2020-09-18 | 2020-08-30 20:00 | 72 | 51.8333 | -20.1667
Site78 | South | GTO | SMALL | NaaS Owned |  | 2020-07-08 | 2020-07-10 | 2020-07-26 | 2020-07-23 04:00 | 2020-07-28 | 2020-07-27 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-23 | 2020-08-09 20:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-03 | 2020-08-20 08:00 | 2020-09-08 | 2020-08-23 20:00 | 2020-09-18 | 2020-08-30 20:00 | 72 | 51.8333 | -20.1667
Site79 | North | QRO | MACRO | NaaS Owned |  | 2020-07-08 | 2020-07-12 | 2020-07-26 | 2020-07-22 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-23 | 2020-08-07 20:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-03 | 2020-08-17 08:00 | 2020-09-08 | 2020-08-22 20:00 | 2020-09-18 | 2020-08-31 20:00 | 72 | 50.8333 | -21.1667
Site80 | North | VER | MINI | SuperTowers |  | 2020-07-08 | 2020-07-13 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-02 16:00 | 2020-08-23 | 2020-08-08 20:00 | 2020-09-01 | 2020-08-17 20:00 | 2020-09-03 | 2020-08-19 08:00 | 2020-09-08 | 2020-08-20 20:00 | 2020-09-18 | 2020-08-29 20:00 | 72 | 47.8333 | -24.1667
Site81 | Center | CHI | SMALL | PremiumTowers |  | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-05 16:00 | 2020-08-23 | 2020-08-11 20:00 | 2020-09-01 | 2020-08-13 20:00 | 2020-09-03 | 2020-08-18 08:00 | 2020-09-08 | 2020-08-23 20:00 | 2020-09-18 | 2020-08-31 20:00 | 72 | 53.8333 | -18.1667
Site82 | Center | MTY | MACRO | NaaS Owned |  | 2020-07-08 | 2020-07-08 | 2020-07-26 | 2020-07-24 04:00 | 2020-07-28 | 2020-07-29 16:00 | 2020-08-17 | 2020-08-03 16:00 | 2020-08-23 | 2020-08-07 20:00 | 2020-09-01 | 2020-08-12 20:00 | 2020-09-03 | 2020-08-19 08:00 | 2020-09-08 | 2020-08-22 20:00 | 2020-09-18 | 2020-08-29 20:00 | 72 | 52.8333 | -19.1667
Site83 | South | ZAC | MINI | NaaS Owned |  | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-31 16:00 | 2020-08-17 | 2020-08-06 16:00 | 2020-08-23 | 2020-08-09 20:00 | 2020-09-01 | 2020-08-18 20:00 | 2020-09-03 | 2020-08-17 08:00 | 2020-09-08 | 2020-08-18 20:00 | 2020-09-18 | 2020-08-30 20:00 | 72 | 52.8333 | -19.1667
Site84 | South | GTO | SMALL | NeatTowers |  | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-02 16:00 | 2020-08-23 | 2020-08-11 20:00 | 2020-09-01 | 2020-08-14 20:00 | 2020-09-03 | 2020-08-19 08:00 | 2020-09-08 | 2020-08-20 20:00 | 2020-09-18 | 2020-08-30 20:00 | 72 | 50.8333 | -21.1667
Site85 | North | QRO | MACRO | SuperTowers |  | 2020-07-08 | 2020-07-11 | 2020-07-26 | 2020-07-25 04:00 | 2020-07-28 | 2020-07-28 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-23 | 2020-08-11 20:00 | 2020-09-01 | 2020-08-11 20:00 | 2020-09-03 | 2020-08-16 08:00 | 2020-09-08 | 2020-08-23 20:00 | 2020-09-18 | 2020-08-28 20:00 | 72 | 48.8333 | -23.1667
Site86 | North | VER | MINI | PremiumTowers |  | 2020-07-08 | 2020-07-09 | 2020-07-26 | 2020-07-21 04:00 | 2020-07-28 | 2020-07-30 16:00 | 2020-08-17 | 2020-08-04 16:00 | 2020-08-23 | 2020-08-11 20:00 | 2020-09-01 | 2020-08-18 20:00 | 2020-09-03 | 2020-08-18 08:00 | 2020-09-08 | 2020-08-21 20:00 | 2020-09-18 | 2020-08-30 20:00 | 72 | 52.8333 | -19.1667
Site87 | Center | CHI | SMALL | SuperTowers |  | 2020-07-15 | 2020-07-15 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-06 16:00 | 2020-08-24 | 2020-08-08 16:00 | 2020-08-30 | 2020-08-15 20:00 | 2020-09-08 | 2020-08-23 20:00 | 2020-09-10 | 2020-08-23 08:00 | 2020-09-15 | 2020-08-27 20:00 | 2020-09-25 | 2020-09-03 20:00 | 72 | 50.8333 | -21.1667
Site88 | Center | MTY | MINI | PremiumTowers |  | 2020-07-15 | 2020-07-20 | 2020-08-02 | 2020-07-30 04:00 | 2020-08-04 | 2020-08-03 16:00 | 2020-08-24 | 2020-08-09 16:00 | 2020-08-30 | 2020-08-17 20:00 | 2020-09-08 | 2020-08-20 20:00 | 2020-09-10 | 2020-08-26 08:00 | 2020-09-15 | 2020-08-28 20:00 | 2020-09-25 | 2020-09-03 20:00 | 72 | 45.8333 | -26.1667
Site89 | South | ZAC | SMALL | NaaS Owned |  | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-08-01 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-08-30 | 2020-08-18 20:00 | 2020-09-08 | 2020-08-21 20:00 | 2020-09-10 | 2020-08-26 08:00 | 2020-09-15 | 2020-08-27 20:00 | 2020-09-25 | 2020-09-04 20:00 | 72 | 48.8333 | -23.1667
Site90 | South | GTO | MACRO | NaaS Owned |  | 2020-07-15 | 2020-07-15 | 2020-08-02 | 2020-07-31 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-08 16:00 | 2020-08-30 | 2020-08-17 20:00 | 2020-09-08 | 2020-08-19 20:00 | 2020-09-10 | 2020-08-24 08:00 | 2020-09-15 | 2020-08-30 20:00 | 2020-09-25 | 2020-09-05 20:00 | 72 | 52.8333 | -19.1667
Site91 | North | QRO | MINI | NeatTowers |  | 2020-07-15 | 2020-07-17 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-08-30 | 2020-08-16 20:00 | 2020-09-08 | 2020-08-21 20:00 | 2020-09-10 | 2020-08-26 08:00 | 2020-09-15 | 2020-08-28 20:00 | 2020-09-25 | 2020-09-02 20:00 | 72 | 47.8333 | -24.1667
Site92 | North | VER | SMALL | NeatTowers |  | 2020-07-15 | 2020-07-19 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-06 16:00 | 2020-08-24 | 2020-08-11 16:00 | 2020-08-30 | 2020-08-17 20:00 | 2020-09-08 | 2020-08-23 20:00 | 2020-09-10 | 2020-08-26 08:00 | 2020-09-15 | 2020-08-27 20:00 | 2020-09-25 | 2020-09-02 20:00 | 72 | 45.8333 | -26.1667
Site93 | Center | CHI | MACRO | SuperTowers |  | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-30 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-08-30 | 2020-08-17 20:00 | 2020-09-08 | 2020-08-20 20:00 | 2020-09-10 | 2020-08-23 08:00 | 2020-09-15 | 2020-08-27 20:00 | 2020-09-25 | 2020-09-02 20:00 | 72 | 46.8333 | -25.1667
Site94 | Center | MTY | MINI | PremiumTowers |  | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-07 16:00 | 2020-08-24 | 2020-08-09 16:00 | 2020-08-30 | 2020-08-15 20:00 | 2020-09-08 | 2020-08-24 20:00 | 2020-09-10 | 2020-08-27 08:00 | 2020-09-15 | 2020-08-27 20:00 | 2020-09-25 | 2020-09-03 20:00 | 72 | 47.8333 | -24.1667
Site95 | South | ZAC | SMALL | NaaS Owned |  | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-29 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-12 16:00 | 2020-08-30 | 2020-08-15 20:00 | 2020-09-08 | 2020-08-22 20:00 | 2020-09-10 | 2020-08-23 08:00 | 2020-09-15 | 2020-08-26 20:00 | 2020-09-25 | 2020-09-06 20:00 | 72 | 50.8333 | -21.1667
Site96 | South | GTO | MACRO | NaaS Owned |  | 2020-07-15 | 2020-07-19 | 2020-08-02 | 2020-08-01 04:00 | 2020-08-04 | 2020-08-05 16:00 | 2020-08-24 | 2020-08-08 16:00 | 2020-08-30 | 2020-08-18 20:00 | 2020-09-08 | 2020-08-20 20:00 | 2020-09-10 | 2020-08-26 08:00 | 2020-09-15 | 2020-08-26 20:00 | 2020-09-25 | 2020-09-06 20:00 | 72 | 49.8333 | -22.1667
Site97 | North | QRO | MINI | SuperTowers |  | 2020-07-15 | 2020-07-16 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-08 16:00 | 2020-08-24 | 2020-08-10 16:00 | 2020-08-30 | 2020-08-19 20:00 | 2020-09-08 | 2020-08-19 20:00 | 2020-09-10 | 2020-08-25 08:00 | 2020-09-15 | 2020-08-26 20:00 | 2020-09-25 | 2020-09-02 20:00 | 72 | 48.8333 | -23.1667
Site98 | North | VER | SMALL | PremiumTowers |  | 2020-07-15 | 2020-07-17 | 2020-08-02 | 2020-07-28 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-12 16:00 | 2020-08-30 | 2020-08-16 20:00 | 2020-09-08 | 2020-08-19 20:00 | 2020-09-10 | 2020-08-22 08:00 | 2020-09-15 | 2020-08-28 20:00 | 2020-09-25 | 2020-09-05 20:00 | 72 | 50.8333 | -21.1667
Site99 | Center | CHI | MACRO | NaaS Owned |  | 2020-07-15 | 2020-07-19 | 2020-08-02 | 2020-07-29 04:00 | 2020-08-04 | 2020-08-04 16:00 | 2020-08-24 | 2020-08-12 16:00 | 2020-08-30 | 2020-08-16 20:00 | 2020-09-08 | 2020-08-20 20:00 | 2020-09-10 | 2020-08-23 08:00 | 2020-09-15 | 2020-08-27 20:00 | 2020-09-25 | 2020-09-04 20:00 | 72 | 47.8333 | -24.1667
Site100 | Center | MTY | MINI | NaaS Owned |  | 2020-07-15 | 2020-07-18 | 2020-08-02 | 2020-07-30 04:00 | 2020-08-04 | 2020-08-07 16:00 | 2020-08-24 | 2020-08-11 16:00 | 2020-08-30 | 2020-08-18 20:00 | 2020-09-08 | 2020-08-24 20:00 | 2020-09-10 | 2020-08-26 08:00 | 2020-09-15 | 2020-08-29 20:00 | 2020-09-25 | 2020-09-04 20:00 | 72 | 48.8333 | -23.1667
Formulas:
SiteEngineeringDocument_BL = Table_SiteMilestonesTracking[[#This Row],[TechnicalSiteSurvey_BL]]+t1_SiteSurveyBL+t2_SiteEngineeringDocumentBL
SiteConstructionWorkOrder_BL = Table_SiteMilestonesTracking[[#This Row],[SiteEngineeringDocument_BL]]+t3_SiteConstructionWorkOrderBL
CivilWorks_BL = Table_SiteMilestonesTracking[[#This Row],[SiteConstructionWorkOrder_BL]]+t4_CivilWorksBL
MechanicalWorks_BL = Table_SiteMilestonesTracking[[#This Row],[CivilWorks_BL]]+t5_MechanicalWorksBL
ElectricalWorks_BL = Table_SiteMilestonesTracking[[#This Row],[MechanicalWorks_BL]]+t6_ElectricalWorksBL
ConstructionAcceptance_BL = Table_SiteMilestonesTracking[[#This Row],[ElectricalWorks_BL]]+t7_ConstructionAcceptanceBL
ReadyForInstallation_BL = Table_SiteMilestonesTracking[[#This Row],[ConstructionAcceptance_BL]]+t8_ReadyForInstallationBL
SiteInOperations_BL = Table_SiteMilestonesTracking[[#This Row],[ReadyForInstallation_BL]]+t9_SiteInOperationsBL

## Summary Tracking Sheet
Deployment Tracking Summary
|  |  |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100 |  | 100
Year | Week | StartDate | EndDate | TechnicalSiteSurvey_BL | TechnicalSiteSurvey_BL(SUM) | TechnicalSiteSurvey_AC | TechnicalSiteSurvey_AC(SUM) | SiteEngineeringDocument_BL | SiteEngineeringDocument_BL(SUM) | SiteEngineeringDocument_AC | SiteEngineeringDocument_AC(SUM) | SiteConstructionWorkOrder_BL | SiteConstructionWorkOrder_BL(SUM) | SiteConstructionWorkOrder_AC | SiteConstructionWorkOrder_AC(SUM) | CivilWorks_BL | CivilWorks_BL(SUM) | CivilWorks_AC | CivilWorks_AC(SUM) | MechanicalWorks_BL | MechanicalWorks_BL(SUM) | MechanicalWorks_AC | MechanicalWorks_AC(SUM) | ElectricalWorks_BL | ElectricalWorks_BL(SUM) | ElectricalWorks_AC | ElectricalWorks_AC(SUM) | ConstructionAcceptance_BL | ConstructionAcceptance_BL(SUM) | ConstructionAcceptance_AC | ConstructionAcceptance_AC(SUM) | ReadyForInstallation_BL | ReadyForInstallation_BL(SUM) | ReadyForInstallation_AC | ReadyForInstallation_AC(SUM) | SiteInOperations_BL | SiteInOperations_BL(SUM) | SiteInOperations_AC | SiteInOperations_AC(SUM)
2020 | 1 | 2019-12-30 | 2020-01-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 2 | 2020-01-06 | 2020-01-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 3 | 2020-01-13 | 2020-01-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 4 | 2020-01-20 | 2020-01-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 5 | 2020-01-27 | 2020-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 6 | 2020-02-03 | 2020-02-09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 7 | 2020-02-10 | 2020-02-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 8 | 2020-02-17 | 2020-02-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 9 | 2020-02-24 | 2020-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 10 | 2020-03-02 | 2020-03-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 11 | 2020-03-09 | 2020-03-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 12 | 2020-03-16 | 2020-03-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 13 | 2020-03-23 | 2020-03-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 14 | 2020-03-30 | 2020-04-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 15 | 2020-04-06 | 2020-04-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 16 | 2020-04-13 | 2020-04-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 17 | 2020-04-20 | 2020-04-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 18 | 2020-04-27 | 2020-05-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 19 | 2020-05-04 | 2020-05-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 20 | 2020-05-11 | 2020-05-17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 21 | 2020-05-18 | 2020-05-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 22 | 2020-05-25 | 2020-05-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 23 | 2020-06-01 | 2020-06-07 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 24 | 2020-06-08 | 2020-06-14 | 9 | 16 | 9 | 16 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 25 | 2020-06-15 | 2020-06-21 | 22 | 38 | 11 | 27 | 7 | 7 | 8 | 9 | 7 | 7 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 26 | 2020-06-22 | 2020-06-28 | 13 | 51 | 13 | 40 | 9 | 16 | 9 | 18 | 9 | 16 | 10 | 11 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 27 | 2020-06-29 | 2020-07-05 | 16 | 67 | 26 | 66 | 10 | 26 | 12 | 30 | 10 | 26 | 10 | 21 | 0 | 0 | 7 | 13 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020 | 28 | 2020-07-06 | 2020-07-12 | 19 | 86 | 19 | 85 | 12 | 38 | 17 | 47 | 12 | 38 | 8 | 29 | 7 | 7 | 9 | 22 | 0 | 0 | 11 | 15 | 0 | 0 | 8 | 8 | 0 | 0 | 4 | 4 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
2020 | 29 | 2020-07-13 | 2020-07-19 | 14 | 100 | 14 | 99 | 29 | 67 | 20 | 67 | 13 | 51 | 16 | 45 | 9 | 16 | 16 | 38 | 7 | 7 | 11 | 26 | 0 | 0 | 8 | 16 | 0 | 0 | 10 | 14 | 0 | 0 | 7 | 8 | 0 | 0 | 0 | 0
2020 | 30 | 2020-07-20 | 2020-07-26 | 0 | 100 | 1 | 100 | 19 | 86 | 19 | 86 | 16 | 67 | 22 | 67 | 10 | 26 | 15 | 53 | 9 | 16 | 12 | 38 | 7 | 7 | 11 | 27 | 0 | 0 | 6 | 20 | 0 | 0 | 10 | 18 | 0 | 0 | 7 | 7
2020 | 31 | 2020-07-27 | 2020-08-02 | 0 | 100 | 0 | 100 | 14 | 100 | 14 | 100 | 19 | 86 | 19 | 86 | 12 | 38 | 17 | 70 | 10 | 26 | 22 | 60 | 9 | 16 | 13 | 40 | 7 | 7 | 17 | 37 | 7 | 7 | 10 | 28 | 0 | 0 | 9 | 16
2020 | 32 | 2020-08-03 | 2020-08-09 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 14 | 100 | 13 | 51 | 21 | 91 | 12 | 38 | 16 | 76 | 10 | 26 | 24 | 64 | 9 | 16 | 21 | 58 | 9 | 16 | 13 | 41 | 0 | 0 | 10 | 26
2020 | 33 | 2020-08-10 | 2020-08-16 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 16 | 67 | 9 | 100 | 29 | 67 | 16 | 92 | 12 | 38 | 16 | 80 | 10 | 26 | 14 | 72 | 10 | 26 | 26 | 67 | 7 | 7 | 12 | 38
2020 | 34 | 2020-08-17 | 2020-08-23 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 19 | 86 | 0 | 100 | 19 | 86 | 8 | 100 | 13 | 51 | 18 | 98 | 12 | 38 | 19 | 91 | 12 | 38 | 19 | 86 | 9 | 16 | 26 | 64
2020 | 35 | 2020-08-24 | 2020-08-30 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 16 | 67 | 2 | 100 | 29 | 67 | 9 | 100 | 13 | 51 | 14 | 100 | 10 | 26 | 19 | 83
2020 | 36 | 2020-08-31 | 2020-09-06 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 19 | 86 | 0 | 100 | 19 | 86 | 0 | 100 | 16 | 67 | 0 | 100 | 12 | 38 | 17 | 100
2020 | 37 | 2020-09-07 | 2020-09-13 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 19 | 86 | 0 | 100 | 29 | 67 | 0 | 100
2020 | 38 | 2020-09-14 | 2020-09-20 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100 | 19 | 86 | 0 | 100
2020 | 39 | 2020-09-21 | 2020-09-27 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 14 | 100 | 0 | 100
2020 | 40 | 2020-09-28 | 2020-10-04 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100 | 0 | 100
Formulas:
StartDate = DATE(Table_SiteMilestoneTrackingSummary[[#This Row],[Year]],1,-2)-WEEKDAY(DATE(Table_SiteMilestoneTrackingSummary[[#This Row],[Year]],1,3))+Table_SiteMilestoneTrackingSummary[[#This Row],[Week]]*7
EndDate = Table_SiteMilestoneTrackingSummary[[#This Row],[StartDate]]+6

## Tracking Graphs
Deployment Schedule Visuals
Schedule Baseline | Schedule Actual
Site-accumulates per milestone, by week | Site-accumulates per milestone, by week
TechnicalSiteSurvey Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteEngineeringDocument Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteConstructionWorkOrder Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
CivilWorks Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
MechanicalWorks Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
ElectricalWorks Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
ConstructionAcceptance Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
ReadyForInstallation Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.
SiteInOperations Baseline vs Actual
Site-accumulates: baseline vs actual. The closer the lines, the better the performance approximates to the plan.