## Slide 1: Figure 1. Module Framework
Supply Chain Management
Strategic Plan & Scope
High Level Network Architecture
Strategic Plan & Scope
High Level Project Plan
Strategy & Scope
Industry & Market Data
Spectrum Regulation and Allocation
Target Market
Geodemographic Data
Financial status
Network Design
Deployment
Field Maintenance
Operations & Maintenance
Post-Launch Engineering

## Slide 2: Figure 2. High-Level Project Plan Functional View
High-Level Schedule
Key Tasks
Milestones
Timelines
Resource Plan
Resource Identification & Assessment
Resource Acquisition
Resource Utilization Plan
Financial Analysis*
CapEx & OpEx
Revenue
Financial Modeling
Communications Plan
Meeting Schedule
Communication Channels
Document Management
High Level
Project Plan
Strategic Objectives
Implementation Strategies
Available / Existing Resources
Organization Design
*Out of Scope

## Slide 3: Figure 3. Generic NaaS High Level Schedule.
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Jan
Dec
Build Project Plan
3 weeks
Headquarters Set-up
6 weeks
Hiring & Staffing
15 weeks
Commercial Agreements
12 weeks
Spectrum Acquisition
16 weeks
Other Resource Acquisition
10 weeks
Network Architecture Definition
14 weeks
Vendor Selection & Onboarding
8 weeks
Network HLD
4 weeks
Network LLD
12 weeks
Site Acquisition & Permits
16 weeks
Hardware Delivery
9 weeks
Site & Fiber Construction
8 weeks
Training & Preparation
8 weeks
Site Deployment
11 weeks
1
2
3, 4
5
6
7
8, 9
11
12,13,14
10
15
16
19
20
17
18
NaaS Initiative Launch
Project Plan Ready
HQ Set-up
TX Provider Agreements
Infra Sharing Agreements
1st Customer Agreement
Minimal Team Onboarding
Spectrum Acquired
Network Architecture Defined
Full Team Onboarded
HLD Ready
Construction Company Onboarded
Deployment Contractors Onboarded
Equipment Vendors Onboarded
Equipment PO Issued
Sites Acquired
Deployment Kickoff
Sites Built
1st Site On-Air
Deployment Complete
Milestones